## Sheet 1
RRH | District | HFacility | VDate | Section | Identified Gap | Agreed Action Point | Institution Responsible | Timelines | due_date | ActionMonth | ActionYr
ENTEBBE | GOMBA | GOMBE GENERAL HOSPITAL. | 2025-04-10 | Equipment | n.a
ENTEBBE | GOMBA | MADDU HC IV | 2025-04-10 | Equipment | Main lab fridge has a faulty compressor and AC in the automation room is also faulty | to follow up with Wabigalo engineering team to come and act on those faulty equipment | lab incharge/Facility incahrge | by 30th April 2024 | 2024-04-30 | Apr | 2024
ENTEBBE | GOMBA | MADDU HC IV | 2026-02-25 | Equipment | Equipments out of service | Follow up with IP to renew service contracts | Hub coordinator/DLFP | 2months | 2026-04-25 | Apr | 2026
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2024-12-09 | Equipment | HUMALYTE PLUS NOT FUNCTIONAL | NHLDS to engage NMS to have reagent cell pack supplied to entebbe regional referral hospital | NHLDS | immediately
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2025-04-14 | Equipment | mall budget allocated to the laboratory Dept | he hospital should lobby to have the laboratory budget increased to improve the running of the laboratory | HD | By next financial year
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFFERAL HOSPITAL | 2026-02-24 | Equipment | No service contracts for newly installed equipments | Follow up on service provider to deliver service schedule | Lab manager | 4 months | 2026-06-24 | Jun | 2026
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFFERAL HOSPITAL | 2026-02-24 | Equipment | Service providers not responding to calls | Continue follow up with service provider | Lab manager/IP | 2months | 2026-04-24 | Apr | 2026
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFFERAL HOSPITAL | 2026-02-24 | Equipment | Expired service contracts | Follow up with IP | LSSO | 2 Weeks
ENTEBBE | WAKISO | KASANGATI HEALTH CENTRE III | 2024-12-16 | Equipment | Faulty centrifuge and refrigerator | To contact the service provider to come and service the equipments | Lab manager | 2 months | 2025-02-16 | Feb | 2025
ENTEBBE | WAKISO | KOMAMBOGA HEALTH CENTRE III | 2024-12-13 | Equipment | Auxillary equipments are not calibrated. | To have all the auxillary equipment calibrated | Lab manager (kerchan Ronald) | 3 months | 2025-03-13 | Mar | 2025
ENTEBBE | WAKISO | WAKISO HEALTH CENTRE IV | 2024-12-12 | Equipment | Non functional biosafet cabinet for over ayear | to have it repaired or disposed off if its beyond repaire. | DLFP AND NHLDS | immediately
ENTEBBE | WAKISO | WAKISO IV | 2026-02-27 | Equipment | Machines not serviced on schedule due to expired service contracts | Work out with IP to have service contracts renewed | LSSO,LAB manager | 1 Month | 2026-03-27 | Mar | 2026
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | Equipment | Presto battery not charging | Follow with calibration center | Supervisor
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | Equipment | AC faulty | Contacted regional | Quality manager
FORTPORTAL | KASESE | MT ST MARY'S HOSPOTIALS KILEMBE | 2024-12-23 | Equipment | Region engineers to respond to emergency breakdown before schedule | Regional mentors at FPRRH | Lab manger and regional supervisor
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | Equipment | Chemistry analyzer. | Refer liver function test to nearest Hospital Kyenjojo. New machine | MoH
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | Equipment | Genexpert only four models four models | Upgrade to 8 or 16 module | CPHL/NTRL
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | Equipment | Power back up challenge | Discuss with MS | Lab Manager and Supervisors
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | Equipment | Stock out EID and VL catridges for a month | Called CPHL stores | CPHL
GULU | AGAGO | DR AMBROSOLI MEMORIAL HOSPITAL-KALONGO | 2024-12-23 | Equipment | Faulty biosafety cabinet | Follow up the repair for the biosafety cabinet | Lab manager | 3 months | 2025-03-23 | Mar | 2025
GULU | GULU | PATIKO H/CIII | 2025-03-20 | Equipment | Reduction in equipment down time
GULU | GULU | PATIKO H/CIII | 2025-03-20 | Equipment | Prolonged equipment downtime
GULU | GULU | PATIKO H/CIII | 2025-03-20 | Equipment | Develope equipment maintenance logs | Remind the Gulu regional equipment maintenance workshop on due dates for service | Training on troubleshooting of equipments
GULU | GULU | PATIKO H/CIII | 2025-03-20 | Equipment | Ojok Jacob
GULU | GULU | PATIKO H/CIII | 2025-03-20 | Equipment | By 30/5/2025
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Equipment | Irregularity in supply of some reagents | Include budget for all the required reagents in the annual procurement plan | Matayo | Immediate
GULU | KITGUM | ST. JOSEPH'S HOSPITAL KITGUM | 2025-03-21 | Equipment | Some Equipments are not being serviced | Followup with UPMB for service contract | Lab Manager | 30/4/2025
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | Equipment | No Equipments at the facility | Equpments to be requested by facility from the district | facility incharge | 2025/2026 FY | 2026-12-31 | Dec | 2026
GULU | NWOYA | ANAKA GENERAL HOSPITAL | 2025-08-08 | Equipment | Lack of internal quality controls panels for the machine | Contacted service provider | George ocen | One month | 2025-09-08 | Sep | 2025
GULU | NWOYA | KOCHGOMA HCIII | 2025-03-21 | Equipment | Centrifuge not installed | Requisition and installation the centrifuge needed | Lab manager | April 2025 | 2025-04-30 | Apr | 2025
GULU | NWOYA | KOCHGOMA HCIII | 2025-03-21 | Equipment | Equipment not serviced as per their schedule | Follow up with the DLFP to liase with the regional workshop to ensure equipment service is done | Lab manager | June 2025
GULU | OMORO | BOBI HC3 | 2025-03-21 | Equipment | Equipment services not done | To develop a services schedule and follow up with GuluRegional referral hospital | Lab manager | Immediately
GULU | OMORO | BOBI HC3 | 2025-03-21 | Equipment | POC testing equipment like PIMA machines | DLFP to Coordinate the requisition | Facilities Incharge | At least three months | 2025-06-21 | Jun | 2025
GULU | OMORO | LALOGI HC IV | 2024-12-18 | Equipment | m-PIMA machine for HIV Viral Load not working | Follow up with the service provider (CPHL) | Laboratory manager | 3 months | 2025-03-18 | Mar | 2025
GULU | PADER | PAJULE HC IV | 2024-12-19 | Equipment | Equipment malfunction | Follow up with the service engineer | Laboratory Manager | 3 months | 2025-03-19 | Mar | 2025
GULU | PADER | PAJULE HCIV | 2025-08-08 | Equipment | Stock outs of Cartidges | Following up with CPHL on supply of cartidges | Hub coordinator | 31/08/2025
GULU | PADER | PAJULE HCIV | 2025-08-08 | Equipment | Delayed servicing of equipment by the service provider | Following up with the service provider | 31/08/2025 | Quality Officer
GULU | PADER | PAPER HEALTH CENTRE LLL | 2025-03-21 | Equipment | Shortage of Catriges | The order is always done through NMSU, | Internal borrowing from other facility. | Laboratory Technician through Store person of the District
GULU | PADER | PURANGA HCIII | 2025-03-28 | Equipment | No maintenance scheduled at HCIII | Regional Biomedical Engineer have plan and cover HCIII | GRRH equipment maintenance workshop team
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | Equipment | LACK OF ESSENTIAL EQUIPMENT | ENGAGE GOVENMENT PROVIDE ESSENTIAL EQUIPMENT TO FACILITIES | FACILITY MANAGER, DHO | IMMEDIATE
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | Equipment | DELAY IN SERVICING | ENSURE ALL EQUIPMENT HAVE SERVICE SCHEDULE AND TIMEYL ENGAGEMENT OF THE JINJA RRH WORKSHOP | FACILITY MANAGER, DHO | IMMEDIATE
JINJA | BUGIRI | NANKOMA HC IV | 2026-03-25 | Equipment | POWER FLUCTUATIONS | ENGAGE STAKEHOLDERS PROCURE POWER BACK UP | FACILITY MANAGER | IMMEDIATE
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | Equipment | Faulty Humastar 60Ts | Mjap to procure a service contract | MJAP Lab advisor and Lab manager | Feb 2025 | 2025-02-28 | Feb | 2025
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | Equipment | No service contract for human machines | Mjap to procure a service contract | MJAP Lab advisor and Lab manager | Feb 2025 | 2025-02-28 | Feb | 2025
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | Equipment | faulty microscope stage | MJAP to support transfer it to the regional workshop for repair | MJAP Lab advisor and Lab manager | Feb 2025 | 2025-02-28 | Feb | 2025
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | Equipment | Need a multi-loader CBC for the facility given the workload | CHPL to support procure a multi-loader CBC | Lab manager and CHPL Logistics | Dec 2025 | 2025-12-31 | Dec | 2025
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | Equipment | constant faulty Chemistry Machine | IP to support get a new chemistry machine | lab manager and MJAP | DEC 2025 | 2025-12-31 | Dec | 2025
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | Equipment | No service contract for all human machines at the time of supervision | IP to procure a service contract | MJAP lab advisor | Jan 2025 | 2025-01-31 | Jan | 2025
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | Equipment | Faulty stages for olympus CX21(KGHL/LMS/02) | regional workshop needs to service the equipment and repair the equipment | lab manager | feb 2025 | 2025-02-28 | Feb | 2025
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | Equipment | most temperature logs not monitored ie (KGHL/RF/06, KGHL/RF/97, KGHL/RF/05) not up to date. | update all equipment logs | quality officer | Dec 2024 | 2024-12-31 | Dec | 2024
JINJA | NAMAYINGO | BUYINJA HC IV | 2026-03-09 | Equipment | UNSERVICED EQUIPMENT | FOLLOW UP SERVICE PROVIDERS TO FOLLOW MANTAINANCE SCHEDULE | FACILITY IN CHARGE | IMMEDIATE
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | Equipment | No serivce contract for human machines | IP to procure service contract for all human machines | MJAP | JAN 2025 | 2025-01-31 | Jan | 2025
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | Equipment | No update maintenance logs for most lab equipment | lab to update all maintenance logs for all equipments | lab manager | DEC 2025 | 2025-12-31 | Dec | 2025
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | Equipment | No competency assessment for POCT | do competency assessment for POCT | Lab manager | JAN 2025 | 2025-01-31 | Jan | 2025
KABALE | KANUNGU | BWINDI COMMUNITY HOSPITAL | 2024-12-12 | Equipment | No service contract for equipment serviced by Human iagnostics | Follow up with UPMB and facility management to ensure service contract is provided | Lab manager | February 2025 | 2025-02-28 | Feb | 2025
KABALE | KISORO | KISORO HOSPITAL | 2024-12-09 | Equipment | some equipment are due for service e.g Sysmex XN330, Humalyte plus, Humastar 200 | Follow up with respective service engineer to come and service all equipment due for service | laboratory manager | 13/12/2024
KAMPALA | KAMPALA | KIRUDDU NATIONAL REFERAL HOSPITAL | 2024-12-19 | Equipment | Fault PIMA machine | To have the Pima machine service | NHLDS | 2 months | 2025-02-19 | Feb | 2025
KAMPALA | KAMPALA | KIRUDDU NATIONAL REFERAL HOSPITAL | 2024-12-19 | Equipment | Centrifuge not serviced | to have the centrifuge serviced | Laboratory manager | 1 month | 2025-01-19 | Jan | 2025
KAYUNGA | BUVUMA | BUSAMIZI HEALTH CENTER III | 2025-04-10 | Equipment | The Microscope power cable is problematic and switches the microscope on and off during use | Engage the district leadership to procure a cable for the microscope | Kisitu Dennis DLFP | August 2025 | 2025-08-31 | Aug | 2025
KAYUNGA | KAYUNGA | BBAALE HEALTH CENTRE IV | 2025-03-13 | Equipment | Equipment like the Microscope, Refrigerator and Genexpert were due for service | Lab Manager to contact Cepheid to service Genexpert machine | Julius Were | 30th April 2025 | 2025-04-30 | Apr | 2025
KAYUNGA | KAYUNGA | BBAALE HEALTH CENTRE IV | 2025-03-13 | Equipment | Equipment like the Microscope, Refrigerator were due for service | Regional team to make preparation for the servicing of the equipment | Kayunga Regional Team | September 2025
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Equipment | GeneXpert borrowed during covid never returned | Follow up on the acquisition of a new /replacement GeneXpert machine | Rashid and Joy Mary | December 2025 | 2025-12-31 | Dec | 2025
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Equipment | m-PIMA and PIMA machine not serviced as per schedule | Follow up with science scope on the servicing of the machine | Rashid and Joy Mary | August 2025 | 2025-08-31 | Aug | 2025
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Equipment | Equipment serviced but not calibrated as per schedule | Follow up with NEC lab on the calibration of the equipment at Kalagala H/C IV | Rashid and Joy Mary | August 2025 | 2025-08-31 | Aug | 2025
KAYUNGA | LUWERO | LUWERO GENERAL HOSPITAL | 2025-03-12 | Equipment | Some equipment serviced but no service stickers put | Follow up with the service engineers to put stickers whenever they come | Gerald | Routine
KAYUNGA | NAKASONGOLA | NABISWERA HEALTH CENTER IV | 2025-03-11 | Equipment | The microscope is faulty [sparkling when plugged] | Procure a new circuit board for the microsocope | Nabiswera H/C management | August 2025 | 2025-08-31 | Aug | 2025
KAYUNGA | NAKASONGOLA | NAKASONGOLA HC IV | 2024-12-19 | Equipment | Increased Equipment downtime due to Stockout of Sysmex Reagent | Make an Emergency Order to NMS, Outsource from nearby facilities that have more | Inventory Officer, Lab Director | 31-12-2024
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | Equipment | The laboratory has auxilliary equipment, e.g Centrifuges, refridgerators that have worked beyond their life time and are very prone to breakdowns | CPHL team to make a replacement of the equipment that have worked beyond their life time i.e Blood Bank Fridge, Centrifuge | Kasone Viola, Wilson Nyegenye | December 2025 | 2025-12-31 | Dec | 2025
MASAKA | KALANGALA | KALANGALA HCIV | 2025-07-31 | Equipment | Lack of Centrifuge | Request for centrifuge from CPHL | RLM, DLFP | 06 Months | 2026-01-31 | Jan | 2026
MASAKA | LWENGO | LWENGO HEALTH CENTER IV. | 2025-07-28 | Equipment | faulty thermostat | purchase a new thermostat | dlfp/incharge | by oct 2025 | 2025-10-31 | Oct | 2025
MASAKA | LWENGO | LWENGO HEALTH CENTRE IV | 2024-12-10 | Equipment | faulty humastar 80 chemistry analyser | the equipment needed upgrading | Human diagnostics | 3 months | 2025-03-10 | Mar | 2025
MASAKA | MASAKA | MASAKA REGIONAL REFERRAL HOSPITAL | 2024-12-09 | Equipment | humaster 200 wasnot serviced as per schedule | liase with implementing partner to ensure that the equipment gets a service contract | implementing partner - IDI | 6 months | 2025-06-09 | Jun | 2025
MASAKA | MASAKA CITY | KIYUMBA HCIV | 2025-06-24 | Equipment | knowledge gap | mentorship and coaching | Regional referal lab coodinator | october 2025 | 2025-10-31 | Oct | 2025
MASAKA | MASAKA CITY | KIYUMBA HCIV | 2025-06-24 | Equipment | unserviced computers | service the computers and other equipments | IP | SEPTEMBER 2025
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | Equipment | Non functioning fridges | Regional workshop to handle | Regional Workshop manager | 2 months | 2025-09-29 | Sep | 2025
MBALE | BUDUDA | BUDUDA DISTRICT HOSPITAL | 2025-04-01 | Equipment | No functional sysmex analyser | Write to service provider to repair | Lab manager | Immediate
MBALE | BUDUDA | BUDUDA DISTRICT HOSPITAL | 2025-04-01 | Equipment | No functional humacount | Redistribution of reagents within the region | Lab manager and lab logistics | Immediate
MBALE | BUSIA | MASAFU HOSPITAL | 2025-04-11 | Equipment | Stock out of reagents | Follow up with NMS | Logistics officer | 30th, April, 2025 | 2025-04-30 | Apr | 2025
MBALE | BUSIA | MASAFU HOSPITAL | 2025-04-11 | Equipment | Equipment down time | Follow up with regional workshop | Hub coordinator | 30, April, 2025 | 2025-04-30 | Apr | 2025
MBALE | BUSIA | MASAFU HOSPITAL | 2025-04-11 | Equipment | Equipment not serviced as per schedule | Follow up with IP to renew contracts | Hub coordinator | 30th, June,2025
MBALE | BUTALEJA | BUSOLWE HOSPITAL | 2025-04-09 | Equipment | Lack of funds for the regional equipment workshop | To follow up with the workshop | Lab manager | May 2025 | 2025-05-31 | May | 2025
MBALE | BUTALEJA | NABIGANDA HC IV | 2025-04-07 | Equipment | No CBC being done due to reagent stock out for nihon | Redistribution within the region | Lab manager | Immediate
MBALE | MBALE CITY | MBALE REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Equipment | All basic equipment under the regional workshop not serviced due to funding challenges | Lobby for funding | Regional lab manager | December 2025 | 2025-12-31 | Dec | 2025
MBALE | PALLISA | PALLISA HOSPITAL | 2025-04-02 | Equipment | Faulty microscope | Replacement of bulb | Lab manager | July 2025 | 2025-07-31 | Jul | 2025
MBALE | PALLISA | PALLISA HOSPITAL | 2025-04-02 | Equipment | Non functional humalyte | Request for reagent pack | Lab manager | July 2025 | 2025-07-31 | Jul | 2025
MBALE | PALLISA | PALLISA HOSPITAL | 2025-04-02 | Equipment | Non functional mpima | Write to service provider | Lab manager | July 2025 | 2025-07-31 | Jul | 2025
MBALE | SIRONKO | BUDADIRI HEALTH CENTER IV | 2025-04-14 | Equipment | No reagent pack for humalyte | Redistribution within the region | Lab manager | Immediate
MBALE | SIRONKO | BUDADIRI HEALTH CENTER IV | 2025-04-14 | Equipment | Equipment not serviced per schedule | Write to regional workshop | Lab manager | Immediate
MBALE | TORORO | TORORO GENERAL HOSPITAL | 2025-04-16 | Equipment | Prolonged equipment down time | Regular service | Mbale RRH | 3 months | 2025-07-16 | Jul | 2025
MBARARA | BUSHENYI | ISHAKA ADVENTIST HOSPITAL | 2026-03-16 | Equipment | No service information | Maintenace unit to develop it | Lab manager | 2months | 2026-05-16 | May | 2026
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | Equipment | centrifuge breakdown | To notify the regional biomedical engineers | Mbarara Regional Referral Hospital, Laboratory manager | 3 weeks
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | Equipment | delays in equipment servicing | Need to notify the biomedical engineers in advance | Laboratory staff | 2 weeks
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | Equipment | Sysmex XS-1000i is not in use yet it is not faulty. It is only used as a back up. | Increase testing demand | lab manager | NA
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | Equipment | Facility is always given visitect kits yet they do not use them. | Push kits to lower facilities that need them | lab manager | NA
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | Equipment | Abbot Ruby has never been used, it failed at set up | Contact CPHL logistics supplier team | lab manager
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | Equipment | too many suppliers with substandard commodities like red tops and india ink | to always recommend brands that work well and give feedback on the poor ones
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | Equipment | NMS supplies have late deliveries, inconsistencies, less quantities delivered, sometimes no delivery of the requested commodities | follow up with management and NMS
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | Equipment | Biosafety cabinet failed at installation step, has never been used |  | CPHL
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | Equipment | BD Facs presto never been serviced since installation |  | BD engineers
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | Equipment | Stock outs and expiries for slides and field stain A,red tops, RBS strips, genexpert catridge |  | logistics
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | Equipment | Delayed placement of requests |  | NMS
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | Equipment | Long delivery times/short expiries |  | NMS
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | Equipment | no contacts were available for the service engineers for facs presto | contact CPHL engineers for a link to a contact person in charge
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | Equipment | some equipment had no power back ups eg Afinon 2 (abbott) | request for power back ups from the responsible teams
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | Equipment | stock out of mPIIMA catridges and pasteur pipettes | Give feedback to the responsible parties | NMS
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | Equipment | delivery of short expiry commodities | Give feedback to the responsible parties | NMS/CPHL logistics
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | Equipment | Facility requests made using FIMS but are not usually fulfilled(DBS cards) | Give feedback to the responsible parties | NMS/CPHL logistics
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2024-12-20 | Equipment | Equipment service schedules not followed | Keep reminding servicee engineers when service date is due | Laboratory Manager | January 2025 | 2025-01-31 | Jan | 2025
MOROTO | KOTIDO | KOTIDO GENERAL HOSPITAL | 2026-02-24 | Equipment | Lack of quality maitainance schedule | Lab in charge to develop and implement maintenance schedule 1 month
MOROTO | KOTIDO | KOTIDO GENERAL HOSPITAL | 2026-02-24 | Equipment | Lab in charge and hospital management to service bio safety cabinet and fire equipment within 60 days
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | Equipment | Equipment not serviced e.g Hemocue, PIMA, microscopes | Contact the regional equipment workshop to assess and repair these equipment | Laboratory In charge | January 2025 | 2025-01-31 | Jan | 2025
MUBENDE | KASSANDA | KASSANDA HEALTH CENTRE IV | 2024-12-13 | Equipment | Faulty equipments (Centrifuge and microscope | To contact Mubende Region Manteinance team to have the equipments repaired. | DLFP | 5TH/Feb/2025 | 2025-02-05 | Feb | 2025
MUBENDE | MITYANA | MITYANA HOSPITAL | 2024-12-12 | Equipment | No adherence to service schedule | To liase with the Implementing partner to ensure adhereance to the service schedule by the regioanal manteinance team | Quality manager, Lab manager | 30th/Jan/2025 | 2025-01-30 | Jan | 2025
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | Equipment | Lack of Reagents | To re-instate the reagents into NMS Catalogue | NMS,MOH- NHLDS | 30 March 2025 | 2025-03-30 | Mar | 2025
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | Equipment | Very Old Equipment Elisyu No | Need to procure New Equipment | MoH/CPHL | 30 January 2025 | 2025-01-30 | Jan | 2025
MUBENDE | NAKASEKE | NGOMA HEALTH CENTRE IV | 2025-04-08 | Equipment | The frequent breakdown of Humacount 60ts. | To follow up with the human diagnostics and CPHL to replace the machine or upgrade. | Kiyonga Edward. | 4 months. | 2025-08-08 | Aug | 2025
SOROTI | AMURIA | AMURIA GH | 2024-12-12 | Equipment | Equipment not serviced as per the schedule | Followup with the regional workshop to have the servicing done | Regional workshop | Immediately
SOROTI | AMURIA | AMURIA HOSPITAL | 2025-03-25 | Equipment | Delay in servicing equipment by the Soroti Region Equipment Workshop | Follow up with the soroti region equipment workshop since equipment under their service are due for service this month of march. | Lab manager | 31/03/2025
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2025-03-24 | Equipment | Delay in equipment service by the service providers. | Ensure the service schedule is adhered to and follow up with the respective service providers, especially soroti region equipment workshop scheduled to service equipment in March 2025 | Lab manager | 30/3/2025
SOROTI | KALAKI | LWALA | 2025-08-20 | Equipment | prolonged down time for pima and humalyte machines | communicate to the service providers | LAB MANAGER | 15TH SEPT 2025 | 2025-09-15 | Sep | 2025
SOROTI | KALAKI | LWALA HOSPITAL | 2026-03-17 | Equipment | No service schedule for the machines | come up with service schedule for the machines | HOD | Ongoing
SOROTI | KALAKI | LWALA HOSPITAL | 2026-03-17 | Equipment | No service contract for the machines | Lobby for the contractor from the partners/IP | Administration | Ongoing
SOROTI | KAPELEBYONG | KAPELOBYONG | 2025-08-19 | Equipment | Non functional equipment-fridge | plan for repair of the fridge in place | Lab manager | 30th Sept 2025 | 2025-09-30 | Sep | 2025
SOROTI | KAPELEBYONG | KAPELOBYONG | 2025-08-19 | Equipment | blood mixed with reagents and samples in the same fridge | separate the blood products from reagents and samples | lab manager | 30th Sept 2025 | 2025-09-30 | Sep | 2025
SOROTI | KATAKWI | KATAKWI GENERAL | 2025-08-20 | Equipment | auxilliary equipment not serviced since Nov 2024 | communicate to the regional equipment team | Lab manager | 30/sept/2025 | 2025-09-30 | Sep | 2025
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | Equipment | Inadequate equipment | Procure the required equipment | MOH
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | Equipment | Some equipment not serviced. | Follow up with the Soroti Region Medical Equipment workshop. | DLFP | 30/04/2025
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | Equipment | Delay in repair of the mPIMA machine (EID POCT)). | Follow up with life care to repair the mPIMA machine. | Quality Officer or DLFP | 30/03/2025
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | Equipment | Equipment maintenance logs not updated | Monitor equipment maintenance on daily basis. | Quality Officer | 02/04/2025
SOROTI | KUMI | ATUTUR | 2025-08-18 | Equipment | Logs out of date | quality officer and ;ab manager to enforce the use of logs | lab manager | 01/SEPT/2025 | 2025-09-01 | Sep | 2025
SOROTI | KUMI | KUMI HCIV | 2024-12-09 | Equipment | Non-functional equipment | Immediate transportation to CPHL for swapping | Lab manager | Immediate
SOROTI | KUMI | KUMI HOSPITAL-ONGINO | 2025-08-22 | Equipment | Incubator has never been repaired for over 30 days | contact the service engineers and schedule the service of the equipment | Lab manager
SOROTI | NGORA | NGORA | 2025-08-13 | Equipment | all auxilliary equipment not serviced since July 2024 | Regional equipment team to regularly perform equipment service quarterly | Betty | SEPT 2025 | 2025-09-30 | Sep | 2025
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | Equipment | Service engineer don't put stickers on the equipment after servicing | Service engineer should stick stickers after servicing | soroti Regional workshop | 01/04/25
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | Equipment | No functional back up system in the laboratory | procure new batteries for the backup | AIC | 30/4/25
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | Equipment | Gene Xpert back up system is faulty. | procure new batteries for the backup | AIC | 30/04/25
SOROTI | SOROTI | SOROTI | 2024-12-13 | Equipment | Exipry of commodities | Always redistribute commodities not being used | Inventory officer
SOROTI | SOROTI | SOROTI | 2024-12-13 | Equipment | Non functional machine | UPS Replacement | IP
SOROTI | SOROTI CITY | SOROTI | 2025-08-18 | Equipment | Service schedule for 2025 not posted | prepare the current service schedule and post | lab Manager | 30th Aug 2025 | 2025-08-30 | Aug | 2025
ENTEBBE | WAKISO | BUWAMBO HCIV | 2026-01-21 | Lab Equipment | Temperature guage on the water bath is faulty | management to take action
ENTEBBE | WAKISO | NAMAYUMBA HCIV | 2026-01-19 | Lab Equipment | Lack of cuvettes
FORTPORTAL | BUNYANGABU | KIBIITO HEALTH CENTER IV | 2026-01-20 | Lab Equipment | Faulty blood storage refrigerator | To repair or replacement of blood storage refrigerator |  | By the end of the 2nd quarter
FORTPORTAL | BUNYANGABU | RWIMI PRISON HEALTH CENTER III | 2026-01-20 | Lab Equipment | The non-functional BD FACSPresto, because of unavailability of reagents, presents a challenge in maintaining uninterrupted CD4 testing for patient monitoring. | Replace the faulty machine with mPIMA or provide reagents |  | By the end of the 2nd quarter.
FORTPORTAL | FORT PORTAL CITY | BUKUKU HEALTH CENTRE IV | 2026-01-22 | Lab Equipment | Non-functional CD4 and CRP testing services. | Ensure supply of CD4 and CRP reagents |  | Before the end of the 1st quarter
FORTPORTAL | KASESE | BWERA GENERAL HOSPITAL | 2026-01-19 | Lab Equipment | Lack of reagents challenges continued use of the hematology analyzer, limiting access to essential tests. | Make a request to the NMS store |  | By the end of the 2nd quarter
FORTPORTAL | KASESE | BWERA GENERAL HOSPITAL | 2026-01-19 | Lab Equipment | Faulty autoclave | Replacement of autoclave machine |  | By the end of the 2nd quarter
FORTPORTAL | KITAGWENDA | NTARA HC IV MAIN LABORATORY | 2026-01-23 | Lab Equipment | Need for a biosafety cabinet | Procure and install a Class II biosafety cabinet |  | By the end of 2026
FORTPORTAL | KITAGWENDA | NTARA HC IV MAIN LABORATORY | 2026-01-23 | Lab Equipment | Absence of a chemistry analyzer | Plan for procurement of a chemistry analyzer |  | By the end of 2026
FORTPORTAL | KITAGWENDA | NTARA HCIV | 2026-03-30 | Lab Equipment | No microbiology lab | request for procurement of a microbiology incubator |  | 30/12/2026
FORTPORTAL | KITAGWENDA | NYABANI HCIII | 2026-03-30 | Lab Equipment | FAULTY MICROSCOPE | SEND THE MICROSCOPE THROUGH THE HUB SYSTEM |  | 30.04.2026
FORTPORTAL | NTOROKO | KARUGUTU HCIV | 2026-03-19 | Lab Equipment | PIMA | SEND THE MACHINE TO CPHL |  | 30/04/2026
FORTPORTAL | NTOROKO | KARUGUTU HCIV | 2026-03-19 | Lab Equipment | MICROSCOPE NOT WORKING | CONTACT FACILITY INCHARGE |  | 30/06/2026
FORTPORTAL | NTOROKO | KARUGUTU HEALTH CENTRE IV | 2026-01-21 | Lab Equipment | A faulty microscope power cable | Purchase a new power cable. |  | By end of 2nd quarter
FORTPORTAL | NTOROKO | RWEBISENGO HCIV | 2026-03-19 | Lab Equipment | Non functional Pima machine | send the Pima through the hub system |  | 30/06/2026
HOIMA | BULIISA | BULIISA HEALTH CENTRE IV | 2026-01-28 | Lab Equipment | The laboratory equipment are not seriviced / calibrated
HOIMA | KIBAALE | KIBAALE HEALTH CENTRE IV | 2026-01-27 | Lab Equipment | Frequent power outtage
HOIMA | KIBAALE | KIBAALE HEALTH CENTRE IV | 2026-01-27 | Lab Equipment | The GeneXpert machine is always off
HOIMA | KIKUUBE | KYEHORO HEALTH CENTER III | 2026-01-29 | Lab Equipment | The equipment at the lab aare not serviced for example the microscope has never been serviced
HOIMA | KIKUUBE | KYEHORO HEALTH CENTER III | 2026-01-29 | Lab Equipment | Unreliable electricity source. The facility depends on solar power which is not strong enough to power all the laboratory activities
HOIMA | MASINDI | BWIJANGA HEALTH CENTRE IV | 2026-01-30 | Lab Equipment | Some laboratory equipment are affected by power irregularities e.g the Blood bank freezers that has made the blood units to be transfered and stored in the hospital freezer
HOIMA | MASINDI | BWIJANGA HEALTH CENTRE IV | 2026-01-30 | Lab Equipment | There is too much dust and overheating of equipment
HOIMA | MASINDI | MASINDI TASO | 2026-02-02 | Lab Equipment | Equipment servicing is not consistent
HOIMA | MASINDI | MASINDI TASO | 2026-02-02 | Lab Equipment | Reagents eg BD presto for CD4 counts are not available yet the machine is available
JINJA | JINJA | BUGEMBE HCIV | 2026-01-19 | Lab Equipment | Failure to update the GeneXpert software. | NTRL software focal person to contact CEPHEID to update software for the facility. |  | 20th January, 2026 | 2026-01-20 | Jan | 2026
JINJA | JINJA | BUGEMBE HCIV | 2026-01-19 | Lab Equipment | Inability to activate compatibility testing prior to blood transfusion. | Facility to make a monthly report detailing the need for these equipment. |  | 28th January,2026 | 2026-01-28 | Jan | 2026
JINJA | MAYUGE | KIGANDALO HC IV | 2026-01-21 | Lab Equipment | Non-functional CBC machine. | Lab Manager to contact the field engineer of Humacount diagnostics to fix machine. |  | 26th January,2026 | 2026-01-26 | Jan | 2026
KABALE | KABALE | MAZIBA HC IV | 2026-01-30 | Lab Equipment | Faulty PIMA machine | To follow-up with CPHL for replacement or return of the PIMA machine that was taken for repair |  | Mar 2026 | 2026-03-31 | Mar | 2026
KABALE | KISORO | MURAMBA HEALTH CENTRE III | 2026-01-28 | Lab Equipment | None
KAMPALA | KAMPALA | KAWEMPE NATIONAL REFERRAL HOSPITAL | 2026-01-22 | Lab Equipment | Lack of reagents controls
KAYUNGA | MUKONO | GOMA HCIII | 2026-02-03 | Lab Equipment | Unstable power | The lab incharge to follow up on installation of power back up |  | 31/3/26
KAYUNGA | MUKONO | GOMA HCIII | 2026-02-03 | Lab Equipment | Stock out of reagents limits usage | Follow up to get adquate supplies of reagents |  | Next ordering cycle
KAYUNGA | MUKONO | KASAWO HCIII | 2026-01-27 | Lab Equipment | Equipment servicing and maintenance | Follow up on the service team |  | 28th February 2026 | 2026-02-28 | Feb | 2026
KAYUNGA | MUKONO | KASAWO HCIII | 2026-01-27 | Lab Equipment | Power interruptions | Incharge to followup on installation of Powerback up |  | 28th February 2026 | 2026-02-28 | Feb | 2026
KAYUNGA | MUKONO | KASAWO HCIII | 2026-01-27 | Lab Equipment | Equipment workload | Incharge to advocate for facility to get another M-pima equipment
KAYUNGA | MUKONO | KYAMPISI HCIII | 2026-01-30 | Lab Equipment | Delays in servicing equipment e.g the microscope was last serviced in 2022 | Follow up with the service team |  | 10/2/2026
KAYUNGA | MUKONO | NAGALAMA HOSPITAL | 2026-01-29 | Lab Equipment | none
KAYUNGA | MUKONO | NAKIFUMA HCIII | 2026-01-28 | Lab Equipment | Delay to repair the broken equipment e.g the fridge has been broken down for 5 months | Facility incharge to engage the district to find an alternative solution |  | 28/02/2026
KAYUNGA | MUKONO | NAKIFUMA HCIII | 2026-01-28 | Lab Equipment | No equipment maintenance logs in the laboratory | Laboratory incharge to find funds to print all necessary documents |  | 10/02/2026
KAYUNGA | MUKONO | SEETA NAZIGO HCIII | 2026-02-02 | Lab Equipment | Power instabilities | Lab incharge to follow up with management to install power back up |  | 31/3/26
LIRA | AMOLATAR | AMOLATA HEALTH CENTRE IV | 2026-01-20 | Lab Equipment | One module of the GeneXpert machine routinely aborts MTB/RIF cartridges | Contact Cepheid for to rectify the modules |  | March 2026 | 2026-03-31 | Mar | 2026
LIRA | AMOLATAR | AMOLATA HEALTH CENTRE IV | 2026-01-20 | Lab Equipment | Trained Cyto-technician is available on site but there are no equipment to support histology services |  |  | May 2026 | 2026-05-31 | May | 2026
LIRA | AMOLATAR | AMOLATA HEALTH CENTRE IV | 2026-01-20 | Lab Equipment | BSC was installed but is not yet in use | The incharge should install a socket close to the BSC |  | JAN 2026 | 2026-01-31 | Jan | 2026
LIRA | DOKOLO | DOKOLO HEALTH CENTRE IV | 2026-01-19 | Lab Equipment | BSC not installed | NEC Laboratory to explore mechanisms to replace broken sash |  | May 2026 | 2026-05-31 | May | 2026
LIRA | DOKOLO | DOKOLO HEALTH CENTRE IV | 2026-01-19 | Lab Equipment | Humacount 60ts has frequent breakdown | Consider replacing Hematology machine |  | March 2026 | 2026-03-31 | Mar | 2026
LIRA | DOKOLO | DOKOLO HEALTH CENTRE IV | 2026-01-19 | Lab Equipment | Insufficient number of microscopes for lab tasks | Repair faulty microscopes Regional workshops |  | May 2026 | 2026-05-31 | May | 2026
LIRA | KOLE | ABOKE HC IV | 2026-01-21 | Lab Equipment | BSC is available but not installed |  |  | May 2026 | 2026-05-31 | May | 2026
LIRA | KOLE | ABOKE HC IV | 2026-01-21 | Lab Equipment | UPS for the Xpert machine is non-functional causing losses of cartridges during power outage | Consider installation of power back-up system |  | NHLDS-May 2026
MASAKA | LWENGO | KYAZANGA HC IV | 2026-02-02 | Lab Equipment | No automated chemistries done | Refer samples for automated chemistries. |  | Immediately.
MBARARA | BUSHENYI | KYEIZOOBA HCIII | 2026-02-05 | Lab Equipment | Power fluctuations | The management should lobby for procurement of power back up machines to keep the lab services running |  | 5/05/2026
MBARARA | IBANDA | ISHONGORORO HCIV | 2026-02-09 | Lab Equipment | The Hb machine is not functional | Cuvettes were bought |  | 28/02/2026
MBARARA | IBANDA | RUHOKO HCIV | 2026-02-06 | Lab Equipment | The functionality of the equipment is sometimes slowed down | The lab in-charge should reach out to the regional workshop to follow up with the engineers on when they would be performing the servicing |  | 6/05/2026
MBARARA | MBARARA CITY | RUHARO MISSION HOSPITAL | 2026-02-02 | Lab Equipment | Power surges that continuously affect the power supply | Perform a power audit to assess what is needed to have a stable power supply |  | 10/05/2026
MBARARA | MBARARA CITY | RUHARO MISSION HOSPITAL | 2026-02-02 | Lab Equipment | Unfavorable environment conditions | Engage the management to have the system installed |  | 10/05/2026
MBARARA | SHEEMA | KABWOHE HCIV | 2026-02-03 | Lab Equipment | Occassional breakdown of machines and inefficiency | Advocate for engineers from Mbarara region |  | 3/08/2026
MBARARA | SHEEMA | KIGARAMA HCIII | 2026-02-04 | Lab Equipment | Equipment maintenance is inconsistent | The management should advocate for engineers/service providers that are closer to the facility |  | 4/05/2026
MOROTO | AMUDAT | AMUDAT HOSPITAL | 2026-01-21 | Lab Equipment | Faulty MPIMA machine that was transferred to NEC for repair in November 2025 has never been returned back |  |  | End of January 2026
MOROTO | AMUDAT | AMUDAT HOSPITAL | 2026-01-21 | Lab Equipment | Pipette calibration |  |  | End of Januart 2026
MOROTO | AMUDAT | AMUDAT HOSPITAL | 2026-01-21 | Lab Equipment | Limited modules to handle high sample volume and multi-disease testing |  |  | End of March 2026
MOROTO | AMUDAT | LOORO HC III | 2026-01-20 | Lab Equipment | The facility has a fridge/freezer transfered form Karita HC IV that is currently faulty | Contact the regional workshop for planned service repair |  | End of February 2026
MOROTO | KAABONG | KAABONG HOSPITAL | 2026-01-19 | Lab Equipment | Humastar 200 broke-down in November 2025 | Issue was resolved through software update |  | End of February 2026
MOROTO | KAABONG | KAABONG HOSPITAL | 2026-01-19 | Lab Equipment | HumaCount 60 and Ni | Issue was resolved through software update |  | End of February 2026
MOROTO | NAKAPIRIPIRIT | TOKORA HEALTH CENTER IV | 2026-01-26 | Lab Equipment | High room temperature in the laboratory is hampering the operation of the Humastar 200 analyzer |  |  | End of February 2026
MOROTO | NAKAPIRIPIRIT | TOKORA HEALTH CENTER IV | 2026-01-26 | Lab Equipment | Most equipment were last serviced on 13th July 2023 |  |  | End of February 2026
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2026-01-28 | Lab Equipment | machine breakdowns |  |  | Feb 2026 | 2026-02-28 | Feb | 2026
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2026-01-28 | Lab Equipment | untimely equipment servicing | USE regional workshops |  | Feb 2026 | 2026-02-28 | Feb | 2026
SOROTI | KABERAMAIDO | LWALA HOSPITAL | 2026-01-22 | Lab Equipment | no GeneXpert machine
SOROTI | KABERAMAIDO | LWALA HOSPITAL | 2026-01-22 | Lab Equipment | No equipment microbiology
SOROTI | KATAKWI | AKETA HCIII | 2026-01-19 | Lab Equipment | Damaged cable for BD presto | competence assessment |  | continuous
SOROTI | KATAKWI | TOROMA HCIV | 2026-01-20 | Lab Equipment | Under utilisation
SOROTI | KATAKWI | TOROMA HCIV | 2026-01-20 | Lab Equipment | staffing gaps
SOROTI | KUMI | MUKONGORO HCIII | 2026-01-30 | Lab Equipment | No equipment
SOROTI | KUMI | MUKONGORO HCIII | 2026-01-30 | Lab Equipment | No reagents
SOROTI | KUMI | MUKONGORO HCIII | 2026-01-30 | Lab Equipment | No Staff trained
SOROTI | SERERE | SERERE HCIV | 2026-01-21 | Lab Equipment | power interruption
SOROTI | SERERE | SERERE HCIV | 2026-01-21 | Lab Equipment | reagent stockouts
SOROTI | SERERE | SERERE HCIV | 2026-01-21 | Lab Equipment | non timely service