## Sheet 1
RRH | District | HFacility | VDate | Section | Identified Gap | Agreed Action Point | Institution Responsible | Timelines | due_date | ActionMonth | ActionYr
ENTEBBE | BUTAMBALA | GOMBE GENERAL HOSPITAL | 2024-12-12 | HR | facility doesnot posses all the required cadre categories | district service commission to help in recruitment | district service commission | one year | 2025-12-12 | Dec | 2025
ENTEBBE | BUTAMBALA | GOMBE HOSPITAL | 2026-02-26 | HR | Human resource gaps | DLFP to lobby for recruitment of personnel | DLFP/Lab manager | 1 yr
ENTEBBE | BUTAMBALA | GOMBE HOSPITAL | 2026-02-26 | HR | Capacity Development | Conduct in house CME | DLFP/lab Manager | 1yr
ENTEBBE | GOMBA | GOMBE GENERAL HOSPITAL. | 2025-04-10 | HR | Not enough staff in the laboratory | To have more staff recruited by the district service comission. | Dr.ssekamatte (DHO) | 4 Months. | 2025-08-10 | Aug | 2025
ENTEBBE | GOMBA | MADDU HC IV | 2025-04-10 | HR | low staffing levels | the district should recruit more staffs for the laboratory | DHO | Long term plan
ENTEBBE | GOMBA | MADDU HC IV | 2026-02-25 | HR | Capacity development activities no longer taking place | Build on CMEs | DLFP | 6months | 2026-08-25 | Aug | 2026
ENTEBBE | MPIGI | MPIGI HCIV LABORATORY | 2025-04-09 | HR | Back up system does not accommodate reagent fridges | lobby from the IP | Fcaility incharge
ENTEBBE | MPIGI | MPIGI HCIV LABORATORY | 2025-04-09 | HR | The biosafety cabinet has been faulty since 2023 | to followup with engeering team from the ministry | IP,MOH
ENTEBBE | MPIGI | MPIGI HCIV LABORATORY | 2025-04-09 | HR | GENEXPERT machine crushed | to have it reported to the IP and the service provider | Service engineers
ENTEBBE | MPIGI | MPIGI HCIV LABORATORY | 2025-04-09 | HR | the lab emergency exit is block by the patients waiting benches and a wall | need to change or adjust the emergency exist | facility incaharge,IP, District
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2024-12-09 | HR | LOW STAFFING LEVELS | HOSPITAL DIRECTOR TO NOTIFY THE DG | DIRECTOR | 4 MONTHS | 2025-04-09 | Apr | 2025
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2025-04-14 | HR | Low staffing level | The hospital should lobby for more wage to recruit more health workers | HD | By next financial year
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFFERAL HOSPITAL | 2026-02-24 | HR | Identify staff that have not been trained | In house trainings | Lab manager | 2 months | 2026-04-24 | Apr | 2026
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFFERAL HOSPITAL | 2026-02-24 | HR | low human resource | Lobby for the recruitment of personnel | lab manager | 6 months | 2026-08-24 | Aug | 2026
ENTEBBE | WAKISO | KASANGATI HEALTH CENTRE III | 2024-12-16 | HR | Limited staff at kasangati health centre IV | To lobby for more staff at centre IV. | Facility incharge and DLFP(KAKEETO ALEX) | 4 months | 2025-04-16 | Apr | 2025
ENTEBBE | WAKISO | KOMAMBOGA HEALTH CENTRE III | 2024-12-13 | HR | Inadquate staffing | To have atleast all cadres recruited | KCCA | 3 Months to have the feedback. | 2025-03-13 | Mar | 2025
ENTEBBE | WAKISO | WAKISO HEALTH CENTRE IV | 2024-12-12 | HR | Understaffing at wakiso health centre iv | To recruit new staff | District service commission / KAKEETO ALEX | 1 YEAR | 2025-12-12 | Dec | 2025
ENTEBBE | WAKISO | WAKISO IV | 2026-02-27 | HR | Human Resource constraints | Lobby for more staff | DLFP/Lab Manager | 1yr
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | HR | No cytotechnologist, lab technologist | MOH to drive to implemet lab structure
FORTPORTAL | KAMWENGE | RUKUNYU GENERAL HOSPITAL | 2024-12-19 | HR | Unavailable cadres in the facility | Recruitment of Cytotechnologist | MOH/District service commission | 6months | 2025-06-19 | Jun | 2025
FORTPORTAL | KAMWENGE | RUKUNYU GENERAL HOSPITAL | 2024-12-19 | HR | Inadequate number of HR (Snr Lab techs, Lab techs and Lab technicians) | Recruitment of more Lab personnel | MOH/District service commission | 6months | 2025-06-19 | Jun | 2025
FORTPORTAL | KASESE | MT ST MARY'S HOSPOTIALS KILEMBE | 2024-12-23 | HR | Currently have less by 5 Technicians, No SLT, SL technicians , No cytotechnologist | Foward to CPHL MoH | Supervisor
GULU | AGAGO | DR. AMBROSOLI MEMORIAL KALONGO | 2025-08-08 | HR | ISO TRAINING | REGIONAL TO CONDUCT THE TRAINING | THE LAB MANAGER AND GULU RR H | 4 MONTHS | 2025-12-08 | Dec | 2025
GULU | AGAGO | DR. AMBROSOLI MEMORIAL KALONGO | 2025-08-08 | HR | STOCK OUT OF REAGENT | PROPER FORECUST | Lab manager and procurement | 3 Months | 2025-11-08 | Nov | 2025
GULU | AMURU | ATIAK HEALTH CENTRE | 2025-08-08 | HR | Inadequate human resource capacity building | Make and share training plan with different stakeholders | Laboratory managers | 15th Ausust 2025 | 2025-08-15 | Aug | 2025
GULU | GULU | PATIKO H/CIII | 2025-03-20 | HR | Laboratory assistant deployed in the facility
GULU | GULU | PATIKO H/CIII | 2025-03-20 | HR | No laboratory Assistant in the laboratory
GULU | GULU | PATIKO H/CIII | 2025-03-20 | HR | Request the facility in charge to inform The DHO about the staffing gap
GULU | GULU | PATIKO H/CIII | 2025-03-20 | HR | Ojok Jacob
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2024-12-17 | HR | Under absorption of staff with the qualification they possessed | Absorption of staff | Gulu RRH and MoH | 6 months (June 2025) | 2025-06-17 | Jun | 2025
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2025-08-08 | HR | Inadequate Human Resource | Conduct Management Review to inform managment on the HR gap | Matayo, Dr Peter | By 31st December 2025 | 2025-12-31 | Dec | 2025
GULU | GULU CITY | ST MARY'S HOSPITAL LACOR | 2025-03-21 | HR | Understaffing at Serology and microbiology dep[artments | Advocate for additional staff to enhance lab services, improve performance, and facilitate the enrollment of more lab tests for accreditation | Lab manager ( Ocakacon Robert) | 30th April 2025 | 2025-04-30 | Apr | 2025
GULU | KITGUM | KITGUM GENERAL HOSPITAL | 2024-12-20 | HR | Inadequate human resource | Lobby for more human resource | Laboratory manager and Medical Superintendent | 6 months | 2025-06-20 | Jun | 2025
GULU | KITGUM | ST. JOSEPH'S HOSPITAL KITGUM | 2025-03-21 | HR | Departmental CME not done | Designate a CME coordinator | Lab Manager (Oryema David) | 27/03/2025
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | HR | HR gap | DHO to make submissions to CAO for onward submission to DSC | DHO | 2025/2026 FY | 2026-12-31 | Dec | 2026
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | HR | Equipment gap | implementation of equipment standardization guidlines | UNHLS | 2025/2026 FY | 2026-12-31 | Dec | 2026
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | HR | Unreliable power supply | installation of backups(facility incharge to include in the work plan and budget) | Facility incharge | 2025/2026 FY | 2026-12-31 | Dec | 2026
GULU | NWOYA | ANAKA GENERAL HOSPITAL | 2025-08-08 | HR | Leadership | Training | Human resource department | One year | 2026-08-08 | Aug | 2026
GULU | NWOYA | KOCHGOMA HCIII | 2025-03-21 | HR | Lack of training to staff | District to include lower facilities into their training plan | DLFP | June 2025
GULU | OMORO | BOBI HC3 | 2025-03-21 | HR | Inadequate staffing | Recommendation for recruitment by the DHT team | Facility incharge | Immediate recommendations in the report
GULU | OMORO | BOBI HC3 | 2025-03-21 | HR | Refresher training | Non adherence to the regional capacity building workplan | Regional Laboratory Coordinator | By end of Qtr 2 | 2025-06-30 | Jun | 2025
GULU | OMORO | LALOGI HC IV | 2024-12-18 | HR | Inadequate human resource | To recruit more staff | Laboratory manager | 6 months | 2025-06-18 | Jun | 2025
GULU | PADER | PAJULE HC IV | 2024-12-19 | HR | Inadequate Human resource | Lobby for recruitment | Laboratory manager | 6 months | 2025-06-19 | Jun | 2025
GULU | PADER | PAJULE HCIV | 2025-08-08 | HR | Understaffing | Communicate to the DH Office, to include these cadres in the recruitment plan | Lab in-charge | 31/12/2025
GULU | PADER | PAPER HEALTH CENTRE LLL | 2025-03-21 | HR | NA
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | HR | FEW STAFFS | ENGAGE DLG TO PROVIDE WAGE FRO MORE LAB STAFF | LAB MANAGER | IMMEDIATE
JINJA | BUGIRI | NANKOMA HC IV | 2026-03-25 | HR | FEW STAFFS | ENGAGE STAKEHOLDERS TO PROVIDE MORE WAGE | FACILITY MANAGER | IMMEDIATE
JINJA | BUGWERI | BUSESE HC IV | 2026-03-20 | HR | LOBBY FOR MORE STAFF | ENGAGE DLG ADMISTRATION TO PROVIDE MORE WAGE | DHO, CAO FACILITY MANAGER | IMMEDIATE
JINJA | BUGWERI | BUSESE HC IV | 2026-03-20 | HR | TRAININGS IN LQMS | LOBBY FOR FUNDING FROM IPs | DLG, IPs | IMMEDIATE
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | HR | THE LAB HAS FEW STAFFS TO OPERATE IT | ADVOCATE WITH DHO to increase the staffing levels | DHO and lab manager | Dec 2025 | 2025-12-31 | Dec | 2025
JINJA | IGANGA | BUGONO HC IV | 2026-03-18 | HR | LOW STAFFING LEVELS | LOBBY WITH MANAGEMENT ABOUT IMPROVING THE WAGE BILL | FACILITY MANAGER | IMMEDIATE
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | HR | Indequate staffing levels | advocate for missing staff through the district service commission | lab manager and DHO | DEC 2025 | 2025-12-31 | Dec | 2025
JINJA | IGANGA | IGANGA HOSPITAL | 2026-03-17 | HR | TRAININGS NEEDED FOR QMS, BRM | LOBBY FOR MORE FUNDING TO MAKE TRAININGS | IPs, DLG | IMMEDIATE
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | HR | Understaffed lacking some cadre | MS needs to advocate for implemenation of the approved structure for general hospital | MS | Dec 2024 | 2024-12-31 | Dec | 2024
JINJA | MAYUGE | MAYUGE HC IV | 2026-03-24 | HR | NO WAGE | ENGAGE RESONSIBLE OFFICERS TO ALLOCATED MORE WAGE FOR LAB STAFF | DHO, CAO | FY 2026-27 | 2027-12-31 | Dec | 2027
JINJA | MAYUGE | ST FRANCIS BULUBA GENERAL HOSPITAL | 2026-03-19 | HR | STAFFING GAPS | ENGAGE STAKEHOLDERS INCREASE ON FUNDING | FACILITY MANAGER | IMMEDIATE
JINJA | NAMAYINGO | BUYINJA HC IV | 2026-03-09 | HR | IN ADEQUATE WAGE | LOBBYING FOR MORE WAGE | DHO, CAO | FY 2026/2027 | 2027-12-31 | Dec | 2027
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | HR | Understaffing as per new structure | advocate for filling of the missing positions | lab manager and DHO | DEC 2025 | 2025-12-31 | Dec | 2025
KABALE | KISORO | KISORO HOSPITAL | 2024-12-09 | HR | No training Plan enable tracking of required trainings for staff development and enhance their skills, No funds allocated for staff trainings | Develop training programme and also present the programme to the facility management for implementation | Laboratory manager and Quality officer | March 2025 | 2025-03-31 | Mar | 2025
KAMPALA | KAMPALA | KIRUDDU NATIONAL REFERAL HOSPITAL | 2024-12-19 | HR | Inaquate staffing | To lobby for staffing | Executive director | 3 months | 2025-03-19 | Mar | 2025
KAYUNGA | KAYUNGA | BBAALE HEALTH CENTRE IV | 2025-03-13 | HR | No training for new staff on new standards like ISO 15189:2022 | Regional team to include new staff during regional trainings | KRRH/Rashid | September 2025
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | HR | Facility personnel not received targeted training in key areas LQMS, Biosafety | Organize targeted LQMS mentorship based on the new ISO 15189:2022 standard | KRRH, IP | April 2025 | 2025-04-30 | Apr | 2025
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | HR | Facility personnel not received targeted training in key areas, Biosafety | Organize targeted Bio safety and Bio Risk mentorship to the laboratory | KRRH, IP | August 2025 | 2025-08-31 | Aug | 2025
KAYUNGA | LUWERO | LUWERO GENERAL HOSPITAL | 2025-03-12 | HR | Some key stuff positions not fully covered | Hire through Luwero DLG | Luwero DLG/DHO | June 2025
KAYUNGA | NAKASONGOLA | NABISWERA HEALTH CENTER IV | 2025-03-11 | HR | Staff have not been trained on LQMS, Biosafety and Biosecurity | The Regional team to include the Nabiswera Team in any upcoming LQMS, Biosafety and Biosecurity | KRRH, Rashid | December 2025 | 2025-12-31 | Dec | 2025
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | HR | The lab lacks some key cadres | The Nakasongola DLG advertised for the position of technologist | Nakasongola DLG | August 2025 | 2025-08-31 | Aug | 2025
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | HR | The lab lacks some key cadres | MUWRP has also placed two additional staff to beef up the manpower | MUWRP | Completed
MASAKA | BUKOMANSIMBI | BUTENGA | 2025-06-25 | HR | understaffing | recruit more staff | CAO,DHO | 6 Month | 2025-12-25 | Dec | 2025
MASAKA | KALANGALA | KALANGALA HCIV | 2025-07-31 | HR | Inadequate Staff | Recruit Lab Staff | DHO, CAO, DLFP | 01 Year | 2026-07-31 | Jul | 2026
MASAKA | KALUNGU | BUKULULA | 2025-06-26 | HR | Understaffing | recruitment of more staff | CAO,DHO | 6 Month | 2025-12-26 | Dec | 2025
MASAKA | KYOTERA | KALISIZO GENERAL HOSPITAL | 2025-07-30 | HR | Inadequate wage for recruitment | Loby for wage increase | Admin, Med Sup, DHO, DLFP | 01 Year | 2026-07-30 | Jul | 2026
MASAKA | KYOTERA | KALISIZO GENERAL HOSPITAL | 2025-07-30 | HR | Non implementation of the new structure | Implement the new structure | Hosp management, District | 01 Year | 2026-07-30 | Jul | 2026
MASAKA | LWENGO | LWENGO HEALTH CENTRE IV | 2024-12-10 | HR | facilty does not posses all the required cadre categories | district service commission to recruit the required cadres | district service commission | one year | 2025-12-10 | Dec | 2025
MASAKA | LYANTONDE | LYANTONDE GENERAL HOSPITAL | 2025-08-01 | HR | Recruitment of the required cadres as per structure | Recruit additional staff | Lab Manager, DHO, CAO | One year | 2026-08-01 | Aug | 2026
MASAKA | MASAKA | MASAKA REGIONAL REFERRAL HOSPITAL | 2024-12-09 | HR | the facility doesnot posses all the required caders | hospital to fill the required caders | Principal human resource officer | one year | 2025-12-09 | Dec | 2025
MASAKA | MASAKA CITY | KIYUMBA HCIV | 2025-06-24 | HR | understaffing | lobby for more staff | DHO
MASAKA | MASAKA CITY | MASAKA REGIONAL REFERRAL HOSPITAL | 2025-06-27 | HR | Understaffing | lobby for more staff | Director | month
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | HR | Lack of promotion | Promote lab staff | Med Sup, DHO, CAO, DLFP | 01 year | 2026-07-29 | Jul | 2026
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | HR | Inadequate wage | Avail the required wage | CAO, DHO, | 01 year | 2026-07-29 | Jul | 2026
MASAKA | SEMBABULE | SEMBABULE HC IV | 2025-06-23 | HR | Staffing gap | lobby for more HR | SDLG | ONGOING
MASAKA | SEMBABULE | SEMBABULE HC IV | 2025-06-23 | HR | KNOWLEDGE GAP | More mentorships and coaching | Regional team
MBALE | BUDUDA | BUDUDA DISTRICT HOSPITAL | 2025-04-01 | HR | CAPA( no staff trained) | To lobby for resources and train | Bududa lab manager, Mbale RRH lab manager | End of jun 2025
MBALE | BUDUDA | BUDUDA DISTRICT HOSPITAL | 2025-04-01 | HR | BSBS | 2 people trained to cascade the training to the rest of the staff | Safety officer, Bududa lab manager | By June 2025
MBALE | BUSIA | MASAFU HOSPITAL | 2025-04-11 | HR | Inadequate numbers of staff | Follow up with HR for recruitment | DLFP, PLT Mbale, MS | Next financial year
MBALE | BUTALEJA | BUSOLWE HOSPITAL | 2025-04-09 | HR | Intensified CMEs | Schedule regular CMEs BSBs | Quality manager, safety officer | Monthly
MBALE | BUTALEJA | NABIGANDA HC IV | 2025-04-07 | HR | No trainings | To work with DLFP to schedule training | Lab in charge | May 2025 | 2025-05-31 | May | 2025
MBALE | KAPCHORWA | KAPCHORWA GENERAL HOSPITAL LABORATORY | 2025-04-04 | HR | Low wage to support implementation of new HR structure | Lobby district to lobby wage from ministry of finance | HR and lab manager | 1st, June, 2026
MBALE | PALLISA | PALLISA HOSPITAL | 2025-04-02 | HR | Some positions not filled | To follow up with DHO and CAO to have particular positions filled I.e lab technologist and senior lab technologist | Lab manager and regional lab manager | By June 2025
MBALE | SIRONKO | BUDADIRI HEALTH CENTER IV | 2025-04-14 | HR | Not all required cadres available at facility | DLFP to write to DHO | DLFP, DHO | July 2025 | 2025-07-31 | Jul | 2025
MBALE | TORORO | TORORO GENERAL HOSPITAL | 2025-04-16 | HR | Inadequate lab staff | Continue lobbying for more staff | Lab manager, MS | 2 years | 2027-04-16 | Apr | 2027
MBARARA | BUSHENYI | ISHAKA ADVENTIST HOSPITAL | 2026-03-16 | HR | Under staffing. GOU has only seconded 01 medical officer to the hosptal | Theres need to lobby through UPMB to second atleast other core staff | HRO & MEDICAL DIRECTOR | Ongoing
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | HR | Inadequate staffing | Need to recruite more staff | Facility incharge | 6 months | 2026-09-30 | Sep | 2026
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | HR | Inadequate training/ mentorship | Need to organise CMEs/ trainings/ support supervision | Mbarara RRH | 3 months | 2026-06-30 | Jun | 2026
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | HR | Scheme of service not implemented | Follow up with public service | HR/facility incharge | 6 months | 2025-06-09 | Jun | 2025
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | HR | understaffed |  | local government
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2024-12-20 | HR | Inadequate staffing | recruit more staff especially laboratory technologis and laboratory technician | Human resource officer | June 2025
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2026-02-24 | HR | Undestaffing | Human resources gab in the laboratory | Hospital MS | 12 months | 2027-02-24 | Feb | 2027
MOROTO | KAABONG | KAABONG GENERAL HOSPITAL | 2026-02-25 | HR | Inadequate staffing across all cadres | Hospital management | 6-12 months
MOROTO | KAABONG | KAABONG GENERAL HOSPITAL | 2026-02-25 | HR | Lack of staff capacity building | Hospital administration and laboratory in charge | 6 months
MOROTO | KARENGA | KARENGA HEALTH CENTRE IV | 2026-02-26 | HR | Inadequate laboratory staffing | Hospital and district to recruit more staff with in 12 months
MOROTO | KOTIDO | KOTIDO GENERAL HOSPITAL | 2026-02-24 | HR | Inadequate staffing across all cadres | District to prioritize recruitment in the next 6-12 months
MOROTO | KOTIDO | KOTIDO GENERAL HOSPITAL | 2026-02-24 | HR | Not all staff trained in BRM and QMS | Regional IP to support BRM and QMS training for all staff in the next 3 months
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | HR | Inadequate Human resource | recruit more staff | HRO | June 2025
MUBENDE | KASSANDA | KASSANDA HEALTH CENTRE IV | 2024-12-13 | HR | Inadquate staffing in the laboratory | To lobby for more laboratory staff | DLFP, Facility incharge | 30th/June/2024
MUBENDE | MITYANA | MITYANA HOSPITAL | 2024-12-12 | HR | No user training on the supplied HB meters | To write to NMS through the hospital superintendent for provision of user training to all user departments. | Lab. Manager( Mr Katende Andrew), Quality Manager (Jimmy Kakaire) | 30th/Jan/2025 | 2025-01-30 | Jan | 2025
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | HR | Frequent reagent stock out of reagentsf reagents | To re instate reagent for CBC and Chemistry into NMS Order catelogue | MOH/CPHL,NMS | 30 March 2025 | 2025-03-30 | Mar | 2025
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | HR | Frequent Equipment breakdown | Delivery of new CBC Analyser | MOH/CPHL | 30 Feb 2025
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | HR | Dead Power backup system | Provision of new power backup system | MOH,CPHL and Baylor | 30 March 2025 | 2025-03-30 | Mar | 2025
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | HR | Regular blackout of e-LIMS | Need to get a focal person for IT at CPHL to handle Mubende RRH | MOH/CPHL | 30 January 2025 | 2025-01-30 | Jan | 2025
MUBENDE | NAKASEKE | NGOMA HEALTH CENTRE IV | 2025-04-08 | HR | Lack of computers for systems connectivity. | DR. MUKUZI (Incharge) to take up the action to the IPs and the district to procure atleast 3 computers for the lab | Facility incharge | 4 months | 2025-08-08 | Aug | 2025
SOROTI | AMURIA | AMURIA GENERAL | 2025-08-22 | HR | LOW STAFFING | Engage DHO's OFFICE | DLFP | S0TH SEPT 2025 | 2025-09-30 | Sep | 2025
SOROTI | AMURIA | AMURIA GH | 2024-12-12 | HR | Understaffing | IP to renew contracts of the MLAs | AIC
SOROTI | AMURIA | AMURIA GH | 2024-12-12 | HR | Staff turnover | Replace the staff that left | IP/MOH
SOROTI | AMURIA | AMURIA HOSPITAL | 2025-03-25 | HR | Inadequate human resource | Recruit more staff to improve and maintain service delivery. | District Health Office | When the wage is available for recruitment.
SOROTI | KABERAMAIDO | KABERAMAIDO GENERAL | 2025-08-21 | HR | LOW STAFFING IN THE LAB | District to analyze the wage and recruit the critical staff to cover the staffing gaps in the labs | DHO | 2025/2026 | 2026-12-31 | Dec | 2026
SOROTI | KABERAMAIDO | KABERAMAIDO GENERAL HOSPITAL | 2026-03-17 | HR | Needs for recruitment | Inadequate staffing / low staffing | Recruitment | HR office
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2025-03-24 | HR | Low staffing levels | Recruit more staff. | District Health Office | Recruitment ongoing(There is a running advert for 2 lab assistants).)
SOROTI | KALAKI | LWALA | 2025-08-20 | HR | the facility has no lab technician | the management to loby from Kalaki district local government or recruit to cover the gap | ADMIN | 2025/2026 FY | 2026-12-31 | Dec | 2026
SOROTI | KALAKI | LWALA HOSPITAL | 2026-03-17 | HR | High Staff turn over | provide adequate wages for the staff | HR | Ongoing
SOROTI | KALAKI | LWALA HOSPITAL | 2026-03-17 | HR | Inadequate number of staff | Recruite more staff | HR | Ongoing
SOROTI | KAPELEBYONG | KAPELOBYONG | 2025-08-19 | HR | LOW STAFFING | Engage DHO's OFFICE | DLFP | 30TH SEPT 2025 | 2025-09-30 | Sep | 2025
SOROTI | KATAKWI | KATAKWI GENERAL | 2025-08-20 | HR | staffing gaps in the laboratory. | district to assess the wage and recruit critical staff based on availability of wage | DHO | 2025/2026 FY | 2026-12-31 | Dec | 2026
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | HR | Understaffing | Recruit more lab officers | MOH
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | HR | Inadequate support staff | Recruit more support staff | Facility
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | HR | Low staffing levels | Recruit or transfer in lab personnel from other health facilities. | District Health office | When the wage for recruitment is available.
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | HR | Inadequate numbers of laboratory staff. | Recruit more lab personnel. | District Health Office | Based on availability of the wage.
SOROTI | KUMI | ATUTUR GENERAL HOSPITAL | 2026-03-25 | HR | Inadequate staffing | Recruitment/lobbying | CAO, HR | On going
SOROTI | KUMI | ATUTUR GENERAL HOSPITAL | 2026-03-25 | HR | Limited staff training on LQMS, Biosafety | IP to conduct the training | IPs, SRRH | On going
SOROTI | KUMI | ATUTUR HOSPITAL | 2024-12-10 | HR | Understaffing | Recruit Officers | District | June 2025
SOROTI | KUMI | KUMI HCIV | 2024-12-09 | HR | Inadequate numbers for the required staff | Recruitment of required cadres | MOH | ONGOING
SOROTI | KUMI | KUMI HOSPITAL-ONGINO | 2025-08-22 | HR | Inadequate number of staff | recruit staff | HR/ADMIN | SEPT 2025 | 2025-09-30 | Sep | 2025
SOROTI | NGORA | NGORA | 2025-08-13 | HR | inadequate number of staff in the lab | district to lobby for more wage and recruit | DHO | 2025/26 FY | 2026-12-31 | Dec | 2026
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | HR | inadequate staffing as per the new Lab structure | Request the district to recruit more staff | DLFP | 30/05/2025
SOROTI | NGORA | NGORA HCIV | 2026-03-18 | HR | Inadequate staff | Recruite more staff | HR | Ongoing
SOROTI | NGORA | NGORA HCIV | 2026-03-18 | HR | Inadequate wage for recruitement | Lobby for more wage for recruitement | HR | Ongoing
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | HR | Low staffing levels at the facility | Recruit more lab personnel to support lab services. | District Health Office | It will base on the availability of the wage bill
SOROTI | SERERE | SERERE HEALTH CENTER IV | 2026-03-20 | HR | Inadequate staffing | Recruitment | HR / CAO to lobby for wage bill | Ongoing
SOROTI | SERERE | SERERE HEALTH CENTER IV | 2026-03-20 | HR | Stockout of HPV cartridge | Quantification and forecast | HOD | Two weeks
SOROTI | SERERE | SERERE HEALTH CENTER IV | 2026-03-20 | HR | Unstable power and lack of power backup | MS to lobby for power backup | MS | Ongoing
SOROTI | SOROTI | SOROTI | 2024-12-13 | HR | Inadequate HR | Needs assessment be done | MOH | 1 month | 2025-01-13 | Jan | 2025
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | HR | Inadequate wage available for recruitement | Provision of wage for recruitement | HR/MOH/Ministry of Public service | When wage is available
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2026-03-16 | HR | Inadequate staffing | Need for recruitement of more staff | HR | Ongoing
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2026-03-16 | HR | Recruited staff failing to report to upcountry Hospitals | Readvertise to attract other staff | HR | Ongoing
SOROTI | SOROTI CITY | SOROTI | 2025-08-18 | HR | Inadequate staffing as per the level of facility | analyze wage and recruit to cover the missing positions | PHRO/DHO | 2025/2026 FY | 2026-12-31 | Dec | 2026
| BUYENDE DISTRICT | KIDERA HC IV | 2026-02-09 | HR | QMS AND BRM CAPACITY BUILDING | ENAGAGE MoH AND IPs TO FACILITATE CAPACITY BUILDING | FACILITY MANAGER, DHO & CAO | IMMEDIATE