## Sheet 1
RRH | District | HFacility | VDate | Section | Identified Gap | Agreed Action Point | Institution Responsible | Timelines | due_date | ActionMonth | ActionYr
ENTEBBE | GOMBA | GOMBE GENERAL HOSPITAL. | 2025-04-10 | QMS | To add more tests on EQA scope | Quality manager and IP | 4 months.
ENTEBBE | GOMBA | MADDU HC IV | 2025-04-10 | QMS | Develop a schedule for EQA/PT performance | Quality officer/Lab Incharge | by 30/04/2025
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2024-12-09 | QMS | Contact UKNEQAS to issue another result feedback report corresponding to the one submitted by the peripheral laboratory | Wamala keefa | 2 weeks
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFFERAL HOSPITAL | 2026-02-24 | QMS | Source for service provider or enroll on interlaboratory comparison | QAO | 1 month
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFFERAL HOSPITAL | 2026-02-24 | QMS | Enroll in interlaboratory comparision | QAO | 1 month
ENTEBBE | WAKISO | KASANGATI HEALTH CENTRE III | 2024-12-16 | QMS | The lab manager to contact CPHL PT coordinator | Lab manager | 2 months
ENTEBBE | WAKISO | KOMAMBOGA HEALTH CENTRE III | 2024-12-13 | QMS | To train all the staff on PT analysis. | Ronald magen | 3 months
ENTEBBE | WAKISO | WAKISO HEALTH CENTRE IV | 2024-12-12 | QMS | to do a laboratory comparison of the same eqa sample with other accredited labs of the same machime to ruleout the root cause | Quality manager / Nassali maryam | 3 months
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | QMS | To follow up with National quality coordinator | Supervisor and lab quality manager
FORTPORTAL | KAMWENGE | RUKUNYU GENERAL HOSPITAL | 2024-12-19 | QMS | Enrollment of tests on EQA | National EQA / QC coordinator - CPHL | 6 months
FORTPORTAL | KASESE | MT ST MARY'S HOSPOTIALS KILEMBE | 2024-12-23 | QMS | CPHL MoH to support | Supervisor
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | QMS | Discuss with national QC department | QC manager, Lab manager, Mentors
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2025-08-08 | QMS | Lobby for funding for additional EQA programs | Matayo | Immediate
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2025-08-08 | QMS | Proper verification of EQA results should be done before submision | Sempiira Paul | Immediate
GULU | KITGUM | ST. JOSEPH'S HOSPITAL KITGUM | 2025-03-21 | QMS | Generate list of test not on EQA and share with CPHL | Lab Manager | 30/5/2025
GULU | KITGUM | ST. JOSEPH'S HOSPITAL KITGUM | 2025-03-21 | QMS | Laiase with the HUB to follow up on timely delivery | Lab Manager | 30/5/2025
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | QMS | Lab workplan and budget | Lab incharge | 2025/2026 FY
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | QMS | Lab to submitt list of test without EQA to UNHLS | Lab incharge | 2025/2026 FY
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | QMS | Backup power ssystem to be built | Facility incharge | 2025/2026 FY
GULU | NWOYA | KOCHGOMA HCIII | 2025-03-21 | QMS | The hub to print EQA reports fron the respective dashboards and deliver to lower facilities for filing | Lab manager | June 2025
GULU | OMORO | BOBI HC3 | 2025-03-21 | QMS | To choose a laboratory such as to atleast to do inter laboratory comparisons . | Laboratory incharge | By end of Qtr1 2025/2026
GULU | OMORO | LALOGI HC IV | 2024-12-18 | QMS | Procure more EQA scheme | Quality manager | 6 months
GULU | PADER | PAJULE HC IV | 2024-12-19 | QMS | Ensure CQI is routinely done with traceable record | Quality manager | 3 months
GULU | PADER | PAJULE HCIV | 2025-08-08 | QMS | Sourcing/ Lobbying from other facilities to ensure TAT for EQAs are met as follow ups are being done to ensure supplies are received from the approved supplier | Laboratory Manager | Whenever there is need
GULU | PADER | PAPER HEALTH CENTRE LLL | 2025-03-21 | QMS | There's demand for the facility to be accredited | Accredited body should consider the facility to be included in the accreditation list
GULU | PADER | PURANGA HCIII | 2025-03-28 | QMS | The staff have to be mentor on HIV testing algorithms and follow SOPs | Quality officer | By the end of March 2025
HOIMA | HOIMA | HOIMA REGIONAL REFFERAL | 2024-12-11 | QMS | train staff | IP | END OF MARCH 2025
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | QMS | ENGAGED CPHL TO PROVIDE ALTERNATIVES TO FACSPRESTO FOR CD4 TESTING | FACILITY MANAGER, DHO | IMMEDIATE
JINJA | BUGIRI | NANKOMA HC IV | 2026-03-25 | QMS | ENGAGE STAKEHOLDERS TO IMRPROVE WAGE BILL FOR LAB STAFF | FACILITY MANAGER | IMMEDIATE
JINJA | BUGWERI | BUSESE HC IV | 2026-03-20 | QMS | REVIEW ALL EQA REPORTS | WANSADHA JOEL | IMMEDIATE
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | QMS | control all external documents in the laboratory | Lab quality officer | DEC 2024
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | QMS | conduct the management review meeting | lab quality officer | DEC 2024
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | QMS | develop and EQA scheme for these tests | MJAP and CHPL | FEB 2025
JINJA | IGANGA | BUGONO HC IV | 2026-03-18 | QMS | ALWAYS ORDER FROM NMS AND FOLLOW UP ON THE ORDERS MADE | FACILITY MANAGER | NEXT QUARTER (CYCLE 2)
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | QMS | Qaulity officer to review the measurement uncertainty for CD4 | Musayi Franco | Jan 2025
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | QMS | Perform inter lab compressions | Musayi Franco | Jan 2025
JINJA | IGANGA | IGANGA HOSPITAL | 2026-03-17 | QMS | ENSURE TIMELY SUPPLY OF HBsAg KITS TO ENSURE EQA IS RUN | FACILITY MANAGER | IMMEDIATE
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | QMS | CPHL and IP to support provide the EQAs or lab to run inter-lab compressions | lab manager | feb 2025
JINJA | MAYUGE | MAYUGE HC IV | 2026-03-24 | QMS | CONTACT CPHL TO DELIVER EQA PANELS FOR HBsAg | LAB MANAGER | APRIL 2026
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | QMS | perform inter lab comparison for test without EQA | Lab manager | Jan 2025
KAMPALA | KAMPALA | KIRUDDU NATIONAL REFERAL HOSPITAL | 2024-12-19 | QMS | To lobby for the accreditation of both heamatology and clinical chemistry test | Lab manager | 3 months
KAMPALA | KAMPALA | KIRUDDU NATIONAL REFERAL HOSPITAL | 2024-12-19 | QMS | To have the root cause documented | Quality manager | 1 month.
KAYUNGA | KAYUNGA | KAYUNGA RRH | 2024-12-12 | QMS | Lab requisitioned funds for malaria refresher training. | Training coordinator (JoyMary) | June 2025
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | QMS | Print and put the results on file | Emma | April 2025
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | QMS | Organize targeted LQMS mentorship based on the new ISO 15189:2022 standard through regionalization strategy | KRRH | April 2025
KAYUNGA | NAKASONGOLA | NABISWERA HEALTH CENTER IV | 2025-03-11 | QMS | Procure a tally counter for the facility | Nabiswera H/C management | August 2025
KAYUNGA | NAKASONGOLA | NAKASONGOLA HC IV | 2024-12-19 | QMS | Refurbish and equip Microbiology Laboratory, Train staff on Culture and sensitivity Testing | Implementing Partner | March 2025
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | QMS | Follow up with CPHL/NTRL to return the report | Lillian Mbabazi | March 2025
MASAKA | BUKOMANSIMBI | BUTENGA | 2025-06-25 | QMS | mentorships and coaching | RRH | 6 month
MASAKA | BUKOMANSIMBI | BUTENGA | 2025-06-25 | QMS | strt implemebtation after being mentored | RRH,Incharge | 6 month
MASAKA | KALUNGU | BUKULULA | 2025-06-26 | QMS | mentorships and coaching | RRH Codinator | 4 month
MASAKA | LYANTONDE | LYANTONDE GENERAL HOSPITAL | 2025-08-01 | QMS | Enroll all tests on EQA | Lab Manager, DLFP | 6 months
MASAKA | LYANTONDE | LYANTONDE GENERAL HOSPITAL | 2025-08-01 | QMS | Train all testers in EQA | Lab Manager, RLM, IP, CPHL | 6 months
MASAKA | MASAKA | KYANAMUKAAKA | 2025-06-28 | QMS | mentorships and coaching | RRH | 6 month
MASAKA | MASAKA | MASAKA REGIONAL REFERRAL HOSPITAL | 2024-12-09 | QMS | Do root cause analysis for failed EQA | Quality Officer | 2 months
MASAKA | MASAKA CITY | KIYUMBA HCIV | 2025-06-24 | QMS | Do baseline audit | RRH | october 2025
MASAKA | MASAKA CITY | KIYUMBA HCIV | 2025-06-24 | QMS | MENTORSHIP & coaching | RRH | MARCH 2026
MASAKA | MASAKA CITY | KIYUMBA HCIV | 2025-06-24 | QMS | availail facility login credentials | IP/UVRI | sept 2025
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | QMS | Refresher training in Gram staining and film comment | Lab Manager | 6 months
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | QMS | CME on interpretation of results | Lab Manager | 2 months
MASAKA | SEMBABULE | SEMBABULE HC IV | 2025-06-23 | QMS | enroll more tests on interlaboratory comparison with MRRH . | Quality officer | october 2025
MBALE | BUDUDA | BUDUDA DISTRICT HOSPITAL | 2025-04-01 | QMS | Develop an SOP , refresher training | Lab manager | 3 months
MBALE | KAPCHORWA | KAPCHORWA GENERAL HOSPITAL LABORATORY | 2025-04-04 | QMS | Reorientation and training to be conducted to the staff | Lab manager and Mbale RRH lab team | 30th, June, 2025
MBALE | PALLISA | PALLISA HOSPITAL | 2025-04-02 | QMS | Perform RCA | Quality manager | Immediate
MBALE | SIRONKO | BUDADIRI HEALTH CENTER IV | 2025-04-14 | QMS | Training on malaria microscopy | Lab manager/ DLFP | July 2025
MBALE | TORORO | TORORO GENERAL HOSPITAL | 2025-04-16 | QMS | Perform RCA following for effectiveness | Quality manager | 3 months
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | QMS | LQMS training/ mentorship | Mbarara Regional Referral Hospital/ Regional Laboratory manager | 3 months
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | QMS | Need for continuous supply from the source | logistics manager | 2 months
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | QMS | Change to ALIS | IT METS/CPHL/MOH
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | QMS | Integrate LIMS EAFIA with ALIS to enable lab requests and reports to meet requirements | IT/METS/CPHL/MOH
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | QMS | Create a lab email to be used for EQA results transfer to and from requester | Facility QC officer/CPHL EQA team | 30/01/2025
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2024-12-20 | QMS | Write to the implementing Partner to organise trainings and mentorships | ANECCA | January 2025
MOROTO | KAABONG | KAABONG GENERAL HOSPITAL | 2026-02-25 | QMS | Repair of EID /VL machine, conduct forensic checks on the failed EQA | Laboratory in charge 3 months
MOROTO | KOTIDO | KOTIDO GENERAL HOSPITAL | 2026-02-24 | QMS | Hospital to advocate for resources to conduct QMS training and mentorship within thnext two months
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | QMS | Enrol all key tests on EQA | Laboratory In charge | March 2025
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | QMS | Enrol laboratory on LQMS | Laboratory In charge | March 2025
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | QMS | To get malaria EQA service provider | MOH/CPHL | 30 March 2025
MUBENDE | NAKASEKE | NGOMA HEALTH CENTRE IV | 2025-04-08 | QMS | To lobby from other facilities with EID,VL to redistribute | Brian Mugerwa | 1 month.
SOROTI | AMURIA | AMURIA HOSPITAL | 2025-03-25 | QMS | Do competent assessment on HIV testing for all testers. Have HIV testing done in the lab by trained personnel. | Quality officer | 31/03/2025
SOROTI | KABERAMAIDO | KABERAMAIDO GENERAL | 2025-08-21 | QMS | Conduct CAPA and track performance | George | 15th Sept 2025
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2025-03-24 | QMS | Do root cause analysis and corrective action for the failed EQA. | Quality officer | ongoing
SOROTI | KALAKI | LWALA | 2025-08-20 | QMS | lab manager to follow up with the service providers | lab manager | 15th sept 2025
SOROTI | KALAKI | LWALA HOSPITAL | 2026-03-17 | QMS | Enroll more tests on available EQA programes | HOD | Ongoing
SOROTI | KALAKI | LWALA HOSPITAL | 2026-03-17 | QMS | conduct CME on how to enroll on EQA program | HOD/IP | Ongoing
SOROTI | KAPELEBYONG | KAPELOBYONG | 2025-08-19 | QMS | engage the incharge of the facility and head of department | lab manager | 01/oct 2025
SOROTI | KAPELEBYONG | KAPELOBYONG | 2025-08-19 | QMS | redistribution from Amuria Hub | lab manager | 01/oct 2025
SOROTI | KATAKWI | KATAKWI GENERAL | 2025-08-20 | QMS | communicate to CPHL requesting for enrolment of the missing tests on EQA | LAB MANAGER | 30TH SEPT 2025
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | QMS | consistent supply of panels | CPHL | 1 MONTH
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | QMS | Do root cause analysis and corrective action for the failed EQA. | Quality officer | 30/3/2025
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | QMS | Do train and competent assessment to the personnel who performed the EQA . | Quality Officer | 18/04/2025
SOROTI | KUMI | ATUTUR GENERAL HOSPITAL | 2026-03-25 | QMS | Refresh training | Quality officer | On going
SOROTI | KUMI | ATUTUR HOSPITAL | 2024-12-10 | QMS | Train staff on gram | CPHL | 1 month
SOROTI | KUMI | KUMI HCIV | 2024-12-09 | QMS | Enroll the facility on all tests | CPHL | 1 Month
SOROTI | NGORA | NGORA | 2025-08-13 | QMS | call CPHL in case of errors | Quality Officer | SEPT 2025
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | QMS | enroll on all test EQA | Lab manager | 26/04/25
SOROTI | NGORA | NGORA HCIV | 2026-03-18 | QMS | Enroll all tests onto available EQA program | HOD | Ongoing
SOROTI | SERERE | SERERE | 2025-08-15 | QMS | perform CAPA and monitor | QO | SEPT 2025
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | QMS | DO RCA for the failed EQA | Lab manager and quality offer | 08/04/25
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | QMS | Do competence assessment for all staff | Lab manager | 08/04/25
SOROTI | SOROTI | SOROTI | 2024-12-13 | QMS | Perform corrective actions for the failed EQA | Lab manager
SOROTI | SOROTI | SOROTI | 2024-12-13 | QMS | Training of staff | Lab manager
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | QMS | come up with the competent assesment schedule | Quality Officer | Two weeks (By 04/04/2025)
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | QMS | Do RCA on failed EQA | Quality Officer | 2 weeks (By 04/04/2025)
SOROTI | SOROTI CITY | SOROTI | 2025-08-18 | QMS | Follow up with the EQA service providers for the reports | BETTY | 30TH AUG 2025
FORTPORTAL | FORT PORTAL CITY | BUKUKU HEALTH CENTRE IV | 2026-01-22 | QMS | None
FORTPORTAL | KASESE | BWERA GENERAL HOSPITAL | 2026-01-19 | QMS | Failure to enroll some tests in EQA programme challenges external validation of test accuracy and quality assurance. | Find out if EQA of these tests is available for these tests at CPHl. Enrol all tests on EQA programme. |  | By end of 1st quarter
FORTPORTAL | KITAGWENDA | NTARA HC IV MAIN LABORATORY | 2026-01-23 | QMS | Failure to enroll all tests in EQA schemes challenges external validation of test accuracy and reliability. | Enroll all tests in EQA schemes |  | By the end of the 2nd quarter.
FORTPORTAL | KITAGWENDA | NTARA HCIV | 2026-03-30 | QMS | EQA for Malaria BS, urinalysis, blood grouping, urinalysis and CBC are not being done | contact CPHL EQA department for enrollment onto those EQA schemes |  | 30/06/2026
FORTPORTAL | KITAGWENDA | NYABANI HCIII | 2026-03-30 | QMS | NO SOPS FOR IMPLEMENTING LQMS | WRITE SOPS AND SEND TO THE HUB FOR PRINTING |  | 30.12.2026
FORTPORTAL | NTOROKO | KARUGUTU HEALTH CENTRE IV | 2026-01-21 | QMS | None
FORTPORTAL | NTOROKO | RWEBISENGO HCIV | 2026-03-19 | QMS | EQA for Malaria RDT, Crag, urinalysis and CBC not being done | contact CPHL EQA depertment for enrollment onto the EQA s |  | 30/09/2026
HOIMA | BULIISA | BULIISA HEALTH CENTRE IV | 2026-01-28 | QMS | QMS is not implemented at the laboratory
HOIMA | KIBAALE | KIBAALE HEALTH CENTRE IV | 2026-01-27 | QMS | Lack of positive response to the EQA panel from the HIV section. The laboratory staff have poor attitude towrads these panels
HOIMA | KIBAALE | KIBAALE HEALTH CENTRE IV | 2026-01-27 | QMS | Knowledge gap in QMS amongst the laboratory staff
HOIMA | KIBAALE | NYAMARWA HEALTH CENTER III | 2026-01-26 | QMS | The laboratory staff do not want to participate in QMS activities
HOIMA | KIBAALE | NYAMARWA HEALTH CENTER III | 2026-01-26 | QMS | Sometimes the EQA panels are brought but not worked on
HOIMA | KIKUUBE | KYEHORO HEALTH CENTER III | 2026-01-29 | QMS | The laboratory staff has no QMS knowledge
HOIMA | KIKUUBE | KYEHORO HEALTH CENTER III | 2026-01-29 | QMS | Sometimes the EQA panels are sent to the facility but not worked on
HOIMA | MASINDI | BWIJANGA HEALTH CENTRE IV | 2026-01-30 | QMS | QMS is not implemented at the facility
HOIMA | MASINDI | MASINDI TASO | 2026-02-02 | QMS | The PT panels sent to the facility atre sometimes not done
HOIMA | MASINDI | MASINDI TASO | 2026-02-02 | QMS | Different methods used at the facility compared to the result required (the facility uses the qualitative/ semi quantitative visitect CD4 cell estimation wile the panel requires quantitative method)
JINJA | JINJA | BUGEMBE HCIV | 2026-01-19 | QMS | The facility does not have a designated quality officer, leaving a substantial gap in the development, adoption, implementation and maintenance of the QMS at the facility. | QMS mentor to be sent to the facility to enable it fast track their QMS. |  | 31st August, 2026 | 2026-08-31 | Aug | 2026
JINJA | JINJA | BUGEMBE HCIV | 2026-01-19 | QMS | The facility lacks clear documentation for QMS like SOPs, bench aids, and does not document maintenance records of equipment in the facility. | Laboratory Manager to request for human resource and appoint a quality officer. |  | 20th January,2026 | 2026-01-20 | Jan | 2026
JINJA | KAMULI | BULOPA H/C III | 2026-01-26 | QMS | Staff need more training on QMS and mentorship. | Implement more QMS mentorship and training programs at the facility. |  | 27th February 2026 | 2026-02-27 | Feb | 2026
JINJA | KAMULI | BULOPA H/C III | 2026-01-26 | QMS | EQA monitoring for TB blinded slides is not done sometimes. | Develop a tracking tool to monitor EQA for TB blinded slides. |  | 27th February 2026 | 2026-02-27 | Feb | 2026
JINJA | KAMULI | NAMWENDWA H/CIV | 2026-01-23 | QMS | Facility does not have a proper QMS documentation; lack of equipment maintenance logs, bench aids. | Conduct weekly CMEs for students, quality improvement officer to take lead on this action. Assign more supervison to the hospital laboratory. Implement more QMS mentorship and training programs at the facility. |  | 27th February 2026 | 2026-02-27 | Feb | 2026
JINJA | MAYUGE | KIGANDALO HC IV | 2026-01-21 | QMS | Facility has never conducted any internal audits. | Train and mentor staff on QMS. |  | 31st March, 2026 | 2026-03-31 | Mar | 2026
JINJA | MAYUGE | KIGANDALO HC IV | 2026-01-21 | QMS | Equipment monitoring logs are not up to date | Development of maintenance logs by lab manager and training staff on how to effectively utilize them. |  | 30th January, 2026 | 2026-01-30 | Jan | 2026
KABALE | KABALE | MAZIBA HC IV | 2026-01-30 | QMS | Facility facing challenges with implementing LQMS | To follow up with NHLDS for posibility of enrolling facility on SMLTA |  | April 2026 | 2026-04-30 | Apr | 2026
KABALE | KABALE | MAZIBA HC IV | 2026-01-30 | QMS | Access to EQA feedback reports is challenging | To follow up with NHLDS for access to the online EQA dashboards. |  | Mar 2026 | 2026-03-31 | Mar | 2026
KABALE | KISORO | MURAMBA HEALTH CENTRE III | 2026-01-28 | QMS | Testers (Nurses and midwives) reluctant in testing PT panels for HIV and Syphilis (Lab staff end up testing on their behalf) | To conduct regular CME sessions on EQA for midwives, nurses and other testers to facilitate cooperation and increased participation rates in PT activities. |  | April 2026 | 2026-04-30 | Apr | 2026
KAYUNGA | MUKONO | GOMA HCIII | 2026-02-03 | QMS | Documents are not well organised and files not well labelled | Lobby to attend QMS training
KAYUNGA | MUKONO | GOMA HCIII | 2026-02-03 | QMS | Personnel not keen on implementing QMS | Staff need to be trained on QMS
KAYUNGA | MUKONO | KASAWO HCIII | 2026-01-27 | QMS | EQA feedback reports are not available on file e.g TB blinded rechecking feedback reports available were upto 1st quarter 2025 | Incharge to followup with DTLs about the feedback reports |  | 28th February 2026 | 2026-02-28 | Feb | 2026
KAYUNGA | MUKONO | KYAMPISI HCIII | 2026-01-30 | QMS | Challenges in documentation and also the laboratory has no registers and is just improvising | Followup with the facility incharge to get printing means |  | 10/2/2026
KAYUNGA | MUKONO | KYAMPISI HCIII | 2026-01-30 | QMS | Staffing gaps | Advocate for more HR |  | 31/3/2026
KAYUNGA | MUKONO | NAGALAMA HOSPITAL | 2026-01-29 | QMS | QMS gaps not sufficiently addresed | To orient management on QMS |  | 28/02/2026
KAYUNGA | MUKONO | NAKIFUMA HCIII | 2026-01-28 | QMS | Documentation gaps | Followup the DLFP to be enrolled on SLMTA |  | 30/3/2026
KAYUNGA | MUKONO | NAKIFUMA HCIII | 2026-01-28 | QMS | No reports of EQA schemes seen | Follow up on the feedback reports |  | 28/02/20
KAYUNGA | MUKONO | SEETA NAZIGO HCIII | 2026-02-02 | QMS | Challenges in printing QMS documents | To follow up with management to get printing services |  | 28/2/26
KAYUNGA | MUKONO | SEETA NAZIGO HCIII | 2026-02-02 | QMS | Less QMS support | To ensure management is oriented on QMS aspects |  | 28/2/26
LIRA | AMOLATAR | AMOLATA HEALTH CENTRE IV | 2026-01-20 | QMS | Routine IQC for most tests are not performed as per the national recommendation | Develop procedures of quality assurance of tests |  | May 2026 | 2026-05-31 | May | 2026
LIRA | AMOLATAR | AMOLATA HEALTH CENTRE IV | 2026-01-20 | QMS | Some test e.g. Chemistry LF-LAM and RBS are not enrolled on EQA
LIRA | DOKOLO | DOKOLO HEALTH CENTRE IV | 2026-01-19 | QMS | Drop in SLIPTA scores from 3 stars to O star | NHLDS to engage top management to support |  | May 2026 | 2026-05-31 | May | 2026
LIRA | DOKOLO | DOKOLO HEALTH CENTRE IV | 2026-01-19 | QMS | IQC not performed for most tests, even those that have IQC material | Develop quality indicators that are reviewed periodically |  | March 2026 | 2026-03-31 | Mar | 2026
LIRA | KOLE | ABOKE HC IV | 2026-01-21 | QMS | EQA feedback reports were not accessed for all TB tests, EID and VL | Put all EQA results in the EQA forms file |  | March 2026 | 2026-03-31 | Mar | 2026
LIRA | OYAM | ATIPE HCIII | 2026-01-23 | QMS | the laboratory is not implementing a formal QMS |  |  | March 2026 | 2026-03-31 | Mar | 2026
MBARARA | IBANDA | ISHONGORORO HCIV | 2026-02-09 | QMS | The QMS has not been fully embraced | Management should organise continuous trainings and they should be documented |  | 9/05/2026
MBARARA | IBANDA | RUHOKO HCIV | 2026-02-06 | QMS | The personnel are exposed to contracting infections | The facility in-charge should work hand in hand with the ministry to have a biosafety cabinet procured and installed |  | 5/08/2026
MBARARA | IBANDA | RUHOKO HCIV | 2026-02-06 | QMS | The lab activities are delayed | The facility in-charge informed the team that it is work in progress |  | 2027
MBARARA | MBARARA CITY | RUHARO MISSION HOSPITAL | 2026-02-02 | QMS | Failure to adhere to the quality improvement projects | The quality team should embark on the previous projects to have them implemented and documented |  | 2/08/2026
MBARARA | SHEEMA | KABWOHE HCIV | 2026-02-03 | QMS | Some EQA panels are sent without kits | Continuous requisition of the test kits and outsourcing from other facilities |  | 28/02/2026
MOROTO | AMUDAT | LOORO HC III | 2026-01-20 | QMS | Delays in receiving HIV/syphilis EQA panels |  |  | End of January 2026
MOROTO | NABILATUK | NABILATUK HC IV | 2026-01-23 | QMS | Inadequate infrastructure in place |  |  | End of March 2026
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2026-01-28 | QMS | expired reagents being used | lab manager to order for commodities |  | By end of Jan 2026
SOROTI | KABERAMAIDO | LWALA HOSPITAL | 2026-01-22 | QMS | afew staffs equipped with LQMs | Lab manager follow ups |  | Feb 2026 | 2026-02-28 | Feb | 2026
SOROTI | KATAKWI | AKETA HCIII | 2026-01-19 | QMS | staffing gaps | Staff lobbying for more |  | continuous
SOROTI | KATAKWI | AKETA HCIII | 2026-01-19 | QMS | work load
SOROTI | KATAKWI | AKETA HCIII | 2026-01-19 | QMS | Knowledge gap | CMES |  | CMEs
SOROTI | KATAKWI | TOROMA HCIV | 2026-01-20 | QMS | not reviewing EQA results