## Sheet 1
RRH | District | HFacility | VDate | Section | Identified Gap | Agreed Action Point | Institution Responsible | Timelines | due_date | ActionMonth | ActionYr
ENTEBBE | BUTAMBALA | GOMBE HOSPITAL | 2026-02-26 | Service Delivery | Intiate test with asking for the required equipments | DLFP/LAB Manager | 1yr
ENTEBBE | GOMBA | GOMBE GENERAL HOSPITAL. | 2025-04-10 | Service Delivery | To have more equipments in gombe hospital like Incubator to start the microbiology lab | DHO | 4 months.
ENTEBBE | GOMBA | MADDU HC IV | 2025-04-10 | Service Delivery | to lobby from other facilities | lab incharge | immediately
ENTEBBE | MPIGI | MPIGI HCIV LABORATORY | 2025-04-09 | Service Delivery | Lobby kits from other facilities | Lab head | immediately
ENTEBBE | MPIGI | MPIGI HCIV LABORATORY | 2025-04-09 | Service Delivery | inform the DHO and the IP to lobby from other facilities that have | lab incharge, facility head,DHO | Within a month
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2024-12-09 | Service Delivery | To have all the tests done as per the national test menu. | Lab manager | 4 months
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2025-04-14 | Service Delivery | the hospital should lobby to have the laboratory budget increased to improve the running of the laboratory | HD | By next financial year
ENTEBBE | WAKISO | KASANGATI HEALTH CENTRE III | 2024-12-16 | Service Delivery | To have the test done | Facility incharge | 3 months (feedback)
ENTEBBE | WAKISO | KASANGATI HEALTH CENTRE III | 2024-12-16 | Service Delivery | To request from the hub the testing materials | Laboratory incharge | immediately.
ENTEBBE | WAKISO | KOMAMBOGA HEALTH CENTRE III | 2024-12-13 | Service Delivery | To engage NMS to deliver the items that are requested by the facility | KCCA and NHLDS | 3 months
ENTEBBE | WAKISO | WAKISO HEALTH CENTRE IV | 2024-12-12 | Service Delivery | To have MOH and NMS agree on terms of suppling consistently these test kits | NHLDS | 3 Months
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | Service Delivery | CPHL to follow up
FORTPORTAL | KAMWENGE | RUKUNYU GENERAL HOSPITAL | 2024-12-19 | Service Delivery | Supplying the facility with EID POC reagent cartridges | CPHL/JMS | 1 month
FORTPORTAL | KASESE | MT ST MARY'S HOSPOTIALS KILEMBE | 2024-12-23 | Service Delivery | Followed up with JMS | Lab manager
FORTPORTAL | KASESE | MT ST MARY'S HOSPOTIALS KILEMBE | 2024-12-23 | Service Delivery | A 16 module requested | Regional Supply
FORTPORTAL | KASESE | MT ST MARY'S HOSPOTIALS KILEMBE | 2024-12-23 | Service Delivery | Adopt to new Mt St Mary's name into the JMS ordering platform | Regional Supply
GULU | AGAGO | DR AMBROSOLI MEMORIAL HOSPITAL-KALONGO | 2024-12-23 | Service Delivery | Follow up the repair for the biosafety cabinet | Laboratory manager | 3 months
GULU | GULU | PATIKO H/CIII | 2025-03-20 | Service Delivery | Timely running of order fill rate and timely submission to NMS | Outsourcing from other facilities
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2024-12-17 | Service Delivery | Develop a costed procurement plan and share with the relevant authorities | Yandua Matayo | 6 months (June 2025)
GULU | GULU CITY | ST MARY'S HOSPITAL LACOR | 2025-03-21 | Service Delivery | Request for BD presto from Gulu RRH | Otim felix | 30th March 2025
GULU | GULU CITY | ST MARY'S HOSPITAL LACOR | 2025-03-21 | Service Delivery | Place emergency orders for TB LAM and missing lab supplies to JMS | Otim Felix | 30th March 2025
GULU | KITGUM | KITGUM GENERAL HOSPITAL | 2024-12-20 | Service Delivery | Follow up the order with NMS | Laboratory manager | 3 months
GULU | KITGUM | ST. JOSEPH'S HOSPITAL KITGUM | 2025-03-21 | Service Delivery | Fasten the Procurement process | Pharmacist | 30/4/2025
GULU | KITGUM | ST. JOSEPH'S HOSPITAL KITGUM | 2025-03-21 | Service Delivery | Make use of backup machine (Swelab Heamatology system Machine) | Quality officer (Ronald) | 24/3/2025
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | Service Delivery | DHO to make submissions for recruitment to District service commision | DHO/Lamwo District Local Government | 2025/2026 Financial year
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | Service Delivery | Implementation of equipment supply plan | UNHLS | 2025/2026 FY
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | Service Delivery | Instalation of power backups | Facility incharge | 2025/2026 FY
GULU | NWOYA | KOCHGOMA HCIII | 2025-03-21 | Service Delivery | Follow up undelivered orders by NMS | Lab manager | June 2025
GULU | OMORO | LALOGI HC IV | 2024-12-18 | Service Delivery | Resubmit the order | Laboratory manager | 3 months
GULU | PADER | PAJULE HCIV | 2025-08-08 | Service Delivery | Follow up with the district procurement offi equipment to liase with the CPHL/MOH such that the missing equipment be placed | Laboratory Incharge | 15/09/2025
GULU | PADER | PAJULE HCIV | 2025-08-08 | Service Delivery | Following the service schedule through engaging service providers | Laboratory Manager | 15/09/2025
GULU | PADER | PAJULE HCIV | 2025-08-08 | Service Delivery | Review and verify the order before submitted and also following up with NMS to ensure items are delivered | Laboratory Manager | 15/09/2025
GULU | PADER | PURANGA HCIII | 2025-03-28 | Service Delivery | Customized the test menu for HCIII
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | Service Delivery | ENGAGE NMS TO ENSURE ORDERS MADE ARE HONOURED | FACILITY MANAGER | IMMEDIATE
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | Service Delivery | ENGAGE GOVERNMENT TO PROVIDE MORE EQUIPMENT | FACILITY MANAGER | IMMEDIATE
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | Service Delivery | ENGAGE STAKE HOLDERS TO IMPROVE LAB INFRASTURE | DHO, CAO | IMMEDIATE
JINJA | BUGIRI | NANKOMA HC IV | 2026-03-25 | Service Delivery | ENGAGE GOVT FOR MORE EQUIPMENT | FACILITY MANAGER | IMMEDIATE
JINJA | BUGWERI | BUSESE HC IV | 2026-03-20 | Service Delivery | ENGAGE NMS TO DO TIMELY DELIVERY | FACILITY MANAGER | IMMEDIATE
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | Service Delivery | MJAP to procure service contract for human machines | MJAP Laboratory advisor and laboratory manager | Jan 2025
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | Service Delivery | Jinja RRH to support the facility with some TB Lam kits | Lab manager | Dec 2024
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | Service Delivery | CHPL to provide some EID and HIV VL Pima cartridges as soon as the supplier provides them in the country | Dina CPHL | Feb 2025
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | Service Delivery | Request for CPHL to support with the missing items | Dina CPHL | Feb 2025
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | Service Delivery | IP to procure service contract | Lab advisor and laboratory manager | Feb 2025
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | Service Delivery | IP to support in procuring service contract | Lab advisor and laboratory manager | Feb 2025
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | Service Delivery | Jinja RRH to support Kamuli with some kits | James higenyi | Jan 2025
JINJA | MAYUGE | MAYUGE HC IV | 2026-03-24 | Service Delivery | TAKEN TO REPAIR AT CPHL | LAB MANAGER | APRIL 2026
JINJA | NAMAYINGO | BUYINJA HC IV | 2026-03-09 | Service Delivery | ENGAGE NMS MAKE TIMELY DELIVERY | DHO, FACILITY IN CHARGE | IMMEDIATE
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | Service Delivery | CHPL to supply the missing cartridges | DINA chpl | march 2025
KABALE | KABALE | KABALE RRH | 2024-12-10 | Service Delivery | Liase with NMS for missing reagents | Laboratory manager and Hospital director | March 2025
KABALE | KISORO | KISORO HOSPITAL | 2024-12-09 | Service Delivery | Follow up with the NMS about their inconsistent supply of ordered items | Laboratory management | March 2025
KAMPALA | KAMPALA | KIRUDDU NATIONAL REFERAL HOSPITAL | 2024-12-19 | Service Delivery | To lobby for a functional histopathology laboratory. | Laboratory director | 4 months.
KAYUNGA | BUVUMA | BUSAMIZI HEALTH CENTER III | 2025-04-10 | Service Delivery | Make requestion to support redistribution | Denis Kisitu [DLFP] | March 2025
KAYUNGA | KAYUNGA | KAYUNGA RRH | 2024-12-12 | Service Delivery | Privately procuring needed items with hospital budget | Lab manager | March 2025
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Service Delivery | Follow up with NTRL on update concerning replacement of the GeneXpert Machine | Rashid, Joy Mary | AUGUST 2025
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Service Delivery | Follow up with CPHL on update of giving Kala | Rashid, Joy Mary | AUGUST 2025
KAYUNGA | LUWERO | LUWEERO GENERAL HOSPITAL | 2024-12-18 | Service Delivery | Make an emergency order for missing kits , Refer samples to nearby testing sites | Inventory Officer, LM | 20-12-2024
KAYUNGA | LUWERO | LUWERO GENERAL HOSPITAL | 2025-03-12 | Service Delivery | Do clinical lab interface about the gram testing | Gerald | April 2025
KAYUNGA | NAKASONGOLA | NABISWERA HEALTH CENTER IV | 2025-03-11 | Service Delivery | CPHL to make consideration during the next alocations to provide an mPIMA to the facility | CPHL | December 2025
KAYUNGA | NAKASONGOLA | NAKASONGOLA HC IV | 2024-12-19 | Service Delivery | Source the reagents from nearby facilities | Hub Coordinator | 31-12-2024
KAYUNGA | NAKASONGOLA | NAKASONGOLA HC IV | 2024-12-19 | Service Delivery | Follow up online orders with Phone calls | Hub Coordinator, Lab Manager | 24-12-2024
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | Service Delivery | Use EQA remnant samples to make IQC material | David and Lillian | June 2025
MASAKA | BUKOMANSIMBI | BUTENGA | 2025-06-25 | Service Delivery | loby for more supplies | incharge | 4 month
MASAKA | KALANGALA | KALANGALA HCIV | 2025-07-31 | Service Delivery | Include Kalangala on NMS list | RLM, DLFP, Judith | 06 months
MASAKA | KALUNGU | BUKULULA | 2025-06-26 | Service Delivery | lobby for space for lab | DHO. INCHARGE | 6 Month
MASAKA | KALUNGU | BUKULULA | 2025-06-26 | Service Delivery | lobbby for equipments | DHO | 4 month
MASAKA | KYOTERA | KALISIZO GENERAL HOSPITAL | 2025-07-30 | Service Delivery | Request for gram reagents | Lab Manager, DLFP | 06 Months
MASAKA | LWENGO | LWENGO HEALTH CENTRE IV | 2024-12-10 | Service Delivery | replace obsolete equipment | MOH | 3 months
MASAKA | MASAKA | KYANAMUKAAKA | 2025-06-28 | Service Delivery | recruitment | CAO,DHO | 6 month
MASAKA | MASAKA CITY | KIYUMBA HCIV | 2025-06-24 | Service Delivery | expand the lab infrustructure to accomodate the available equipments | incharge | dec 2025
MASAKA | MASAKA CITY | MASAKA REGIONAL REFERRAL HOSPITAL | 2025-06-27 | Service Delivery | RECUITMENT OF STAFFSS | MANAGER,PRINCIPAL HUMAN RESOURCE AND SENIOR MANAGEMENT CONSULTANTS | 6 MONTHS
MASAKA | SEMBABULE | SEMBABULE HC IV | 2025-06-23 | Service Delivery | refer tests not being done | Francis | 1 month
MBALE | BUDUDA | BUDUDA DISTRICT HOSPITAL | 2025-04-01 | Service Delivery | To order for reagents from NMS | Lab manager and lab logistics | By April 2025
MBALE | BUDUDA | BUDUDA DISTRICT HOSPITAL | 2025-04-01 | Service Delivery | To procure power backup | Hospital administration
MBALE | BUSIA | MASAFU HOSPITAL | 2025-04-11 | Service Delivery | Need to follow up with CPHL on CD4 catridges | PLT Mbale | 3 months
MBALE | BUTALEJA | BUSOLWE HOSPITAL | 2025-04-09 | Service Delivery | Redistribution of reagents, following up with NMS | Logistics, lab manager | April 2025
MBALE | BUTALEJA | NABIGANDA HC IV | 2025-04-07 | Service Delivery | Write to CPHL to avail chemistry analyser | Regional lab manager | June 2025
MBALE | PALLISA | PALLISA HOSPITAL | 2025-04-02 | Service Delivery | To place an order with NMS | Lab manager, logistics officer
MBALE | TORORO | TORORO GENERAL HOSPITAL | 2025-04-16 | Service Delivery | Timely ordering | Logistics officer | Next six months
MBARARA | BUSHENYI | ISHAKA ADVENTIST HOSPITAL | 2026-03-16 | Service Delivery | To develop SOP | Quality Manager | By end of April
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | Service Delivery | Need to forecast needs of supplies and order for adequate supplies and on time | Facility incharge | 2 months
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | Service Delivery | to always follow up with CPHL | Laboratory staff/ Hub coordinator | 1 month
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | Service Delivery | follow up with concerned authorities | MOH | Were promised soon(last year)
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2024-12-20 | Service Delivery | Right quantification during ordering and redistribution | Laboratory manager | January 2025
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2024-12-20 | Service Delivery | new infrustructural block needs to be constructed | DHO | June 2025
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2026-02-24 | Service Delivery | Lab in charge | 3 months
MOROTO | KAABONG | KAABONG GENERAL HOSPITAL | 2026-02-25 | Service Delivery | All stake holders particularly hospital administration | 12 months
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | Service Delivery | Right quantification during ordering and redistribution | Laboratory In charge | February 2025
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | Service Delivery | Procure solar system for the laboratory | ANECCA/ Facility In charge | June 2025
MUBENDE | KASSANDA | KASSANDA HEALTH CENTRE IV | 2024-12-13 | Service Delivery | To write to the IP to help on battery replacement | DHO,Facility Incharge | 30th/Jan/2024
MUBENDE | KASSANDA | KASSANDA HEALTH CENTRE IV | 2024-12-13 | Service Delivery | To lobby from the District LC5 for a transformer | DHO, Facility Incharge | 30th/Jan/2024
MUBENDE | MITYANA | MITYANA HOSPITAL | 2024-12-12 | Service Delivery | To lobby for space where to put microbiology lab and also lobby for microbiology supplies | Lab Manager | 30th/mar/2025
MUBENDE | MITYANA | MITYANA HOSPITAL | 2024-12-12 | Service Delivery | To lobby for more analysers from CPHL | Lab manager | 30th/mar/2025
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | Service Delivery | To plan for procurement of missing reagents and equipment | MRRH and MOH | 30 July 2025
SOROTI | AMURIA | AMURIA GENERAL | 2025-08-22 | Service Delivery | request for microbiology services/Equipment from CPHL | Lab manager | 30th Sept 2025
SOROTI | AMURIA | AMURIA GH | 2024-12-12 | Service Delivery | Procure the equipment | IP/MOH
SOROTI | AMURIA | AMURIA GH | 2024-12-12 | Service Delivery | Timely and consistent supply of commodities | IP/MOH
SOROTI | AMURIA | AMURIA HOSPITAL | 2025-03-25 | Service Delivery | Out source lab commodities from facilities that are well stocked. NMS should endeavor to deliver ordered commodities in time as per the delivery schedule. | Lab manager/NMS | 30/4/2025
SOROTI | KABERAMAIDO | KABERAMAIDO GENERAL | 2025-08-21 | Service Delivery | Redistribution from sister hubs | George | two weeks
SOROTI | KABERAMAIDO | KABERAMAIDO GENERAL HOSPITAL | 2026-03-17 | Service Delivery | Write to minstry of health to request for one | HOD | Two weeks
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2025-03-24 | Service Delivery | Source out from well stocked facilities. Timely delivery of orders by NMS. | Lab manager/DLFP | 30/5/2025
SOROTI | KALAKI | LWALA | 2025-08-20 | Service Delivery | loby for an equipment and order for supplies | admin | 2025/2026 FY
SOROTI | KALAKI | LWALA HOSPITAL | 2026-03-17 | Service Delivery | Correct quantification of orders | HOD | Ongoing
SOROTI | KATAKWI | KATAKWI GENERAL | 2025-08-20 | Service Delivery | lobby for more equipment to enable the lab widen their test menu e.g Microbiology services | lab manager | 30th sept 2025
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | Service Delivery | Supply commodities | MOH
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | Service Delivery | Procure the required equipment | MOH
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | Service Delivery | Timely delivery of lab commodities by NMS | NMS(Lab manager follows up the requests) | 20/4/2025(next consignment)
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | Service Delivery | 1. Source out cartridges from health facilities that have stock. NMS to ensure prompt delivery of the supplies. | Lab logistician and NMS | 30/5/2025
SOROTI | KUMI | ATUTUR GENERAL HOSPITAL | 2026-03-25 | Service Delivery | Order from NMS / improve order and quantification | Lab Manager | Two weeks
SOROTI | KUMI | ATUTUR GENERAL HOSPITAL | 2026-03-25 | Service Delivery | Staff incompetence | Quality officer | On going
SOROTI | KUMI | ATUTUR HOSPITAL | 2024-12-10 | Service Delivery | Procure the equipment
SOROTI | KUMI | ATUTUR HOSPITAL | 2024-12-10 | Service Delivery | consistent supply of commodities | NMS
SOROTI | KUMI | KUMI HCIV | 2024-12-09 | Service Delivery | Provide equipment | MOH | 1 QUARTER
SOROTI | NGORA | NGORA | 2025-08-13 | Service Delivery | order for kits from NMS | lab manager | 30th sept 2025
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | Service Delivery | order and follow up with NMS | Lab Manager | 01/04/2025
SOROTI | NGORA | NGORA HCIV | 2026-03-18 | Service Delivery | Correct quantification of commodities while ordering | HOD | Ongoing
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | Service Delivery | Make a request to NMS for cartridges. Source out from other health facilities. | Lab manager | 30/3/2025(In the next consignment)
SOROTI | SERERE | SERERE HEALTH CENTER IV | 2026-03-20 | Service Delivery | Poor quantification and forecast | Lab Manager | Two weeks
SOROTI | SOROTI | SOROTI | 2024-12-13 | Service Delivery | timely ordeing of commodities | lab manager
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2026-03-16 | Service Delivery | correct quantification of orders to NMS | Logistics person | Ongoing
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2026-03-16 | Service Delivery | conduct CME on stockcard usage | Quality officer | 30/03/2026
ENTEBBE | WAKISO | BUWAMBO HCIV | 2026-01-21 | Service Delivery | Staff shortage
ENTEBBE | WAKISO | BUWAMBO HCIV | 2026-01-21 | Service Delivery | lack of chemistry equipment
ENTEBBE | WAKISO | BUWAMBO HCIV | 2026-01-21 | Service Delivery | lack of training in LQMS
ENTEBBE | WAKISO | NABWERU HCIII | 2026-01-20 | Service Delivery | Limited test menu coverage
ENTEBBE | WAKISO | NAMAYUMBA HCIV | 2026-01-19 | Service Delivery | Staffing gaps
FORTPORTAL | BUNYANGABU | KIBIITO HEALTH CENTER IV | 2026-01-20 | Service Delivery | The absence of a chemistry analyzer presents a challenge in providing timely chemistry test results, contributing to prolonged turnaround times and delayed clinical interventions, due to the high demand. | Procure and install chemistry analyzer. |  | By the end of 2026
FORTPORTAL | BUNYANGABU | RWIMI PRISON HEALTH CENTER III | 2026-01-20 | Service Delivery | The absence of a GeneXpert platform presents a significant challenge in delivering rapid diagnostic results. | Procure and install a GeneXpert machine. |  | By the end of the 2nd quarter
FORTPORTAL | BUNYANGABU | RWIMI PRISON HEALTH CENTER III | 2026-01-20 | Service Delivery | The lack of a biosafety cabinet for sputum sample processing poses a challenge in ensuring adequate protection of laboratory staff. | Procure and intall a biosafety cabinet, Class II |  | By the end of the year 2026
FORTPORTAL | FORT PORTAL CITY | BUKUKU HEALTH CENTRE IV | 2026-01-22 | Service Delivery | Absence of a chemistry analyzer | Plan and procure a chemistry analyzer |  | By end of 2026.
FORTPORTAL | KASESE | BWERA GENERAL HOSPITAL | 2026-01-19 | Service Delivery | No coagulation tests | To provide supplies |  | By the end of the 2nd quarter
FORTPORTAL | KITAGWENDA | NTARA HC IV MAIN LABORATORY | 2026-01-23 | Service Delivery | None
FORTPORTAL | KITAGWENDA | NTARA HCIV | 2026-03-30 | Service Delivery | NOT DOING CBC | request for redistribution for other health facilities |  | 30/04/2026
FORTPORTAL | KITAGWENDA | NYABANI HCIII | 2026-03-30 | Service Delivery | NOT DOING MICROSCOPY | SEND A MICROSCOPE TO THE REGIONAL WORKSHOP |  | 30.04.2026
FORTPORTAL | NTOROKO | KARUGUTU HCIV | 2026-03-19 | Service Delivery | NO MICROBIOLOGY LAB | REFER CULTURE SAMPLES |  | 30/06/2026
FORTPORTAL | NTOROKO | KARUGUTU HEALTH CENTRE IV | 2026-01-21 | Service Delivery | None
FORTPORTAL | NTOROKO | RWEBISENGO HCIV | 2026-03-19 | Service Delivery | NOT DOING CHEMISTRY TESTS | WRITE THROUGH THE DHO FOR PLACEMENT OF A CHEMISTRY MACHINE FROM HUMAN DIAGNOSTICS |  | 30/09/2026
HOIMA | BULIISA | BULIISA HEALTH CENTRE IV | 2026-01-28 | Service Delivery | The equipment required for the implementations of some of the tests in the test menu are not availed at the facility
HOIMA | BULIISA | BULIISA HEALTH CENTRE IV | 2026-01-28 | Service Delivery | Some of the supplies including kits and reagents required for some of the tests in the test menu are not supplied by NMS
HOIMA | BULIISA | BULIISA HEALTH CENTRE IV | 2026-01-28 | Service Delivery | There is limited human resource to perform/ implement all the tests in the test menu
HOIMA | KIBAALE | KIBAALE HEALTH CENTRE IV | 2026-01-27 | Service Delivery | Unreliable electricity at the facility
HOIMA | KIBAALE | NYAMARWA HEALTH CENTER III | 2026-01-26 | Service Delivery | Some tests are not performed at the laboratory because of lack reagents/ test kits
HOIMA | KIBAALE | NYAMARWA HEALTH CENTER III | 2026-01-26 | Service Delivery | Equipment for the tests are not available.
HOIMA | KIKUUBE | KYEHORO HEALTH CENTER III | 2026-01-29 | Service Delivery | The reagents required for the performance of other tests in the test menu are not provided
HOIMA | KIKUUBE | KYEHORO HEALTH CENTER III | 2026-01-29 | Service Delivery | The equipment required for some of these lab tests are not availed
HOIMA | MASINDI | BWIJANGA HEALTH CENTRE IV | 2026-01-30 | Service Delivery | The laboratory suppliess and equipment required for the implementation of some of the tests in the test menu are not supplied to the the facility
HOIMA | MASINDI | BWIJANGA HEALTH CENTRE IV | 2026-01-30 | Service Delivery | There is space limitation within the laboratory
HOIMA | MASINDI | MASINDI TASO | 2026-02-02 | Service Delivery | Some of the tests are not done at masindi TASO
JINJA | JINJA | BUGEMBE HCIV | 2026-01-19 | Service Delivery | Absence of the national guidelines, that is; National Test Menu, TB Laboratory Manual and National Diagnostic Algorithm | Download online copies of the national guidelines and print them out. |  | 19th January, 2026 | 2026-01-19 | Jan | 2026
JINJA | JINJA | BUGEMBE HCIV | 2026-01-19 | Service Delivery | Facility does not carry out the tests on their test menu, for example the Hepatitis B antigen test | Contact the City Health Officer (CHO))to request for kits |  | 20th January 2026 | 2026-01-20 | Jan | 2026
JINJA | JINJA | BUGEMBE HCIV | 2026-01-19 | Service Delivery | Facility does not carry out clinical tests, consequently partially perfoming the tests required of the them as per the national test menu. Additionally, there are sufficient and spacious bench tops to place equipment on. | Monthly report to be forwarded to CHO to request for machines from MOH. |  | 28th January 2026 | 2026-01-28 | Jan | 2026
JINJA | KAMULI | BULOPA H/C III | 2026-01-26 | Service Delivery | No kits for rapid sickle cell test. | Request for rapid sickle cell kits from CPHL and staff to receive refresher training. |  | 27th February, 2026 | 2026-02-27 | Feb | 2026
JINJA | KAMULI | BULOPA H/C III | 2026-01-26 | Service Delivery | Absence of the national guidelines that is national test menu, Tb laboratory manual, NTLP manual and National Diagnostic Algorithm. | Download online copies of the national guidelines and print them out. |  | 28th January 2026 | 2026-01-28 | Jan | 2026
JINJA | KAMULI | NAMWENDWA H/CIV | 2026-01-23 | Service Delivery | Facility does not carry out clinical chemistry tests and CD4 count testing. | Lab in-charge to Make a monthly report detailing a proposal for renovation of the facility laboratory and write a report making reference to the national test menu and identify equipment needed by facility at their level and start testing. |  | 27th February 2026 | 2026-02-27 | Feb | 2026
JINJA | KAMULI | NAMWENDWA H/CIV | 2026-01-23 | Service Delivery | Inadequate staffing at the facility with the laboratory department having to depend on volunteers and students to carryout testing in the laboratory. | MOH to organize supervision programmes at facilities for atleast a month to monitor performance. |  | 30th April 2026 | 2026-04-30 | Apr | 2026
JINJA | KAMULI | NAMWENDWA H/CIV | 2026-01-23 | Service Delivery | Absence of the national guidelines that is national test menu, Tb laboratory manual, NTLP manual and National Diagnostic Algorithm. | Download online copies of the national guidelines and print them out. |  | 28th January 2026. | 2026-01-28 | Jan | 2026
JINJA | MAYUGE | KIGANDALO HC IV | 2026-01-21 | Service Delivery | Facility does not have the current versions of the manuals. | Lab-incharge to download current version of the manuals and print them. |  | 22nd January,2026 | 2026-01-22 | Jan | 2026
KABALE | KABALE | MAZIBA HC IV | 2026-01-30 | Service Delivery | Chemistry tests and clotting time tests are not offered | To advocate for a Clinical Chemistry analyzer and a water bath |  | June 2026
KABALE | KABALE | MAZIBA HC IV | 2026-01-30 | Service Delivery | Bleeding time test is not offered | To review and update the laboratory test menu to include Bleeding time |  | Feb 2026 | 2026-02-28 | Feb | 2026
KABALE | KABALE | MAZIBA HC IV | 2026-01-30 | Service Delivery | Hepatitis A, Hep C, H.Pyroli and typhoid tests not offered | To follow up with NMS for test kits ordered for but not supplied such as test kits for Hepatitis A, Hep. C, H.pyroli, Typhoid tests |  | Feb 2026 | 2026-02-28 | Feb | 2026
KABALE | KISORO | MURAMBA HEALTH CENTRE III | 2026-01-28 | Service Delivery | Only 73% of tests on the national laboratory test menu for HC III level conducted | To advocate for inclusion of tests such as H.Pylori, Hep. A, Hep. C on the NMS catalogue and to advocate for a WBC analyzer |  | April 2026 | 2026-04-30 | Apr | 2026
KABALE | KISORO | MURAMBA HEALTH CENTRE III | 2026-01-28 | Service Delivery | Over 20 patients presumed to have TB in Dec 2025 and Jan 2026 are not registered in TB lab register and therefore not tested for TB | Test sputum samples using TB microscopy before referral for GeneXpert |  | Feb 2026 | 2026-02-28 | Feb | 2026
KABALE | KISORO | MURAMBA HEALTH CENTRE III | 2026-01-28 | Service Delivery | Testing for Sickle Cell Disease not done | To order for test kits for SCD in the next order cycle |  | March 2026 | 2026-03-31 | Mar | 2026
KAMPALA | KAMPALA | KAWEMPE NATIONAL REFERRAL HOSPITAL | 2026-01-22 | Service Delivery | Delays in supplies delivery | Make regular follow-ups
KAYUNGA | MUKONO | GOMA HCIII | 2026-02-03 | Service Delivery | For the tests not done, the reagents are not supplied even if ordered | Incharge to follow up with NMS |  | 28/02/26
KAYUNGA | MUKONO | GOMA HCIII | 2026-02-03 | Service Delivery | Stock out of reagents | To involve the DLFP incase of stock outs to see if they can be got from the facilities |  | 28/02/26
KAYUNGA | MUKONO | KASAWO HCIII | 2026-01-27 | Service Delivery | Lack of supplies to perform some tests on the menu e.g Helicobacter Pylori, Hepatitis B | To borrow and keep putting in orders |  | 28th Febuary 2026
KAYUNGA | MUKONO | KYAMPISI HCIII | 2026-01-30 | Service Delivery | No equipment and reagents to carry out some tests | Incharge to find out if they can provide the tests |  | 28/02/26
KAYUNGA | MUKONO | NAGALAMA HOSPITAL | 2026-01-29 | Service Delivery | Some reagents to some tests are expensive | To always forecast and engage DLFP |  | Ordering cycle
KAYUNGA | MUKONO | NAGALAMA HOSPITAL | 2026-01-29 | Service Delivery | Some tests are not commonly requested for and there are always few cases | To inform clinicians on the test menu |  | 28/02/2024
KAYUNGA | MUKONO | NAKIFUMA HCIII | 2026-01-28 | Service Delivery | Some equipment to do some tests like differential counter are not available | lab incharge to engage management to purchase the necessary equipment |  | 28th February 2026 | 2026-02-28 | Feb | 2026
KAYUNGA | MUKONO | NAKIFUMA HCIII | 2026-01-28 | Service Delivery | Staffing gap | Advocate for more staff
KAYUNGA | MUKONO | SEETA NAZIGO HCIII | 2026-02-02 | Service Delivery | Some supplies are not given to perform the tests on the test menu | Lab incharge to look into the possibility of revising the order menu |  | 31/03/2026
KAYUNGA | MUKONO | SEETA NAZIGO HCIII | 2026-02-02 | Service Delivery | Unstable power affects testing | Follow up with a facility incharge to install power backup |  | 31/3/26
KAYUNGA | MUKONO | SEETA NAZIGO HCIII | 2026-02-02 | Service Delivery | Stock out of supplies | Lab incharge to ensure stock outs do not occur
LIRA | AMOLATAR | AMOLATA HEALTH CENTRE IV | 2026-01-20 | Service Delivery | hi
LIRA | KOLE | ABOKE HC IV | 2026-01-21 | Service Delivery | No capacity for conducting Clinical chemistry test and Sickle cell Disease detection
LIRA | KOLE | ABOKE HC IV | 2026-01-21 | Service Delivery | The facility still has obsolete documents for TB diagnostics | NTLP to disseminate TB tools to all health facilities |  | May 2026 | 2026-05-31 | May | 2026
LIRA | OYAM | ATIPE HCIII | 2026-01-23 | Service Delivery | The facility lacked national guideline for diagnostics |  |  | March 2026 | 2026-03-31 | Mar | 2026
MASAKA | KYOTERA | KALISIZO GENERAL HOSPITAL | 2026-01-27 | Service Delivery | Coagulation assays not done | Run bleeding time for the mean time, Conduct a CME on bleeding time, Develop a SOP and a bench guideline |  | 28th February, 2026 | 2026-02-28 | Feb | 2026
MASAKA | KYOTERA | KALISIZO GENERAL HOSPITAL | 2026-01-27 | Service Delivery | ESR test not done | Presumptively monitor CBC counts |  | 28th February, 2026 | 2026-02-28 | Feb | 2026
MBARARA | BUSHENYI | KYEIZOOBA HCIII | 2026-02-05 | Service Delivery | Lack of equipment to run the tests | The management should work hand in hand with the implementing partners to see that the necessary equipment are procured |  | 5/05/2026
MBARARA | IBANDA | ISHONGORORO HCIV | 2026-02-09 | Service Delivery | No chemistry tests done | The reagents should be ordered before a total stock outs |  | 28/02/2026
MBARARA | IBANDA | RUHOKO HCIV | 2026-02-06 | Service Delivery | Some tests are not being run | The lab in-charge should follow up with the regional workshop to have the equipment repaired |  | 28/02/2026
MBARARA | MBARARA CITY | RUHARO MISSION HOSPITAL | 2026-02-02 | Service Delivery | Reagent stockouts | Keep track of the online ordering system and the actual physical count |  | 10/02/2026
MBARARA | MBARARA CITY | RUHARO MISSION HOSPITAL | 2026-02-02 | Service Delivery | Inavailability of equipment to run tests | Talk to management to look into the volumes of samples /tests conducted |  | 16/05/2026
MBARARA | MBARARA CITY | RUHARO MISSION HOSPITAL | 2026-02-02 | Service Delivery | Unstable power supply | Conduct a power audit to do an analysis of what is needed to improve the state of the power supply |  | 19/05/2026
MBARARA | SHEEMA | KABWOHE HCIV | 2026-02-03 | Service Delivery | Reagent stock out | The lab in charge to make a request to have the reagents added on the NMS catalogue |  | 3/05/2026
MBARARA | SHEEMA | KABWOHE HCIV | 2026-02-03 | Service Delivery | Unstable power supply | The lab in charge should follow up with the regional workshop |  | 3/05/2026
MBARARA | SHEEMA | KABWOHE HCIV | 2026-02-03 | Service Delivery | Congestion in the lab | The construction is ongoing |  | 3/12/2026
MBARARA | SHEEMA | KIGARAMA HCIII | 2026-02-04 | Service Delivery | Failure to send the DBS (plasma) | The facility management should devise means to see how to procure a centrifuge |  | 4/12/2026
MOROTO | AMUDAT | AMUDAT HOSPITAL | 2026-01-21 | Service Delivery | The installed solar power only support the running of a few key equipment | as they await for the intermittent power supply from the Sironko power grid to be stabilized |  | End of March 2026
MOROTO | AMUDAT | LOORO HC III | 2026-01-20 | Service Delivery | Only two laboratory personnel working in alternating shifts, resulting in overwhelming workload |  |  | Long term
MOROTO | KAABONG | KAABONG HOSPITAL | 2026-01-19 | Service Delivery | Breakdown of key equipment like Humastar 200, HumaCount 60 | In the event of Equipment breakdown while awaiting repairs and maintenance, samples were being re-routed to Matany, Moroto, Kotido, and Abim |  | End of February 2026
MOROTO | NABILATUK | NABILATUK HC IV | 2026-01-23 | Service Delivery | Only two laboratory personnel working in alternating shifts, resulting in overwhelming workload |  |  | End of March 2026
MOROTO | NAKAPIRIPIRIT | TOKORA HEALTH CENTER IV | 2026-01-26 | Service Delivery | Short shelf life of EID/Viral Load test kits |  |  | End of March 2026
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2026-01-28 | Service Delivery | Stock outs | NMS to supply orders prompt
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2026-01-28 | Service Delivery | Unstable internet | need to strengthen internet connectivity
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2026-01-28 | Service Delivery | power outrages | procure power backup batteries
SOROTI | KABERAMAIDO | LWALA HOSPITAL | 2026-01-22 | Service Delivery | Commodity stockouts
SOROTI | KATAKWI | AKETA HCIII | 2026-01-19 | Service Delivery | LEVEL OF FACILITY | leaverage on hub system |  | 30.1.2026
SOROTI | KATAKWI | AKETA HCIII | 2026-01-19 | Service Delivery | Infrastructure | Advocacy |  | Continuous
SOROTI | KATAKWI | AKETA HCIII | 2026-01-19 | Service Delivery | Understaffing | Continuous lobbying for staff |  | Continuous
SOROTI | KUMI | MUKONGORO HCIII | 2026-01-30 | Service Delivery | STOCK OUTS
SOROTI | KUMI | MUKONGORO HCIII | 2026-01-30 | Service Delivery | DIGITALISATION LACKING
SOROTI | SERERE | SERERE HCIV | 2026-01-21 | Service Delivery | Stock outs
SOROTI | SERERE | SERERE HCIV | 2026-01-21 | Service Delivery | equipment breakdown
SOROTI | SERERE | SERERE HCIV | 2026-01-21 | Service Delivery | power interruptions