## Sheet 1
RRH | District | HFacility | VDate | Identified Gap | Agreed Action Point | Institution Responsible | Timelines | Section | VDate_date | due_date | ActionMonth | ActionYr
ENTEBBE | GOMBA | MADDU HC IV | 2025-04-10 | The facility should fast tract the implementation of EMR system | Facility incharge/MOH | by jute/2025 |  | ICT | 2025-04-10
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2024-12-09 | To have the saver installed at the regional refferal | Lab manager and NHLDS | 1 month |  | ICT | 2024-12-09
ENTEBBE | WAKISO | KASANGATI HEALTH CENTRE III | 2024-12-16 | To have ALIS installed and trained on for use in the laboratory | LAB MANAGER AND CPHL | 2 months |  | ICT | 2024-12-16
ENTEBBE | WAKISO | KOMAMBOGA HEALTH CENTRE III | 2024-12-13 | To retrain all the staff on the use of ALIS | Kerchan ronald (lab manager) | 3 months |  | ICT | 2024-12-13
ENTEBBE | WAKISO | WAKISO HEALTH CENTRE IV | 2024-12-12 | to have the two machines interfaced. | Maryam nassali and Jackson cphl | 2 months |  | ICT | 2024-12-12
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | Implementation of HIE | Rebecca and Iga Tadeo | 2 month |  | ICT | 2024-12-20
FORTPORTAL | KAMWENGE | RUKUNYU GENERAL HOSPITAL | 2024-12-19 | Enroll facility on HIE | CPHL | 3months |  | ICT | 2024-12-19
FORTPORTAL | KASESE | MT ST MARY'S HOSPOTIALS KILEMBE | 2024-12-23 | Forward to national ICT manager |  |  |  | ICT | 2024-12-23
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | Discuss with IP | Lab Manager, MS |  |  | ICT | 2024-12-16
GULU | AGAGO | DR AMBROSOLI MEMORIAL HOSPITAL-KALONGO | 2024-12-23 | procure a power back up | Laboratory manager | 6 months |  | ICT | 2024-12-23
GULU | AMURU | ATIAK HEALTH CENTRE | 2025-08-08 | Continue engaging CPHL ICT team | DLFP | 30/8/2025 |  | ICT | 2025-08-08
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2024-12-17 | Follow up with IT personnel whenever there is internet hiccup | Sempiira Paul | January 2025 |  | ICT | 2024-12-17
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Conduct reqular training of staff on the operations of e-LIMS at the various departments | Matayo | Immediate |  | ICT | 2025-08-08
GULU | KITGUM | KITGUM GENERAL HOSPITAL | 2024-12-20 | IT team to check the connectivity and retrain staff | Laboratory manager | 3 months |  | ICT | 2024-12-20
GULU | KITGUM | ST. JOSEPH'S HOSPITAL KITGUM | 2025-03-21 | train and avail computers | ICT FP |  |  | ICT | 2025-03-21
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | Facility to request for equipments for LIMS | Lab In-charge | 2025/2026 FY |  | ICT | 2025-03-20
GULU | NWOYA | ANAKA GENERAL HOSPITAL | 2025-08-08 | To fully transition to e-lims | Lab manager | Two months |  | ICT | 2025-08-08
GULU | OMORO | BOBI HC3 | 2025-03-21 | Orientation of the government facility health information assistance onEMR | Facility Incharge | Immediately |  | ICT | 2025-03-21
GULU | OMORO | LALOGI HC IV | 2024-12-18 | Procure more internet data | Laboratory manager | 3 months |  | ICT | 2024-12-18
GULU | PADER | PAJULE HC IV | 2024-12-19 | Follow up for the procurment of a power back up | Laboratory manager | 6 months |  | ICT | 2024-12-19
GULU | PADER | PAJULE HCIV | 2025-08-08 | Follow up with the district health office to ensure computer Systems are put in the district procurement plan | DLFP and Lab Manager | Immediate and by end of August 2025 |  | ICT | 2025-08-08
GULU | PADER | PURANGA HCIII | 2025-03-28 | Provide computer and training of the personal on computer skills | Facility in charge | Next financial year 2025/2026 |  | ICT | 2025-03-28
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | GOVERNMENT TO PROVIDE MORE SERVERS TO FACILITATE ALIS UTILISATION | FACILITY MANAGER, CPHL | IMMEDIATE |  | ICT | 2026-03-26
JINJA | BUGIRI | NANKOMA HC IV | 2026-03-25 | ENGAGE STAKEHOLDERS PROVIDE COMPUTERS, ALIS SERVERS | FACILITY MANAGER, CPHL | IMMEDIATE |  | ICT | 2026-03-25
JINJA | BUGWERI | BUSESE HC IV | 2026-03-20 | ENGAGE THE ADMINISTATION ON POWER BACK UP | DHO | IMMEDIATE |  | ICT | 2026-03-20
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | IP to support with the enabling of EMR to do HIE | lab manager and MJAP | JAN 2025 |  | ICT | 2024-12-09
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | train the facility on HIE | MJAP | JAN 2025 |  | ICT | 2024-12-12
JINJA | MAYUGE | MAYUGE HC IV | 2026-03-24 | ENGAGE IPs AND DLG FOR FUNDS | DLFPs FACILITY MANAGER | APRIL 2026 |  | ICT | 2026-03-24
KAMPALA | KAMPALA | KIRUDDU NATIONAL REFERAL HOSPITAL | 2024-12-19 | to have reduced internet interruptions by purchasing more mbps | Lab manager | 3 months |  | ICT | 2024-12-19
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Leverage on the PHC and IP support to get data bundles | Twahirwa Henry | Continous |  | ICT | 2025-03-14
KAYUNGA | LUWERO | LUWEERO GENERAL HOSPITAL | 2024-12-18 | Procure Missing batteries for Back up system | IP | March 2025 |  | ICT | 2024-12-18
KAYUNGA | LUWERO | LUWERO GENERAL HOSPITAL | 2025-03-12 | The Implementing partner to provide back up power plan to support the issue of power unstability at the facility | Richard (MUWRP) | October 2025 |  | ICT | 2025-03-12
MASAKA | KALUNGU | BUKULULA | 2025-06-26 | mentorships and coaching | CPHL&RRH | 6 month |  | ICT | 2025-06-26
MBALE | BUDUDA | BUDUDA DISTRICT HOSPITAL | 2025-04-01 | Train staff | IP | 1 month |  | ICT | 2025-04-01
MBALE | BUSIA | MASAFU HOSPITAL | 2025-04-11 | MRRH to train the facilities | Hub coordinator | 30, April, 2025 |  | ICT | 2025-04-11
MBALE | BUTALEJA | BUSOLWE HOSPITAL | 2025-04-09 | Train staff on HIE | Regional lab manager | June 2025 |  | ICT | 2025-04-09
MBALE | BUTALEJA | NABIGANDA HC IV | 2025-04-07 | Training by CPHL needed, computer and internet needed | IP | June 2025 |  | ICT | 2025-04-07
MBALE | SIRONKO | BUDADIRI HEALTH CENTER IV | 2025-04-14 | Avail more computers to lab and train users on ALIS utilizations | DHO , MOH | July 2025 |  | ICT | 2025-04-14
MBALE | TORORO | TORORO GENERAL HOSPITAL | 2025-04-16 | Ensure functionality of ALIS system | Mbale RRH | 3 months |  | ICT | 2025-04-16
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | Soon connecting to ALIS | IT teams facility/CPHL |  |  | ICT | 2024-12-11
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | Request IP for unlimited bundles and prompt renewal of subscriptions | IP | open |  | ICT | 2024-12-13
MOROTO | KARENGA | KARENGA HEALTH CENTRE IV | 2026-02-26 | Improve ALIS functionality and integration with EAFYA in 12 months |  |  |  | ICT | 2026-02-26
MUBENDE | KASSANDA | KASSANDA HEALTH CENTRE IV | 2024-12-13 | To request for more computer sets from the DHOs office | DLFP,Facility incharge | 30th/mar/2025 |  | ICT | 2024-12-13
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | To procure a new power backup system | MOH and Baylor Uganda | 30 March 2025 |  | ICT | 2024-12-16
MUBENDE | NAKASEKE | NGOMA HEALTH CENTRE IV | 2025-04-08 | To lobby for more computers from the Ip (baylor uganda) | Hub coordinator (Adowa molly) | 2 months |  | ICT | 2025-04-08
SOROTI | AMURIA | AMURIA GH | 2024-12-12 | Train and enroll the facility onto HIE | CPHL | Jan 2025 |  | ICT | 2024-12-12
SOROTI | AMURIA | AMURIA HOSPITAL | 2025-03-25 | Re-orientation of facility personnel and encourage utilization of the EMR for viral requests and results return. | UNHLDS/ART in charge (Lab manager to give feedback to the ART in charge since we were nt able to interact with him) | 30/4/2025 |  | ICT | 2025-03-25
SOROTI | KABERAMAIDO | KABERAMAIDO GENERAL | 2025-08-21 | Facility management to lobby for a stable power back up system | med.SUP | 2025/26 FY |  | ICT | 2025-08-21
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2025-03-24 | Notify UNHLDS IT department and the implementing partner. | Lab manager | 30/04/2025 |  | ICT | 2025-03-24
SOROTI | KAPELEBYONG | KAPELOBYONG | 2025-08-19 | FUNCTIONALIZE THE USE OF ALIS FOR ALL LAB TESTS | LAB MANAGER | 30TH SEPT 2025 |  | ICT | 2025-08-19
SOROTI | KATAKWI | KATAKWI GENERAL | 2025-08-20 | Place the main server into the solar socket to avoid interruptions | ab manager | 30th Aug 2025 |  | ICT | 2025-08-20
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | train facilities in HIE | CPHL | I month |  | ICT | 2024-12-11
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | Ensure the computers are serviced as scheduled to avoid service interruptions. | HMIS foal person | 30/03/2025 |  | ICT | 2025-03-20
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | Lobby for data and internet connectivity for the laboratory. | Lab manager | 30/04/2025 |  | ICT | 2025-03-18
SOROTI | KUMI | ATUTUR HOSPITAL | 2024-12-10 | Have machines connected | CPHL | 1 month |  | ICT | 2024-12-10
SOROTI | KUMI | KUMI HOSPITAL-ONGINO | 2025-08-22 | IT to identify a stable network connectivity | ICT TEAM | ONGOING |  | ICT | 2025-08-22
SOROTI | NGORA | NGORA | 2025-08-13 | Central team to service the server | CPHL team | Sept 2025 |  | ICT | 2025-08-13
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | procure new batteries for the backup system | AIC and MOH | 26/04/25 |  | ICT | 2025-03-17
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | procure solar for the facility | DHO | 30/04/25 |  | ICT | 2025-03-19