## Sheet 1
RRH | District | HFacility | VDate | Identified Gap | Agreed Action Point | Institution Responsible | Timelines | Section | VDate_date | due_date | ActionMonth | ActionYr
ENTEBBE | BUTAMBALA | GOMBE HOSPITAL | 2026-02-26 | No AMR surveillance done | Intiate C/A as this is starting point for c/s | DLFP/Lab Manager | 1yr | MB_AMR | 2026-02-26
ENTEBBE | GOMBA | GOMBE GENERAL HOSPITAL. | 2025-04-10 | Microbiology laboratory is not fully functional i.e no culture and sensitivity is being perfomed. | To lobby for the incubator through the DHO's office. | Nantabaazi irene | 4 months. | MB_AMR | 2025-04-10 | 2025-08-10 | Aug | 2025
ENTEBBE | GOMBA | MADDU HC IV | 2025-04-10 | No microbiological tests like culture, gram being performed | Lobby from Partners/MOH to acquire the needed items for microbiological tests | facility Head/DHO | Long term plan | MB_AMR | 2025-04-10
ENTEBBE | MPIGI | MPIGI HCIV LABORATORY | 2025-04-09 | No culture and sensitivity tests done | The lab should lobby for items to start up an active microbiological section | Lab incharge, facility Head/DHO/IP | Long term project | MB_AMR | 2025-04-09
ENTEBBE | WAKISO | KASANGATI HEALTH CENTRE III | 2024-12-16 | No bacteriology department at kasangati Health centre IV. | To have infrastracture development at kasangati Health centre IV to have a bacteriology department. | Facility incharge | 4 months. | MB_AMR | 2024-12-16 | 2025-04-16 | Apr | 2025
ENTEBBE | WAKISO | WAKISO HEALTH CENTRE IV | 2024-12-12 | No bacteriology lab at wakiso health centre IV. | to have a bacteriology lab at wakiso health centre iv | DLFP | 3 months | MB_AMR | 2024-12-12 | 2025-03-12 | Mar | 2025
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | Sample collecition bottle shortage | Follow up with CPHL/AMR | Ibrahim Mugerwa | 1month | MB_AMR | 2024-12-20 | 2025-01-20 | Jan | 2025
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | Support supervision and Mentorship of Microbiology /AMR | CPHL/ Fortportal reg. ref. | Ibrahim Mugerwa | 2months | MB_AMR | 2024-12-20 | 2025-02-20 | Feb | 2025
FORTPORTAL | KAMWENGE | RUKUNYU GENERAL HOSPITAL | 2024-12-19 | Training gap on AMR | Training and mentorship on AMR | 1. CPHL/AMR | 3 months | MB_AMR | 2024-12-19 | 2025-03-19 | Mar | 2025
FORTPORTAL | KASESE | MT ST MARY'S HOSPOTIALS KILEMBE | 2024-12-23 | Gap in mentorship | Staff to to be trained at the RRH | Lab manger and regionalization |  | MB_AMR | 2024-12-23
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | Culture test | Recommend to MoH | MoH |  | MB_AMR | 2024-12-16
GULU | GULU | KITGUM GENERAL HOSPITAL | 2025-08-08 | The site should be accedited and capacity building performed |  |  |  | MB_AMR | 2025-08-08
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Inadequate workspace that compromises biosafety and bio-security of staff | Request MoH to support infructructure improvements to suit the current demands | Matayo, Dr Peter | Immediate | MB_AMR | 2025-08-08
GULU | KITGUM | ST. JOSEPH'S HOSPITAL KITGUM | 2025-03-21 | Staff not trained on AMR | Laise with with competent institutions for support | Quality Officer | 30/4/2025 | MB_AMR | 2025-03-21
GULU | OMORO | BOBI HC3 | 2025-03-21 | NA |  |  |  | MB_AMR | 2025-03-21
GULU | OMORO | BOBI HC3 | 2025-03-21 | NA |  |  |  | MB_AMR | 2025-03-21
GULU | PADER | PAPER HEALTH CENTRE LLL | 2025-03-21 | NA |  |  |  | MB_AMR | 2025-03-21
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | NO EQUIPMENT TO SUPPORT MICROBIOLOGY | ENGAGE GOVT PROVIDE EQUIPMENT TO SUPPORT MICROBIOLOGY | FACILITY MANAGER | IMMEDIATE | MB_AMR | 2026-03-26
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | no competencies on file at the time supervision for Urinalysis and stool analysis | do competencies for stool analysis and urinalysis and file them | lab manager | jan 2025 | MB_AMR | 2024-12-12 | 2025-01-31 | Jan | 2025
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | staff not trained in risk management | IP to support the training | lab advisor | feb 2025 | MB_AMR | 2024-12-11 | 2025-02-28 | Feb | 2025
JINJA | MAYUGE | MAYUGE HC IV | 2026-03-24 | N/A |  |  |  | MB_AMR | 2026-03-24
KAMPALA | KAMPALA | KIRUDDU NATIONAL REFERAL HOSPITAL | 2024-12-19 | Luck of some essential supplies for culture and sensitivity due to instability of deliveries | to have a consistency in supply of lab logistics | Lab manager and NHLDS | 2 months feedback | MB_AMR | 2024-12-19 | 2025-02-19 | Feb | 2025
KAYUNGA | LUWERO | LUWEERO GENERAL HOSPITAL | 2024-12-18 | No Microbiology Lab | Establish Microbiology Lab | IP, MS | March 2025 | MB_AMR | 2024-12-18 | 2025-03-31 | Mar | 2025
KAYUNGA | LUWERO | LUWEERO GENERAL HOSPITAL | 2024-12-18 | No Antibiogram established | Train staff on Microbiology | IP, CPHL | March 2025 | MB_AMR | 2024-12-18 | 2025-03-31 | Mar | 2025
KAYUNGA | LUWERO | LUWERO GENERAL HOSPITAL | 2025-03-12 | Few samples coming in for microbiology gram | Conduct CME to increase utilization of the test | Gerald | April 2025 | MB_AMR | 2025-03-12 | 2025-04-30 | Apr | 2025
KAYUNGA | NAKASONGOLA | NAKASONGOLA HC IV | 2024-12-19 | Lack of Antibiogram, Inadequate Caoacity for Microbiology testing | Refurbish the Microbiology Laboratory, equip Microbiology | IP | April 2025 | MB_AMR | 2024-12-19 | 2025-04-30 | Apr | 2025
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | No formal training of the microbiology test personnel | Skills placement of the personnel at the KRRH | DHO | August 2025 | MB_AMR | 2025-03-11 | 2025-08-31 | Aug | 2025
MASAKA | BUKOMANSIMBI | BUTENGA | 2025-06-25 | No samples being referred for microbilogy testing | utilise the hub for sample referral and results back | all staff | 1 month | MB_AMR | 2025-06-25 | 2025-07-25 | Jul | 2025
MASAKA | KALANGALA | KALANGALA HCIV | 2025-07-31 | staff not trained on AMR surveillance | To train in AMR | RLM,DLFP,IP | 6 Months | MB_AMR | 2025-07-31 | 2026-01-31 | Jan | 2026
MASAKA | KYOTERA | KALISIZO GENERAL HOSPITAL | 2025-07-30 | Lack of AMR surveillance | Train staff in AMR Surveillance | RLM, DLFP | 06 months | MB_AMR | 2025-07-30 | 2026-01-30 | Jan | 2026
MASAKA | LWENGO | LWENGO HEALTH CENTER IV. | 2025-07-28 | Not trained in AMR | To train staff in AMR Surveillance | RLM,IP, DLFP/ Lab in charge | 6 months | MB_AMR | 2025-07-28 | 2026-01-28 | Jan | 2026
MASAKA | LYANTONDE | LYANTONDE GENERAL HOSPITAL | 2025-08-01 | No training in AMR conducted | Conduct training in AMR Surveillance for hospital staff | Regional EOC, RLM, IP, Lab Manager, CPHL | 6 months | MB_AMR | 2025-08-01 | 2026-02-01 | Feb | 2026
MASAKA | MASAKA | MASAKA REGIONAL REFERRAL HOSPITAL | 2024-12-09 | no records of training and competence assessments in microbiology | conduct competence assessment | quality officer | 3 months | MB_AMR | 2024-12-09 | 2025-03-09 | Mar | 2025
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | No gram staining done | Acquire Gram stains | Lab Manager, RLM & CPHL | 06 Months | MB_AMR | 2025-07-29 | 2026-01-29 | Jan | 2026
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | Lack of AMR surveillance training | Train staff in AMR surveillance | RLM, Lab Manager | 06 Months | MB_AMR | 2025-07-29 | 2026-01-29 | Jan | 2026
MASAKA | SEMBABULE | SEMBABULE HC IV | 2025-06-23 | no microbiology service offere for C/S | do refer samples for the tests | lab manager | ongoing | MB_AMR | 2025-06-23
MBALE | BUTALEJA | BUSOLWE HOSPITAL | 2025-04-09 | No available equipment for AMR | Avail with AMR supplies | Lab manager | 6 months | MB_AMR | 2025-04-09 | 2025-10-09 | Oct | 2025
MBALE | BUTALEJA | NABIGANDA HC IV | 2025-04-07 | No microbiology tests done | Request for gram reagents from NMS | Lab manager | May 2025 | MB_AMR | 2025-04-07 | 2025-05-31 | May | 2025
MBALE | TORORO | TORORO GENERAL HOSPITAL | 2025-04-16 | Stock out supplies | IPs and Fleming fund to support | Head of section microbiology | 3 months | MB_AMR | 2025-04-16 | 2025-07-16 | Jul | 2025
MBALE | TORORO | TORORO GENERAL HOSPITAL | 2025-04-16 | Inadequate staff to perform microbiology tests | IPs and government | MS, lab manager and HR | 1 year | MB_AMR | 2025-04-16 | 2026-04-16 | Apr | 2026
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | Lack of trained personnel | Need for an apprenticeship | Mbarara Regional Referral Hospital | 1 month | MB_AMR | 2026-03-31 | 2026-04-30 | Apr | 2026
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | Equipment | To secure equipments required to operate a basic microbiology Laboratory | Facility incharge | up to 6 months | MB_AMR | 2026-03-31 | 2026-09-30 | Sep | 2026
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | Logistics | Need to ensure necessary microbiology reagents are included in facility orders | Facility incharge | 6 months | MB_AMR | 2026-03-31 | 2026-09-30 | Sep | 2026
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | STOCK OUT OF SUPPLIES | NEED FOR IMPROVED ORDER FULFILLMENT | NMS |  | MB_AMR | 2024-12-09
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | UN AVAILABILITY OF CERTAIN DRUGS. | ALWAYS FOLLOW UP ON REQUESTS MADE | NMS |  | MB_AMR | 2024-12-09
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | NA | NA | NA |  | MB_AMR | 2024-12-11
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | Inconsistent supply of microbiology reagents such as media and discs | Adhere to facility orders | NMS | 30 March 2025 | MB_AMR | 2024-12-16 | 2025-03-30 | Mar | 2025
MUBENDE | NAKASEKE | NGOMA HEALTH CENTRE IV | 2025-04-08 | No trained staff for AMR No equipments for culture and sensitivity | To have infrastructure developments to consider the laboratory (microbiology lab ) | Dr.muhereza (facility incharge) | 1 year | MB_AMR | 2025-04-08 | 2026-04-08 | Apr | 2026
SOROTI | AMURIA | AMURIA HOSPITAL | 2025-03-25 | Not applicable |  |  |  | MB_AMR | 2025-03-25
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | Knowledge gap | Train facilitiy personnel | MOH |  | MB_AMR | 2024-12-11
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | Inadequate equipment | Request for equipment | MOH |  | MB_AMR | 2024-12-11
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | Limited space in the microbiology room | Hospital administration should have a plan to remodel lab and create more space | Medical superintendent | when funds are available | MB_AMR | 2025-03-20
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | lack of biosafety cabinet | There is need for the implementing partner to support the facility to purchase a biosafety cabinet. | Implementing partner/Hospital administration | when funds are available | MB_AMR | 2025-03-20
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | Weak back up system | Need to add more batteries and voltage regulator. | Lab manager and AIC | 30/5/2025 | MB_AMR | 2025-03-18
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | Faulty AC | Repair the AC | Lab manager and AIC | 15/04/2025 | MB_AMR | 2025-03-18
SOROTI | KUMI | ATUTUR GENERAL HOSPITAL | 2026-03-25 | N/A |  |  |  | MB_AMR | 2026-03-25
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | No items/ materials to be used for the work | order for supplies from NMS | Lab manager | 26/04/25 | MB_AMR | 2025-03-17
SOROTI | SERERE | SERERE | 2025-08-15 | Staff performing microbiology lab tests, and AMR surveillance NOT trained | train staff | Lab manager | Sept 2025 | MB_AMR | 2025-08-15 | 2025-09-30 | Sep | 2025
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | NO equipment for culture | order from NMS | Administration | 30/04/25 | MB_AMR | 2025-03-19
SOROTI | SERERE | SERERE HEALTH CENTER IV | 2026-03-20 | Inadequate staffing | Recruitment | CAO/HR | Ongoing | MB_AMR | 2026-03-20
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | Stockouts of Antibiotics | Timely request | Laboratory Manager | (Next cycle (3 months from now) | MB_AMR | 2025-03-21
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | Inadequate staffing | Recruite more staff | HR/MOH/Ministry of Public Service |  | MB_AMR | 2025-03-21
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | Inadequate space | Expansion of available space | Hospital admin/ MOH |  | MB_AMR | 2025-03-21
SOROTI | SOROTI CITY | SOROTI | 2025-08-18 | inadequate/no supplies for vital tests | place orders to NMS | EPAJA JOHN | 30TH SEPT 2025 | MB_AMR | 2025-08-18 | 2025-09-30 | Sep | 2025