## Sheet 1
RRH | District | HFacility | VDate | Identified Gap | Agreed Action Point | Institution Responsible | Timelines | Section | VDate_date | due_date | ActionMonth | ActionYr
ENTEBBE | GOMBA | MADDU HC IV | 2025-04-10 | the riders need to always be given enough fuel for continuity of the sample network | IP | June/2025 |  | nsrtn | 2025-04-10
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2024-12-09 | To have the service schedule for the bikes | IP and hub coordinator | 1 month |  | nsrtn | 2024-12-09
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2025-04-14 | to requisition fuel in time | Riders | by next quarter June 2025 |  | nsrtn | 2025-04-14
ENTEBBE | WAKISO | WAKISO HEALTH CENTRE IV | 2024-12-12 | to have a defined service schedule for the bikes | IP and Mary hub coordinator | immediately |  | nsrtn | 2024-12-12
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | Follow up with Baylor to improve on Bike servicing | National Hub coordinator | 31st January 2025 |  | nsrtn | 2024-12-20
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | Reducing on TAT to 7 days | Faridah / Rebecca | 31st January 2025 |  | nsrtn | 2024-12-20
FORTPORTAL | KASESE | MT ST MARY'S HOSPOTIALS KILEMBE | 2024-12-23 | Mentorship | Regionalization's |  |  | nsrtn | 2024-12-23
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | Renewing contracts between supplier and IPs. | National hub coordinator. |  |  | nsrtn | 2024-12-16
GULU | AGAGO | DR. AMBROSOLI MEMORIAL KALONGO | 2025-08-08 | GETTING A NEW NUMBER PLATE | LAB MANAGER AND JCRC | 6 MONTHS |  | nsrtn | 2025-08-08
GULU | AMURU | ATIAK HEALTH CENTRE | 2025-08-08 | Continuous engagement of the IP | Hub DHO | 30/9/2025 |  | nsrtn | 2025-08-08
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2024-12-17 | Recruit a back up rider | Laboratory manager | 6 months |  | nsrtn | 2024-12-17
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Request MoH to include the position of Hub riders in the scheme of service at Health Service Commision or District Local Goverment levels | Matayo, Dr Peter | Immediate |  | nsrtn | 2025-08-08
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2024-12-17 | Provide timely written notification for hub bike service | Hub riders | 3 months |  | nsrtn | 2024-12-17
GULU | KITGUM | ST. JOSEPH'S HOSPITAL KITGUM | 2025-03-21 | facility to allocate resources to transport samples to the HUB | Medical superintendent |  |  | nsrtn | 2025-03-21
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | The hub system to be re-instated | Hub coordinator and UNHLS | 2025/2026 FY |  | nsrtn | 2025-03-20
GULU | NWOYA | KOCHGOMA HCIII | 2025-03-21 | The district to provide a plan on how to transport samples and results to and from the hub | DLFP | June 2025 |  | nsrtn | 2025-03-21
GULU | OMORO | BOBI HC3 | 2025-03-21 | To develop creteria and tools for use | Lab manager | Immediately |  | nsrtn | 2025-03-21
GULU | OMORO | LALOGI HC IV | 2024-12-18 | Follow up with the implementing partner on issue of fuel and data bundles | Laboratory manager | 3 months |  | nsrtn | 2024-12-18
GULU | PADER | PAJULE HCIV | 2025-08-08 | Follow up with the district health office to ensure computer Systems are put in the district procurement plan | DLFP and Lab Manager | Immediate and by end of August 2025 |  | nsrtn | 2025-08-08
GULU | PADER | PAJULE HCIV | 2025-08-08 | Update the rejection form to include lab number for tracking rejected samples | Quality Officer | 31/08/2025 |  | nsrtn | 2025-08-08
GULU | PADER | PURANGA HCIII | 2025-03-28 | Provide records of samples rejection as required | Lab in charge | Immediately |  | nsrtn | 2025-03-28
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | ENGAGE STAKEHOLDERS PROCURE PHONES FOR SAMPLE TRACKING | HUB COORDINATOR | IMMEDIATE |  | nsrtn | 2026-03-26
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | ENGAGE STAKEHOLDERS PROVIDE FUNDING FOR MOTORCYCLE SERVICING AND REPAIR | FACILITY MANAGER | IMMEDIATE |  | nsrtn | 2026-03-26
JINJA | BUGWERI | BUSESE HC IV | 2026-03-20 | ENGAGE WITH THE IPs TO REAPIR AND MANTAIN THE MOTORCYCLES | FACILITY MANAGER | IMMEDIATE |  | nsrtn | 2026-03-20
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | IP to recuit a backup at the facility | MJAP lab advisor | jan 2025 |  | nsrtn | 2024-12-09
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | IP to provide the backup rider | MJAP | JAN 2025 |  | nsrtn | 2024-12-12
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | IP to support recuit the backup rider | Lab advisor MJAP | FEB 2025 |  | nsrtn | 2024-12-11
JINJA | MAYUGE | ST FRANCIS BULUBA GENERAL HOSPITAL | 2026-03-19 | LOOBY FOR MORE FUNDING FROM IPS | FACILITY MANAGER | IMMEDIATE |  | nsrtn | 2026-03-19
JINJA | NAMAYINGO | BUYINJA HC IV | 2026-03-09 | FOLLLOW UP ON CPHL | DLFP, HUB COORDINATOR | IMMEDIATE |  | nsrtn | 2026-03-09
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | IP TO RECURIT A BACKUP RIDER | MJAP | JAN 2025 |  | nsrtn | 2024-12-16
KABALE | KISORO | KISORO HOSPITAL | 2024-12-09 | Follow up with UVRI and NHLDS for missing results | Laboratory manager | 12/12/2024 |  | nsrtn | 2024-12-09
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Calculate the TAT of every test confirmed | Emma | Routine |  | nsrtn | 2025-03-14
KAYUNGA | LUWERO | LUWERO GENERAL HOSPITAL | 2025-03-12 | calculate the TAT and follow up on delays | Namubiru | April 2025. On going |  | nsrtn | 2025-03-12
KAYUNGA | NAKASONGOLA | NABISWERA HEALTH CENTER IV | 2025-03-11 | Record sample receipt date | Aliwaari Anthony & Ocuka Samuel | Daily |  | nsrtn | 2025-03-11
KAYUNGA | NAKASONGOLA | NABISWERA HEALTH CENTER IV | 2025-03-11 | Calculate TAT and fill column for TAT | Aliwaari Anthony & Ocuka Samuel | Daily |  | nsrtn | 2025-03-11
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | Record the date results received | Francis | Daily |  | nsrtn | 2025-03-11
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | Present on TAT and rejection | Lillian | April 2025 |  | nsrtn | 2025-03-11
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | Capture the sample rejection in column | Francis | Daily |  | nsrtn | 2025-03-11
MASAKA | BUKOMANSIMBI | BUTENGA | 2025-06-25 | establish the book to moniter rejections | QO | 2 month |  | nsrtn | 2025-06-25
MASAKA | KYOTERA | KALISIZO GENERAL HOSPITAL | 2025-07-30 | Refresher training in ALIS | IT officer RRH | 03 month |  | nsrtn | 2025-07-30
MASAKA | LYANTONDE | LYANTONDE GENERAL HOSPITAL | 2025-08-01 | Use the sample rejection documents | Lab Manager, Quality Officer | 1 month |  | nsrtn | 2025-08-01
MASAKA | MASAKA | MASAKA REGIONAL REFERRAL HOSPITAL | 2024-12-09 | follow up servicing of hub motor cycles | hub cordinator and IDI officer | 3 months |  | nsrtn | 2024-12-09
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | Use the ALIS module to document rejected samples | Lab Manager | 06 months |  | nsrtn | 2025-07-29
MBALE | BUDUDA | BUDUDA DISTRICT HOSPITAL | 2025-04-01 | Follow up with CPHL | Hub coordinator | 2 weeks |  | nsrtn | 2025-04-01
MBALE | BUSIA | MASAFU HOSPITAL | 2025-04-11 | Follow up with IP | Hub coordinator | 30, June, 2025 |  | nsrtn | 2025-04-11
MBALE | BUTALEJA | NABIGANDA HC IV | 2025-04-07 | Monitor on the system | Lab manager, hub coordinator | June 2025 |  | nsrtn | 2025-04-07
MBALE | MBALE CITY | MBALE REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Lobby for funding | Lab manager | October 2025 |  | nsrtn | 2025-08-08
MBALE | MBALE CITY | MBALE REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Document rejected samples | Hub coordinator | September 2025 |  | nsrtn | 2025-08-08
MBALE | TORORO | TORORO GENERAL HOSPITAL | 2025-04-16 | Monitor on the VL dashboard routinely | Hub coordinator | 3 months |  | nsrtn | 2025-04-16
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | Laiase with IT teams | IT, Facility/CPHL |  |  | nsrtn | 2024-12-11
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | Follow up with the supply chain management/ send EID samples to CPHL for testing | LOGISTICS, Facility/CPHL |  |  | nsrtn | 2024-12-11
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | Make a request for one/Repair the faulty one | IP(TASO) |  |  | nsrtn | 2024-12-13
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | Continuous follow up on requests made | NMS/CPHL Logistics |  |  | nsrtn | 2024-12-13
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2024-12-20 | followup with hub coordinator to check results from the dashboard | Hub coordinator | January 2025 |  | nsrtn | 2024-12-20
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2024-12-20 | Buy data bundles | ANECCA | January 2025 |  | nsrtn | 2024-12-20
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | Follow up with the hub coordinator to check results from the dashboard | Hubcoordinator | January 2025 |  | nsrtn | 2024-12-17
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | This to be addressed to the Hub coordinator to ensure hub riders reach the facility twice in a week | Hubcoordinator/Lab. In charge | January 2025 |  | nsrtn | 2024-12-17
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | Contact the hub to deliver the SST | Hubcoordinator | January 2025 |  | nsrtn | 2024-12-17
MUBENDE | KASSANDA | KASSANDA HEALTH CENTRE IV | 2024-12-13 | To make requisitions to IP for stationery and to also lobby increament on the stationery budget | Hub Coordinator | 15th/Jan/2025 |  | nsrtn | 2024-12-13
MUBENDE | MITYANA | MITYANA HOSPITAL | 2024-12-12 | To lobby from the IP for a 3rd hub rider to ensure no service interrruptions | Hub Coordinator (Jimmy Kakaire) | 30th/Mar/2025 |  | nsrtn | 2024-12-12
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | Need to strengthen communication during transit of samples | MRRH,MOH-CPHL and UVRI |  |  | nsrtn | 2024-12-16
MUBENDE | NAKASEKE | NGOMA HEALTH CENTRE IV | 2025-04-08 | To contact the baylor team for further investigation of the matter | Hub coordinator (Adowa molly) | 2 weeks |  | nsrtn | 2025-04-08
MUBENDE | NAKASEKE | NGOMA HEALTH CENTRE IV | 2025-04-08 | Baylor team to be contact and find out the root cause. | Hub ccordinator.(Adowa molly ) | 3 weeks |  | nsrtn | 2025-04-08
SOROTI | AMURIA | AMURIA GENERAL | 2025-08-22 | Hospital to plan for a power back-up system | Lab manager | 2025/26 FY |  | nsrtn | 2025-08-22
SOROTI | AMURIA | AMURIA GENERAL | 2025-08-22 | request for engagement of a backup rider | Hub coordinator | 30th Aug 2026 |  | nsrtn | 2025-08-22
SOROTI | AMURIA | AMURIA HOSPITAL | 2025-03-25 | Recruit a back up hub rider. | Implementing partner(AIC) | 30/6/2035 |  | nsrtn | 2025-03-25
SOROTI | AMURIA | AMURIA HOSPITAL | 2025-03-25 | Follwo up with implemneting partner(AIC) on internet bundles. | Lab manager/AIC | 31/3/2025 |  | nsrtn | 2025-03-25
SOROTI | KABERAMAIDO | KABERAMAIDO GENERAL | 2025-08-21 | IP to provide data bundles for riders on regular basis | Timothy | 01/oct/2025 |  | nsrtn | 2025-08-21
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2025-03-24 | Follow up with the implementing partner on the internet bundles. | Lab manager/Hub coordinator | 30/04/2025 |  | nsrtn | 2025-03-24
SOROTI | KAPELEBYONG | KAPELOBYONG | 2025-08-19 | AIC to provide enough fuel for riders | Timothy | OCT 2025 |  | nsrtn | 2025-08-19
SOROTI | KATAKWI | KATAKWI GENERAL | 2025-08-20 | make reminders | HUB COORDINATOR | 30TH SEPT 2025 |  | nsrtn | 2025-08-20
SOROTI | KATAKWI | KATAKWI GENERAL | 2025-08-20 | AIC to revive quarterly hub review meetings to enable hubs to handle issues wit sample delays within the district | TIMOTHY | 30TH SEPT 2025 |  | nsrtn | 2025-08-20
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | Always check the VL dashboard to print the results timely | lab manager | Immediate |  | nsrtn | 2024-12-11
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | Follow up with the implementing partner on internet bundles and motorcycle repairs. | Hub coordinator | 30/03/2025 |  | nsrtn | 2025-03-20
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | Request for data from the implementing partner. | Hub coordinator | 31/03/2025 |  | nsrtn | 2025-03-18
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | Engage facility staff and encourage timely packaging of samples. | Hub coordinator | 30/4/2025 |  | nsrtn | 2025-03-18
SOROTI | KUMI | ATUTUR HOSPITAL | 2024-12-10 | Write to Management at CPHL | Lab manager | 1 week |  | nsrtn | 2024-12-10
SOROTI | KUMI | ATUTUR HOSPITAL | 2024-12-10 | Train facilities in BSBS | CPHL | 1 month |  | nsrtn | 2024-12-10
SOROTI | NGORA | NGORA | 2025-08-13 | SRRH to include in the budget of regionalization | SRRH TEAM | 2025/26 FY |  | nsrtn | 2025-08-13
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | procure a new bike | MOH and AIC | 26/04/25 |  | nsrtn | 2025-03-17
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | procure airtime | AIC | 25/03/25 |  | nsrtn | 2025-03-17
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | procuring of centrifuges | DLFP | 30/04/25 |  | nsrtn | 2025-03-19
SOROTI | SERERE | SERERE HEALTH CENTER IV | 2026-03-20 | MOH /IP to provide fuel card | MOH/ IP | Ongoing |  | nsrtn | 2026-03-20
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | IP to provide adequate data/internet connectivity bundles | Hub Cordinator | one month (By 21/04/2025) |  | nsrtn | 2025-03-21
SOROTI | SOROTI CITY | SOROTI | 2025-08-18 | AIC to identify alternative sources of fuel | Timothy | 2025/2026 Cop YEAR |  | nsrtn | 2025-08-18
SOROTI | SOROTI CITY | SOROTI | 2025-08-18 | AIC to ensure there is consistent data provision to the riders | Timothy | 2025/2026 Cop year |  | nsrtn | 2025-08-18