## Sheet 1
RRH | District | HFacility | VDate | Identified Gap | Agreed Action Point | Institution Responsible | Timelines | Section | VDate_date | due_date | ActionMonth | ActionYr
ENTEBBE | GOMBA | GOMBE GENERAL HOSPITAL. | 2025-04-10 | To lobby for the funds to service the X-ray to life. | Dr. mbugga (Medical superitendant. | 4 months. |  | Radighy | 2025-04-10
ENTEBBE | GOMBA | MADDU HC IV | 2025-04-10 | to recruit a Radiographer/acquire an X-Ray machine | DHO | Long time project |  | Radighy | 2025-04-10
ENTEBBE | MPIGI | MPIGI HCIV LABORATORY | 2025-04-09 | to acquire X-Ray equipment | DHO/District | by end of 2025 |  | Radighy | 2025-04-09
ENTEBBE | WAKISO | KASANGATI HEALTH CENTRE III | 2024-12-16 | To have x-ray and scan machine at health centre. | Facility incharge | 4 months. |  | Radighy | 2024-12-16
ENTEBBE | WAKISO | KOMAMBOGA HEALTH CENTRE III | 2024-12-13 | To have atleast a scan procured for komamboga health centre III | Facility incharge | 4 months for feedback |  | Radighy | 2024-12-13
ENTEBBE | WAKISO | WAKISO HEALTH CENTRE IV | 2024-12-12 | to lobby for the new ultra sound scan and an x-ray machine. | DHO | 3 months |  | Radighy | 2024-12-12
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | X-RAY servicing and replay, Procure new X-ray Machine | Medical Supretendant/ MOH | 1year |  | Radighy | 2024-12-20
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | Ibrahim Mugerwa | 2months |  |  | Radighy | 2024-12-20
FORTPORTAL | KASESE | MT ST MARY'S HOSPOTIALS KILEMBE | 2024-12-23 | Certification of X-ray | Lukyamuzi Collins ,Medical Superindetendant | 31st January 2025 |  | Radighy | 2024-12-23
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | Recommend radiology testing | MoH |  |  | Radighy | 2024-12-16
GULU | NWOYA | ANAKA GENERAL HOSPITAL | 2025-08-08 | Informed the ministry engineers | Hospital supretendant | On going |  | Radighy | 2025-08-08
GULU | PADER | PAJULE HC IV | 2024-12-19 | Procure the radiation protection gadgets | Facility incharge | 6 months |  | Radighy | 2024-12-19
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | Facility to lobby for xray through the DHO's office | DHO | DEC 2025 |  | Radighy | 2024-12-09
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | workshop should access the problem with the xray and give a report | MS | FEB 2025 |  | Radighy | 2024-12-12
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | IP to lobby for acquiring an XRAY at the hospital | MJAP | DEC 2025 |  | Radighy | 2024-12-16
KABALE | KISORO | KISORO HOSPITAL | 2024-12-09 | hospital administration followed up with MoH and New machine is soon getting delivered | Medical superintendent | Jan 2025 |  | Radighy | 2024-12-09
KAYUNGA | LUWERO | LUWEERO GENERAL HOSPITAL | 2024-12-18 | IP, CPHL | March 2025 |  |  | Radighy | 2024-12-18
MASAKA | KALANGALA | KALANGALA HCIV | 2025-07-31 | construct a Radiology department | Facility in charge ,DHO | 1 YEAR |  | Radighy | 2025-07-31
MASAKA | KYOTERA | KALISIZO GENERAL HOSPITAL | 2025-07-30 | Install the machine | Administration | 06 months |  | Radighy | 2025-07-30
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | RLM, Lab Manager | 06 Months |  |  | Radighy | 2025-07-29
MBALE | BUSIA | MASAFU HOSPITAL | 2025-04-11 | Follow up with MS | Radiology incharge | 3 months |  | Radighy | 2025-04-11
MBALE | PALLISA | PALLISA HOSPITAL | 2025-04-02 | Follow up with the MS | Head of radiology | 4 months |  | Radighy | 2025-04-02
MBALE | TORORO | TORORO GENERAL HOSPITAL | 2025-04-16 | MS, lab manager and HR | 1 year |  |  | Radighy | 2025-04-16
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | Facility incharge | up to 6 months |  | Logistics | Radighy | 2026-03-31
MBARARA | MBARARA | BIHARWE HEALTH CENTRE | 2026-03-31 | Facility incharge | 6 months |  |  | Radighy | 2026-03-31
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | NMS |  |  |  | Radighy | 2024-12-09
MUBENDE | MITYANA | MITYANA HOSPITAL | 2024-12-12 | To make an emergency order for the xray films froM NMS | Head radiology, Head pharmacy | 30th/jan/2024 |  | Radighy | 2024-12-12
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | X-ray needs to be repaired as soon as possible | MRRH and MOH Engineering departments | 30 January 2025 |  | Radighy | 2024-12-16
MUBENDE | NAKASEKE | NGOMA HEALTH CENTRE IV | 2025-04-08 | To lobby for an ultra sound scan | Dr. Muhereza (in charge facility) | 4 months |  | Radighy | 2025-04-08
SOROTI | AMURIA | AMURIA GENERAL | 2025-08-22 | lobby for radiology equipment for the facility | facility incharge | 2025/26 FY |  | Radighy | 2025-08-22
SOROTI | KABERAMAIDO | KABERAMAIDO GENERAL | 2025-08-21 | request for X-ray films from NMS | Radiologist | 30th Sept 2025 |  | Radighy | 2025-08-21
SOROTI | KALAKI | LWALA | 2025-08-20 | THE DEPARTMENT HEAD TO PLACE REQUEST FOR THE ITEMS FROM JMS | RADIOGRAPHER | 30TH SEPT 2025 |  | Radighy | 2025-08-20
SOROTI | KAPELEBYONG | KAPELOBYONG | 2025-08-19 | recruit and post a senographer | DHO | 2025/2026 FY |  | Radighy | 2025-08-19
SOROTI | KATAKWI | KATAKWI GENERAL | 2025-08-20 | equipment put out of use awaiting replacement based on the recommendations from Atomic energy team- radiographer to follow up. | Radiographer | 01/sept/2025 |  | Radighy | 2025-08-20
SOROTI | KATAKWI | KATAKWI GENERAL HOSPITAL | 2024-12-11 | MOH |  |  |  | Radighy | 2024-12-11
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | Ensure regular servicing of equipment | Medical superintendent | when funds are available. |  | Radighy | 2025-03-20
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | Implementing partner/Hospital administration | when funds are available |  |  | Radighy | 2025-03-20
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | Purchase new X-ray Machine | Radiology manager and MOH |  |  | Radighy | 2025-03-18
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | Lab manager and AIC | 15/04/2025 |  |  | Radighy | 2025-03-18
SOROTI | KUMI | ATUTUR | 2025-08-18 | request for x-ray films from NMS | Radiologist | 30th Sept 2025 |  | Radighy | 2025-08-18
SOROTI | KUMI | ATUTUR GENERAL HOSPITAL | 2026-03-25 | Recruitment | CAO, HR | On going |  | Radighy | 2026-03-25
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | NA | NA | NA |  | Radighy | 2025-03-17
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | recruit more staff | administration | 30/04/25 |  | Radighy | 2025-03-19
SOROTI | SOROTI | SOROTI | 2024-12-13 | communicate the issue to management and IP | LAB MANAGER | Immediate |  | Radighy | 2024-12-13
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | Recruite more staff | HR/MOH/MIN of Public Servie |  |  | Radighy | 2025-03-21
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2026-03-16 | Recruitement of more staff | HR | Ongoing |  | Radighy | 2026-03-16
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | HR/MOH/Ministry of Public Service |  |  | Inadequate space | Radighy | 2025-03-21
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | Hospital admin/ MOH |  |  |  | Radighy | 2025-03-21
SOROTI | SOROTI CITY | SOROTI | 2025-08-18 | Request for contrast liquid | Radiologist | 30th SEPT 2025 |  | Radighy | 2025-08-18