## Sheet 1
RRH | District | HFacility | VDate | Identified Gap | Agreed Action Point | Institution Responsible | Timelines | Section | VDate_date | due_date | ActionMonth | ActionYr
ENTEBBE | BUTAMBALA | GOMBE HOSPITAL | 2026-02-26 | CME on waste management with emphasis on recording of generated waste | IPC focal person | 1yr |  | BSBS | 2026-02-26
ENTEBBE | GOMBA | GOMBE GENERAL HOSPITAL. | 2025-04-10 | To purchase a weighing scale | Dr.Mbugga | 3 months. |  | BSBS | 2025-04-10
ENTEBBE | GOMBA | MADDU HC IV | 2025-04-10 | Create a schedule for carrying out Biorisk management and the that schedule should be followed | Quality officer | 20/04/2025 |  | BSBS | 2025-04-10
ENTEBBE | GOMBA | MADDU HC IV | 2026-02-25 | Conduct CMEs on waste management | IPC focal person | 6months |  | BSBS | 2026-02-25
ENTEBBE | GOMBA | MADDU HC IV | 2025-04-10 | acquire a weighing scake | lab incharge/Fcaility head | by June 2025 |  | BSBS | 2025-04-10
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2024-12-09 | Hospital director to procure the weighing scale for the laboratory. | Kiyonga edward (lab manager) | 1 month |  | BSBS | 2024-12-09
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFERRAL HOSPITAL | 2025-04-14 | to buy a weighing scale | HD | By 2025/26 FY |  | BSBS | 2025-04-14
ENTEBBE | WAKISO | ENTEBBE REGIONAL REFFERAL HOSPITAL | 2026-02-24 | obtain records or guidelines for waste management | IPC focal person | 1 month |  | BSBS | 2026-02-24
ENTEBBE | WAKISO | KASANGATI HEALTH CENTRE III | 2024-12-16 | To properly segregate the waste generated. | Laboratory incharge | immediately. |  | BSBS | 2024-12-16
ENTEBBE | WAKISO | KASANGATI HEALTH CENTRE III | 2024-12-16 | To have the procedure in the waste management SOP documented. | Biosafety officer and lab manager. | Immediately. |  | BSBS | 2024-12-16
ENTEBBE | WAKISO | KOMAMBOGA HEALTH CENTRE III | 2024-12-13 | To procure the weighing scale in order to weigh the waste generated. | Facility incharge | 3 months |  | BSBS | 2024-12-13
ENTEBBE | WAKISO | KOMAMBOGA HEALTH CENTRE III | 2024-12-13 | To decontaminate all the waste generated before disposal. | Kerchan Ronald | 2 months |  | BSBS | 2024-12-13
ENTEBBE | WAKISO | WAKISO HEALTH CENTRE IV | 2024-12-12 | procure a weighing scale and the lab to update the SOP and implement it. | Quality manager .Nassali maryam | immediately |  | BSBS | 2024-12-12
ENTEBBE | WAKISO | WAKISO IV | 2026-02-27 | Training in regards to this area | Lab manager | 1yr |  | BSBS | 2026-02-27
FORTPORTAL | BUNDIBUGYO | BUNDIBUGYO GENERAL HOSPITAL | 2024-12-20 | Admin should train one more staff on incineration of HCW | Lab Manager | 31st January 2025 |  | BSBS | 2024-12-20
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | Need guidance on standard incinerator | MS, Safety officer, National BRM |  |  | BSBS | 2024-12-16
FORTPORTAL | KYEGEGWA | KYEGEGWA GENERAL HOSP | 2024-12-16 | To discuss with MS |  |  |  | BSBS | 2024-12-16
GULU | AGAGO | DR AMBROSOLI MEMORIAL HOSPITAL-KALONGO | 2024-12-23 | Procure the weighing scale | Laboratory manager | 3 months |  | BSBS | 2024-12-23
GULU | AMURU | ATIAK HEALTH CENTRE | 2025-08-08 | Awareness creation | facility safety officer | 30th sept 2025 |  | BSBS | 2025-08-08
GULU | AMURU | ATIAK HEALTH CENTRE | 2025-08-08 | the management to ensure procurement waste weighing scale | Lab manager | 30th sept 2025 |  | BSBS | 2025-08-08
GULU | GULU | PATIKO H/CIII | 2025-03-20 | Conduct the training on BRM |  |  |  | BSBS | 2025-03-20
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2024-12-17 | Procure weighing scale and have the waste generated recorded | Laboratory Manager | 6 months |  | BSBS | 2024-12-17
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Allocate a budget to support procurement of Waste weighing equipment | Matayo | Immediate |  | BSBS | 2025-08-08
GULU | GULU CITY | GULU REGIONAL REFERRAL HOSPITAL | 2024-12-17 | schedule and conduct the audit | Angom Bena | 3 months |  | BSBS | 2024-12-17
GULU | GULU CITY | ST MARY'S HOSPITAL LACOR | 2025-03-21 | Develop schedule for safety assessment and implement risk assessment | Safety Officer ( Ocholi Geoffrey) | 30th March 2025 |  | BSBS | 2025-03-21
GULU | GULU CITY | ST MARY'S HOSPITAL LACOR | 2025-03-21 | Develop logs for recording lab wastes before final disposal | Safety Officer | 30th march 2025 |  | BSBS | 2025-03-21
GULU | KITGUM | KITGUM GENERAL HOSPITAL | 2024-12-20 | Routinely quantify the waste | Laboratory Manager | 6 months |  | BSBS | 2024-12-20
GULU | KITGUM | ST. JOSEPH'S HOSPITAL KITGUM | 2025-03-21 | Conduct CME and label waste bins to guidebins | Safety officer (Omony) | 30/3/2025 |  | BSBS | 2025-03-21
GULU | LAMWO | PALABEK KAL HCIV | 2025-03-20 | Facility to acquire wast management tools | Lab incharge | 2025/2026 |  | BSBS | 2025-03-20
GULU | NWOYA | ANAKA GENERAL HOSPITAL | 2025-08-08 | Start recording waste generated in the lab | The cleaner | Immediately |  | BSBS | 2025-08-08
GULU | NWOYA | KOCHGOMA HCIII | 2025-03-21 | Include the safety requirements into the work and structural plans by the district | DLFP | June 2025 |  | BSBS | 2025-03-21
GULU | NWOYA | KOCHGOMA HCIII | 2025-03-21 | Display of safety signages in proper | Laboratory manager | June 2025 |  | BSBS | 2025-03-21
GULU | OMORO | LALOGI HC IV | 2024-12-18 | quantify waste being generated and disposed | Laboratory manager | 3 months |  | BSBS | 2024-12-18
GULU | PADER | PAJULE HC IV | 2024-12-19 | Procure an incinerator | Laboratory manager and Facility incharge | 6 months |  | BSBS | 2024-12-19
GULU | PADER | PAJULE HCIV | 2025-08-08 | Following the internal audits schedule | Quality Officer | 30/09/2025 |  | BSBS | 2025-08-08
GULU | PADER | PAJULE HCIV | 2025-08-08 | Develop a tool to help monitor waste decontamination before disposal | Safety officer | 15/08/2025 |  | BSBS | 2025-08-08
GULU | PADER | PAJULE HCIV | 2025-08-08 | Develop a tool to help monitor quantity of waste generated per day before final disposal | Safety officer | 15/08/2025 |  | BSBS | 2025-08-08
GULU | PADER | PURANGA HCIII | 2025-03-28 | There is no equipment /system of recording waste at HCIII |  |  |  | BSBS | 2025-03-28
JINJA | BUGIRI | BUGIRI GENERAL HOSPITAL | 2026-03-26 | ENGAGE STAKEHOLDERS HAVE NEW INCINERATOR, WEIGHING SCALE | FACILITY MANAGER, DHO, CAO | IMMEDIATE |  | BSBS | 2026-03-26
JINJA | BUGIRI | NANKOMA HC IV | 2026-03-25 | ENGAGE GOVT AND IPs TO PROCURE AN INCINERATOR | FACILITY MANAGER, DHO, CAO | IMMEDIATE |  | BSBS | 2026-03-25
JINJA | BUGWERI | BUSESE HC IV | 2026-03-20 | ENGAGE ADMINISTRATION FOR AN INCINERATOR | DAVIS | IMMEDIATE |  | BSBS | 2026-03-20
JINJA | BUGWERI | BUSESE HC IV | 2026-03-20 | ENGAGE HOSPITAL ADMINISTARTION FOR WEIGHING SCALE | DAVIS | IMMEDIATE |  | BSBS | 2026-03-20
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | BMR audit to be conducted | Quality officer | Feb 2025 |  | BSBS | 2024-12-09
JINJA | BUYENDE | KIDERA HEALTH CENTRE IV | 2024-12-09 | Always record the waste generated in the lab and document it | Lab manager | Dec 2024 |  | BSBS | 2024-12-09
JINJA | IGANGA | BUGONO HC IV | 2026-03-18 | ALWAYS WAIGH THE WASTES | FACILITY MANAGER | IMMEDIATE |  | BSBS | 2026-03-18
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | Record all waste generate in the laboratory | safety officer | Jan 2025 |  | BSBS | 2024-12-12
JINJA | IGANGA | IGANGA GENERAL HOSPITAL | 2024-12-12 | Monitor atleast one quality indicator in BMR | quality officer | Jan 2025 |  | BSBS | 2024-12-12
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | Record the waste generated in the lab weekly | lab manager | jan 2025 |  | BSBS | 2024-12-11
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | Monitor a BIO-Risk management indicator in the lab | safety officer | feb 2025 |  | BSBS | 2024-12-11
JINJA | KAMULI | KAMULI GENERAL HOSPITAL | 2024-12-11 | develop a continuity and emergency preparedness plan for the lab | quality officer | feb 2025 |  | BSBS | 2024-12-11
JINJA | MAYUGE | MAYUGE HC IV | 2026-03-24 | PROPER PALLNING TO PROCURE MORE WASTE BINS AND PPE | LAB MANAGER, DLFP, DHO | JUNE 2026 |  | BSBS | 2026-03-24
JINJA | MAYUGE | MAYUGE HC IV | 2026-03-24 | DHO AND CAO TO ENGAGE STAKEHOLDERS | CAO, DHO, LAB MANAGER | JUNE 2026 |  | BSBS | 2026-03-24
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | record the waste generated in the lab and file | lab manager | JAN 2025 |  | BSBS | 2024-12-16
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | procure and install a automatic smoke detector | MJAP | FEB 2025 |  | BSBS | 2024-12-16
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | Install a biosafety cabinet in the genxpert room | MJAP | DEC 2025 |  | BSBS | 2024-12-16
JINJA | NAMAYINGO | BUYINJA HCIV | 2024-12-16 | repair the lock for the access door to the lab | lab manager | JAN 2025 |  | BSBS | 2024-12-16
KABALE | KISORO | KISORO HOSPITAL | 2024-12-09 | hold meeting with green label team and hospital management to harmonize the issue of irregular picking of waste | laboratory manager | Feb 2025 |  | BSBS | 2024-12-09
KAMPALA | KAMPALA | KIRUDDU NATIONAL REFERAL HOSPITAL | 2024-12-19 | To have the procedure for weighing if waste generated | Biosafety officer. | immediately |  | BSBS | 2024-12-19
KAMPALA | KAMPALA | KIRUDDU NATIONAL REFERAL HOSPITAL | 2024-12-19 | To have aroot cause as to why there is no an incinerator | Biosafety officer | immediately |  | BSBS | 2024-12-19
KAYUNGA | KAYUNGA | KAYUNGA RRH | 2024-12-12 | Safety officer re educated on the need for recording waste and a sheet for recording waste generated | Bridget | Done onsite |  | BSBS | 2024-12-12
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Conduct CME for all staff | Fred | April 2025 |  | BSBS | 2025-03-14
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Follow up with stores to provide functional waste bins | Julius | August 2025 |  | BSBS | 2025-03-14
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Create a template | Fred | April 2025 |  | BSBS | 2025-03-14
KAYUNGA | LUWERO | KALAGALA HEALTH CENTRE IV | 2025-03-14 | Perform Bio risk assessment | Fred | April 2025 |  | BSBS | 2025-03-14
KAYUNGA | LUWERO | LUWEERO GENERAL HOSPITAL | 2024-12-18 | Request for more waste bins for all categories of waste | Biosafety Officer | 20-12-2024 |  | BSBS | 2024-12-18
KAYUNGA | LUWERO | LUWEERO GENERAL HOSPITAL | 2024-12-18 | Train srtaff on waste management | Biosafety officer | 31-12-2024 |  | BSBS | 2024-12-18
KAYUNGA | LUWERO | LUWERO GENERAL HOSPITAL | 2025-03-12 | Conduct Bio risk assessment | Nathan | March 2025 |  | BSBS | 2025-03-12
KAYUNGA | LUWERO | LUWERO GENERAL HOSPITAL | 2025-03-12 | Put all colour bin types in one place [testing area]. | Nathan | March 2025. April 2025 |  | BSBS | 2025-03-12
KAYUNGA | LUWERO | LUWERO GENERAL HOSPITAL | 2025-03-12 | CME to students before placement | Nathan and Gerald | On going |  | BSBS | 2025-03-12
KAYUNGA | LUWERO | LUWERO GENERAL HOSPITAL | 2025-03-12 | Print waste segregation guides and display | Nathan | April 2025 |  | BSBS | 2025-03-12
KAYUNGA | NAKASONGOLA | NABISWERA HEALTH CENTER IV | 2025-03-11 | Make orders to NMS provide bins as the current ones have been used beyond their recommended timeframe | CPHL/NMS | August 2024 |  | BSBS | 2025-03-11
KAYUNGA | NAKASONGOLA | NAKASONGOLA HC IV | 2024-12-19 | Construct Incinerator, Gazette waste holding area, Record all wastes generated before disposal, Perform safety drills | Lab Director, Lab Manager, Safety officer | April 2025 |  | BSBS | 2024-12-19
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | Conduct BRM assessment | David and Daniel | April 2025 |  | BSBS | 2025-03-11
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | Share BRM assessment tool | Joy Mary | March 2025 |  | BSBS | 2025-03-11
KAYUNGA | NAKASONGOLA | NAKASONGOLA HEALTH CENTER IV | 2025-03-11 | Develop a waste record tool | Lillian | March 2025 |  | BSBS | 2025-03-11
MASAKA | BUKOMANSIMBI | BUTENGA | 2025-06-25 | proper segregation | staff | immediately |  | BSBS | 2025-06-25
MASAKA | BUKOMANSIMBI | BUTENGA | 2025-06-25 | mentordhips.cmes | incharge lab | 2 month |  | BSBS | 2025-06-25
MASAKA | KALANGALA | KALANGALA HCIV | 2025-07-31 | facility to construct an incinerator | facility in charge ,DHO,IP | 1 Year |  | BSBS | 2025-07-31
MASAKA | KYOTERA | KALISIZO GENERAL HOSPITAL | 2025-07-30 | Construct an incinerator | Hosp management, District | 01 years |  | BSBS | 2025-07-30
MASAKA | KYOTERA | KALISIZO GENERAL HOSPITAL | 2025-07-30 | Design the log | Biosafety Officer | 02 Months |  | BSBS | 2025-07-30
MASAKA | LWENGO | LWENGO HEALTH CENTER IV. | 2025-07-28 | construct an incinerator | DHO/incharge | 1 year |  | BSBS | 2025-07-28
MASAKA | LWENGO | LWENGO HEALTH CENTER IV. | 2025-07-28 | Develop training schedule | lab in charge | 1 month |  | BSBS | 2025-07-28
MASAKA | LWENGO | LWENGO HEALTH CENTRE IV | 2024-12-10 | schedule biorisk management audits | safety officer | 2 months |  | BSBS | 2024-12-10
MASAKA | LYANTONDE | LYANTONDE GENERAL HOSPITAL | 2024-12-11 | repairing incenerator | facility incharge | 3 months |  | BSBS | 2024-12-11
MASAKA | LYANTONDE | LYANTONDE GENERAL HOSPITAL | 2025-08-01 | Develop a log for documenting amount of waste | Biosafety Officer | 2 months |  | BSBS | 2025-08-01
MASAKA | LYANTONDE | LYANTONDE GENERAL HOSPITAL | 2024-12-11 | shedule and implement biorisk management audits | safety officer and lab manager | 2 months |  | BSBS | 2024-12-11
MASAKA | MASAKA | KYANAMUKAAKA | 2025-06-28 | CME on waste managment |  |  |  | BSBS | 2025-06-28
MASAKA | MASAKA | MASAKA REGIONAL REFERRAL HOSPITAL | 2024-12-09 | train staff in risk assessment and conduct risk assessment | safety officer | 2months |  | BSBS | 2024-12-09
MASAKA | MASAKA CITY | KIYUMBA HCIV | 2025-06-24 | waste segregation | ipcfp | august 2025 |  | BSBS | 2025-06-24
MASAKA | MASAKA CITY | KIYUMBA HCIV | 2025-06-24 | cmes on waste managment | lab incharge | sept 2025 |  | BSBS | 2025-06-24
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | Need for an incinerator | DHO, Med Sup, MOH | 01 Year |  | BSBS | 2025-07-29
MASAKA | RAKAI | RAKAI GENERAL HOSPITAL | 2025-07-29 | Avail a budget for waste management | DHO, Med Sup, MOH | 01 Year |  | BSBS | 2025-07-29
MASAKA | SEMBABULE | SEMBABULE HC IV | 2025-06-23 | more cmes on mind change | inchaarge | August |  | BSBS | 2025-06-23
MASAKA | SEMBABULE | SEMBABULE HC IV | 2025-06-23 | lobby for more supplies | incharge | September |  | BSBS | 2025-06-23
MBALE | BUDUDA | BUDUDA DISTRICT HOSPITAL | 2025-04-01 | It should be constructed near the lab | Hospital administration, lab manager |  |  | BSBS | 2025-04-01
MBALE | BUSIA | MASAFU HOSPITAL | 2025-04-11 | Procurement of weighing scale | DHO, facility incharge | July 2025 |  | BSBS | 2025-04-11
MBALE | BUTALEJA | BUSOLWE HOSPITAL | 2025-04-09 | Training or mentorship should be done | Biosafety officer | 3 months |  | BSBS | 2025-04-09
MBALE | BUTALEJA | NABIGANDA HC IV | 2025-04-07 | Develop a log tracking waste produced | Safety officer | June 2025 |  | BSBS | 2025-04-07
MBALE | KAPCHORWA | KAPCHORWA GENERAL HOSPITAL LABORATORY | 2025-04-04 | Lobby for procurement of heavy duty weighing balance | Lab manager | 1st July, 2025 |  | BSBS | 2025-04-04
MBALE | MBALE CITY | MBALE REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Following up with internal auditors to follow schedule | Quality officer | September 2025 |  | BSBS | 2025-08-08
MBALE | MBALE CITY | MBALE REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Ordering of enough supply of waste bin liners from NMS | Logistics officer | September 2025 |  | BSBS | 2025-08-08
MBALE | MBALE CITY | MBALE REGIONAL REFERRAL HOSPITAL | 2025-08-08 | Training of staff in safety practices | Safety officer | October 2025 |  | BSBS | 2025-08-08
MBALE | PALLISA | PALLISA HOSPITAL | 2025-04-02 | Follow up with NMS | Hospital MS , laboratory manager | Next cycle |  | BSBS | 2025-04-02
MBALE | SIRONKO | BUDADIRI HEALTH CENTER IV | 2025-04-14 | To procure weighing scale | Lab manager | June 2025 |  | BSBS | 2025-04-14
MBALE | TORORO | TORORO GENERAL HOSPITAL | 2025-04-16 | Hold refresher training | Safety officer | 3 months |  | BSBS | 2025-04-16
MBARARA | BUSHENYI | ISHAKA ADVENTIST HOSPITAL | 2026-03-16 | Do risk assessments and audits | Administration | 3months |  | BSBS | 2026-03-16
MBARARA | MBARARA | MBARARA HOSPITAL | 2024-12-09 | CONSISTENTLY MONITOR STOCK AND BUY SUFFICIENT DECONTAMINANTS | LOGISTICS OFFICER |  |  | BSBS | 2024-12-09
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | make the incenerator functional functional | BSBS team |  |  | BSBS | 2024-12-11
MBARARA | NTUNGAMO | ITOJO HOSPITAL | 2024-12-11 | Come up with a list of all liquid waste and discuss decontamination methods | BSBS team |  |  | BSBS | 2024-12-11
MBARARA | RUBIRIZI | RUGAZI HCIV | 2024-12-13 | Request for BSBS training of all staff | BSBS officer |  |  | BSBS | 2024-12-13
MBARARA | RUBIRIZI | RUGAZI HCIV | 2026-03-13 | Start QI on waste management | Mellon | 1 week |  | BSBS | 2026-03-13
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2024-12-20 | buy a weighing scale and start weighing wastes produced in the laboratory | laboratory manager | January 2025 |  | BSBS | 2024-12-20
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2024-12-20 | develop a log and keep record of wastes produced | laboratory manager | January 2025 |  | BSBS | 2024-12-20
MOROTO | ABIM | ABIM GENERAL HOSPITAL | 2024-12-20 | procure or repair the biometric system | facility incharge | January 2025 |  | BSBS | 2024-12-20
MOROTO | KOTIDO | KOTIDO GENERAL HOSPITAL | 2026-02-24 | Quality officer to develop and implement laboratory waste register immediately 7 days |  |  |  | BSBS | 2026-02-24
MOROTO | KOTIDO | KOTIDO GENERAL HOSPITAL | 2026-02-24 | Laboratory and hospital management to conduct and document quarterly BRM internal audits |  |  |  | BSBS | 2026-02-24
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | Buy a weighing scale and start weighing wastes produced in the laboratory | Laboratory in charge | January 2025 |  | BSBS | 2024-12-17
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | Develop a log and keep record of wastes produced | Laboratory in charge | January 2025 |  | BSBS | 2024-12-17
MOROTO | NAKAPIRIPIRIT | NAKAPIRIPIRIT HEALTH CENTER III | 2024-12-17 | Avail the colour coded bins and liners and segregate wastes accordingly | Laboratory in charge | January 2025 |  | BSBS | 2024-12-17
MUBENDE | KASSANDA | KASSANDA HEALTH CENTRE IV | 2024-12-13 | A tool to be developed by the incharge and put in waste collection area | Lab Incharge | 15th/Jan/2025 |  | BSBS | 2024-12-13
MUBENDE | MITYANA | MITYANA HOSPITAL | 2024-12-12 | To request for a weighing scle from the hospital administration | Logisctics officer (Nseera Lawrence) | 30th/Jan/2025 |  | BSBS | 2024-12-12
MUBENDE | MITYANA | MITYANA HOSPITAL | 2024-12-12 | To design a tool for recording waste before disposal | Biosafety officer (Nabaterega Safina | 30th/Jan/2025 |  | BSBS | 2024-12-12
MUBENDE | MUBENDE | MUBENDE RRH | 2024-12-16 | To obtain service contracts with service providers | MOH/CPHL and BAYLOR | 30 March 2025 |  | BSBS | 2024-12-16
MUBENDE | NAKASEKE | NGOMA HEALTH CENTRE IV | 2025-04-08 | To lobby for new waste bins | Kiyonga Edward | 2 months. |  | BSBS | 2025-04-08
SOROTI | AMURIA | AMURIA GENERAL | 2025-08-22 | lobby for and incinerator | facility management | 2025/26 FY |  | BSBS | 2025-08-22
SOROTI | AMURIA | AMURIA GH | 2024-12-12 | Conduct training to lower facilities | Region and Central trainers | Immediately |  | BSBS | 2024-12-12
SOROTI | KABERAMAIDO | KABERAMAIDO GENERAL | 2025-08-21 | facility to procure the weighing scale and have record of waste disposed | Rebecca | 15th Sept 2025 |  | BSBS | 2025-08-21
SOROTI | KABERAMAIDO | KABERAMAIDO GENERAL HOSPITAL | 2026-03-17 | To improve order and quantification | HoD | Two weeks |  | BSBS | 2026-03-17
SOROTI | KABERAMAIDO | KABERAMAIDO HOSPITAL | 2025-03-24 | Train at least one lab personnel as a safety officer to handle BRM activities. | Implementing partner(AIC) | 20/06/2025 |  | BSBS | 2025-03-24
SOROTI | KALAKI | LWALA | 2025-08-20 | purchase and always weigh the wastes before disposal | Biorisk Manager | 25th Sept 2025 |  | BSBS | 2025-08-20
SOROTI | KALAKI | LWALA HOSPITAL | 2026-03-17 | Create a temporal area for waste storage | HOD | 30/03/2026 |  | BSBS | 2026-03-17
SOROTI | KALAKI | LWALA HOSPITAL | 2026-03-17 | Purchase a padlock to restrict access to the incenarator | Administration | 30/03/2026 |  | BSBS | 2026-03-17
SOROTI | KALAKI | LWALA HOSPITAL | 2026-03-17 | Purchase of weighing balance | Administration | 17/04/2026 |  | BSBS | 2026-03-17
SOROTI | KAPELEBYONG | KAPELOBYONG | 2025-08-19 | facility mgt to ensure all waste disposed is weighed | facility in charge | 30th SEPT 2025 |  | BSBS | 2025-08-19
SOROTI | KATAKWI | KATAKWI GENERAL | 2025-08-20 | procure the weighing scale and ensure waste is weighed before disposal | medical Sup | 2025/26 FY |  | BSBS | 2025-08-20
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | Implementing partner needs to schedule annual BRM trainings for the laboratory safety officer. | AIC(Biosafety officer to follow up). | 20/04/2025 |  | BSBS | 2025-03-20
SOROTI | KATAKWI | KATAKWI HOSPITAL | 2025-03-20 | Quantify the right bin liners during ordering. | Logistic officer. | 31/03/2025 |  | BSBS | 2025-03-20
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | NMS to supply bin liners as per the order made. | Lab Manager | 30/5/2025 |  | BSBS | 2025-03-18
SOROTI | KUMI | ATURTUR HOSPITAL | 2025-03-18 | Include medium sized bins in the NMS order | Lab Manager | 30/5/2025 |  | BSBS | 2025-03-18
SOROTI | KUMI | ATUTUR | 2025-08-18 | perform risk assessment for the lab | biosafety officer | 30th/sept 2025 |  | BSBS | 2025-08-18
SOROTI | KUMI | KUMI HOSPITAL-ONGINO | 2025-08-22 | identify space for temporary storage of waste | lab manager | ongoing |  | BSBS | 2025-08-22
SOROTI | NGORA | NGORA | 2025-08-13 | procure weighing scale for waste | facility incharge | Sept 2025 |  | BSBS | 2025-08-13
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | request for alcohol for decontamination | Safety officer | 01/04/25 |  | BSBS | 2025-03-17
SOROTI | NGORA | NGORA HC1V | 2025-03-17 | buy a padlock for the waste holding area | Safer officer | 01/04/25 |  | BSBS | 2025-03-17
SOROTI | NGORA | NGORA HCIV | 2026-03-18 | Lobby for incinerator from District/partners | Facility In-charge | Ongoing |  | BSBS | 2026-03-18
SOROTI | NGORA | NGORA HCIV | 2026-03-18 | Restrict access to the open burning pit by fencing | Facility In-charge | Ongoing |  | BSBS | 2026-03-18
SOROTI | SERERE | SERERE | 2025-08-15 | IPC focal person to inform the facility incharge the need for weighing scale for weighing waste | IPC F/P | SEPT 2025 |  | BSBS | 2025-08-15
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | schedule a date for internal audit | safety officer | 19/04/25 |  | BSBS | 2025-03-19
SOROTI | SERERE | SERERE HCIV | 2025-03-19 | fence off the waste holding area | safety officer | 19/04/25 |  | BSBS | 2025-03-19
SOROTI | SOROTI | SOROTI REGIONAL REFERRAL HOSPITAL | 2025-03-21 | Allocate more funding for BRM activities | Laboratory Manager | one month (By 21/04/2025) |  | BSBS | 2025-03-21
SOROTI | SOROTI CITY | SOROTI | 2025-08-18 | allocated days in the duty rosta for handling biorisk assessment | Lab Manager | 30th Aug 2025 |  | BSBS | 2025-08-18
SOROTI | SOROTI CITY | SOROTI | 2025-08-18 | include the plan for purchase of the weighing scale for the waste in the facility work plan and budget for 2025/2026 | lab manager | 30th Aug 2025 |  | BSBS | 2025-08-18